## Worksheet
ID PROJECT | PROJECT NAME | TYPE PROJECT | CLIENT | SEGMEN | PM NAME | AM NAME | PARTNERS | START DATE | END DATE | PLAN | ACHIEVEMENT | DEVIASI | STATUS | REASON OF DELAY | PROJECT VALUE | CATEGORY | LAST UPDATE
PROJ171 | AIRPORT OPERATION CONTROL CENTER BANDARA SOEKARNO HATTA | APPLICATION | ANGKASA PURA II (PERSERO) - BUISH | TMS | ATAM RUSTAM | HIDAYAT KURNIAWAN | PT PINS Indonesia | 01-JAN-17 | 31-AUG-18 | 99.696 | 86.898 | -12.798 | LAG | 8.CR (perubahan yang belum terkendali) & amandemen (customer) | 93655243000 | STRATEGIS | 13/08/2018 14:54:08
PROJ213 | WIFI.ID BALAI PUSTAKA | CONNECTIVITY | BALAI PUSTAKA PT | EMS | SRI NURFALAH | GUSTI AYU MADE MAS MARHAENI |  | 01-JAN-17 | 31-DEC-18 | 100 | 70 | -30.009 | LAG |  | 216000000 | REGULER | 09/08/2018 16:56:20
PROJ7 | PROJECT FTTH DUKUH GOLF KEMAYORAN BOUGENVILLE | SMART BUILDING | AGUNG SEDAYU PROPERTINDO | IBS | PRAKOSA TRIWIBOWO | FAHMI MUHAMMAD HUSIN | PT PRAMINDO IKAT NUSANTARA (PINS) | 18-SEP-14 | 30-SEP-16 | 99.986 | 99.997 | 0.011 | DELAY | 4.Keterlambatan BAST (customer) | 19043050000 | MEDIUM | 10/01/2018 10:54:08
PROJ843 | NAC SOLUTION EDC DIAL UP BANK MANDIRI | CPE & OTHERS | BANK MANDIRI | BMS-1 | MUHAMMAD MASYHUDI | FERY KURNIAWAN | PT Sigma Cipta Caraka, PT Sigma Cipta Caraka | 21-SEP-17 | 07-SEP-18 | 100 | 32.07 | -67.93 | LAG |  | 39960000000 | STRATEGIS | 06/06/2018 14:19:58
PROJ11 | PROJECT PARK LAND AVENUE | SMART BUILDING | SUMMARECON AGUNG TBK | IBS | PRAKOSA TRIWIBOWO | ACHMAD SUTARJONO | PT PRAMINDO IKAT NUSANTARA (PINS) | 01-NOV-15 | 30-DEC-18 | 90.715 | 76.89 | -13.825 | DELAY | 11.Komitmen mitra(termasuk deal harga)(mitra) | 3550000000 | SMALL | 25/04/2018 10:19:49
PROJ834 | JASA PENGADAAN DAN PEMASANGAN BACKBONE FO DATA CENTER DI PERUM PERURI | CPE & OTHERS | PERURI PERUM | FMS | IRWANDI | WIJAYANTO | Koperasi Metropolitan | 19-DEC-17 | 19-MAR-18 | 100 | 100 | 0 | DELAY |  | 443117000 | SMALL | 11/04/2018 16:05:01
PROJ2179 | Layanan Migrasi VSAT ke VPN IP PT. Pegadaian | CONNECTIVITY | PEGADAIAN PT | FMS | FACHRI | ANDIKA PRATAMA PUTRA |  | 01-JUL-18 | 31-OCT-18 |  |  |  | LEAD |  | 248640300000 | STRATEGIS
PROJ1194 | PROJECT PENGEMBANGAN ERP MERAH PUTIH DI PT. VIRAMA KARYA (PERSERO) | APPLICATION | VIRAMA KARYA PT | PCS | RIKA AMALIA SASANTY | MASRUL DINAR |  | 15-FEB-18 | 14-AUG-18 | 99.98 | 97.7 | -2.28 | DELAY |  | 1135766181 | SMALL | 22/05/2018 09:14:37
PROJ1494 | PENGADAAN MATERIAL ELECTRICAL DAN PLUMBING PROYEK RUMAH SUSUN PASAR RUMPUT MANGGARAI JAKARTA SELATAN | SMART BUILDING | PT. LINKADATA CITRA MANDIRI | PCS | HERU IRMAN | FERY KURNIAWAN | PT Sigma Cipta Caraka | 30-APR-18 | 01-MAY-18 |  |  |  | DELAY | 1.Delivery barang/jasa (mitra) | 34296609465 | BIG | 19/07/2018 11:42:39
PROJ1545 | UPGRADE DAN PSB VPN IP DAN 2 BACKHAUL, PSB ASTINET LITE DAN 2 BACKHAUL, DAN MANAGED AP BANK BTPN | CONNECTIVITY | BANK BTPN | BMS-2 | M ISNAINI SAPUTRO | BERTHA DESVIANI PURBA | PT Teltranet Aplikasi Solusi (Telkom Telstra) | 07-MAY-18 | 31-AUG-18 | 0 | 0 | 0 | LEAD |  | 3445000000 | MEDIUM | 08/05/2018 11:26:25
PROJ1109 | PENGADAAN PERANGKAT COMMAND CENTER PT ADHI KARYA (PERSERO) TBK | CPE & OTHERS | ADHI KARYA PT | PCS | ROBIYANTO | DWI PUDJI IRAWATI |  | 03-MAY-18 | 30-APR-18 | 95 | 70 | -25 | DELAY |  | 107890000 | SMALL | 20/04/2018 10:21:37
PROJ1169 | PENGADAAN JASA PENGEMBANG APLIKASI E-PAS & INFRASTRUKTUR PENDUKUNGNYA PT PUPUK SRIWIDJAJA PALEMBANG | APPLICATION | PUPUK SRIWIJAYA | MAS | RIKA AMALIA SASANTY | MUHAMMAD HANIS | PT Infomedia Nusantara | 23-MAR-18 | 28-DEC-18 | 49 | 41.22 | -7.78 | LAG |  | 523800000 | STRATEGIS | 11/07/2018 10:49:03
PROJ1275 | PAKET SISTEM ELEKTRONIK APARTEMENT TOWER 1, HOTEL DAN MALL,PROYEK GREEN SEDAYU TAMAN PALEM JAKARTA | SMART BUILDING | AGUNG SEDAYU PROPERTINDO | IBS | HERU IRMAN | FAHMI MUHAMMAD HUSIN | PT PINS Indonesia, PT PINS Indonesia | 26-MAR-18 | 26-MAR-19 | 0 | 0 | 0 | LEAD |  | 26124999999 | BIG | 02/07/2018 10:49:01
PROJ1755 | PENGADAAN PERANGKAT HARDWARE UNTUK KEBUTUHAN ADMIN KAPAL, KANTOR PUSAT DAN CABANG DENGAN MENGGUNAKAN SKEMA SEAT MANAGEMENT | CPE & OTHERS | PELAYARAN NASIONAL INDONESIA (PELNI) PT | MLS | FAHMI RAHMANTHAHA NURDINSYAH | NAWIN | PT Sigma Cipta Caraka | 26-JUN-18 | 26-JUN-21 | 20 | 20 | 0 | LAG |  | 16205288400 | MEDIUM | 30/05/2018 11:16:04
PROJ1903 | PENGADAAN HYPERCONVERGED STORAGE SERVER DENGAN VIRTUAL MACHINE GATEWAY SCADA PT. PLN | CPE & OTHERS | PERUSAHAAN LISTRIK NEGARA (PERSERO) PLN | ERS | DODI IRAWAN | NASHRI | PT Sigma Cipta Caraka, PT Sigma Cipta Caraka | 20-APR-18 | 25-SEP-18 | 43 | 100 | 57 | LAG | 1.Delivery barang/jasa (mitra) | 1475000000 | STRATEGIS | 02/07/2018 11:28:05
PROJ209 | WIFI.ID BTDC NUSA DUA TAHAP 2 | CONNECTIVITY | BTDC NUSA DUA | THS | SRI NURFALAH | I MADE BUDIANA, SE, MM |  | 01-JAN-17 | 31-DEC-18 | 99.996 | 95 | -4.996 | LAG |  | 20000000 | REGULER | 09/08/2018 16:55:15
PROJ222 | UPGRADE VPN IP & MIGRASI FO SUMMIT OTO FINANCE | CONNECTIVITY | SUMMIT OTO FINANCE | FMS | ARI WIDIYANTO | ARISTYA MEGA PUTRANTO |  | 18-FEB-17 | 01-MAY-17 | 0 | 0 | 0 | DELAY |  | 10753500000 | MEDIUM | 23/10/2017 22:42:39
PROJ2398 | PEKERJAAN ELEKTRONIK PROJEK TRANS PARK BEKASI | SMART BUILDING | ADHI KARYA PT | PCS | IMAM ZAHIR | DWI PUDJI IRAWATI | PT PINS Indonesia | 26-JUL-18 | 20-JUL-19 | 0 | 0 | 0 | LEAD |  | 20300000156 | BIG | 13/08/2018 15:47:56
PROJ775 | PENGADAAN TEKNOLOGI BIG DATA UNTUK BRI | APPLICATION | BANK RAKYAT INDONESIA (PERSERO) | BMS-1 | ADRID | RUDY WIBOWO | PT Metra-Net | 09-NOV-17 | 31-AUG-18 | 99.991 | 97.068 | -2.923 | LAG | 1.Delivery barang/jasa (mitra) | 25704545454 | STRATEGIS | 14/08/2018 10:44:51
PROJ1581 | PENGADAAN PERANGKAT GATE DAN PENDUKUNG SISTEM TIKET ELEKTRONIK DI PT TRANPORTASI JAKARTA | CPE & OTHERS | PT. TRANSPORTASI JAKARTA | TMS | DODI IRAWAN | ERSYHAD PRABAWA ADIGUNA | PT. Nutech Integrasi | 19-APR-18 | 04-SEP-18 | 100 | 98.1 | -1.9 | LAG | 8.CR (perubahan yang belum terkendali) & amandemen (customer) | 8507262000 | BIG | 03/08/2018 17:07:40
PROJ212 | WIFI.ID KIMIA FARMA (TAHAP 2) | CONNECTIVITY | KIMIA FARMA PT | HWS | SRI NURFALAH | MELANY ULFA |  | 01-JAN-17 | 31-DEC-18 | 99.997 | 89 | -10.997 | LAG |  | 318000000 | REGULER | 09/08/2018 16:55:57
PROJ449 | PURI MANSION APARTMENT | SMART BUILDING | AGUNG SEDAYU PROPERTINDO | IBS | HERU IRMAN | FAHMI MUHAMMAD HUSIN | Cv Dwi Mandiri Berjaya | 10-JUL-17 | 07-OCT-17 | 100 | 76 | -24 | DELAY | 3.Perubahan desain/spek pelanggan (customer) | 8301000000 | MEDIUM | 22/05/2018 15:29:45
PROJ801 | PROJECT DIGITALISASI KIMIA FARMA | CPE & OTHERS | KIMIA FARMA PT | HWS | ADRID | MELANY ULFA | PT Sigma Cipta Caraka | 27-DEC-17 | 01-SEP-18 | 102.71 | 97.52 | -5.19 | LAG | 1.Delivery barang/jasa (mitra) | 787000000000 | STRATEGIS | 14/08/2018 10:54:36
PROJ928 | PENGADAAN SEWA 12.000 UNIT EDC BNI UNTUK PT. BRINGIN GIGANTARA | CPE & OTHERS | BANK NEGARA INDONESIA 46TBK(BNI 46) | BMS-1 | RUDIONO | ARJANI ROSALINA, RADEN | PT Sigma Cipta Caraka | 15-JAN-18 | 31-DEC-18 | 100 | 17.783 | -82.217 | LAG | 2.Kesiapan lokasi ( customer) | 57000000000 | BIG | 23/04/2018 14:44:50
PROJ648 | PENGADAAN JARINGAN KOMUNIKASI TEKNOLOGI MULTI CARRIER ACCESS (MCA) | CPE & OTHERS | BANK MANDIRI | BMS-1 | ARI WIDIYANTO | FACHRUL INDRACAHYO |  | 20-OCT-17 | 20-DEC-17 | 0 | 0 | 0 | DELAY |  | 4200000000 | MEDIUM | 24/01/2018 14:16:38
PROJ1489 | PENGADAAN PERSONAL COMPUTER (PC) DAN MANAGE SERVICE DI PT BANK DKI TAHAP II | CPE & OTHERS | BANK DKI | BMS-2 | HASBUR GHALI | NADIA PRIMASARI | PT PINS Indonesia | 30-APR-18 | 31-AUG-18 | 99 | 98.25 | -0.75 | LAG | 2.Kesiapan lokasi ( customer) | 7840000000 | ORDINARY | 06/08/2018 15:09:35
PROJ1492 | ORACLE ENTERPRISE BUSINESS SUITE (EBS) SUPPLY CHAIN MANAGEMENT`MODULE PT. PELNI (PERSERO) | APPLICATION | PELAYARAN NASIONAL INDONESIA (PELNI) PT | MLS | ADRID | NAWIN |  | 06-MAR-18 | 21-SEP-18 | 62.5 | 40.4 | -22.1 | LAG |  | 8935000000 | STRATEGIS | 14/08/2018 11:18:01
PROJ1517 | PENGADAAN ENHANCEMENT PORTAL BTN PROPERTI PHASE 2 | CPE & OTHERS | BANK TABUNGAN NEGARA (PERSERO) | BMS-1 | SHEPTIAN KURNIA SALEH | DISKAERI |  | 28-MAR-18 | 28-SEP-18 | 100 | 66.6 | -33.4 | LAG |  | 4086363636 | STRATEGIS | 07/08/2018 14:55:05
PROJ1877 | PROJECT PEKERJAAN DIGITAL CORE PLATFORM DI PERUM PERURI | CPE & OTHERS | PERURI PERUM | FMS | IRWANDI | WIJAYANTO | PT Sigma Metrasys Solution | 07-JUN-18 | 22-DEC-18 | 0 | 0 | 0 | LEAD |  | 89318181818 | STRATEGIS | 25/06/2018 16:50:41
PROJ207 | WIFI.ID ANGKASA PURA I (NGURAH RAI) TAHAP 2 | CONNECTIVITY | ANGKASAPURA I | TMS | SRI NURFALAH | ONHI YULIARTI SEMARA |  | 01-JAN-17 | 31-DEC-18 | 70.52 | 0 | -70.52 | LAG |  | 2394000000 | ORDINARY | 09/08/2018 16:54:46
PROJ2396 | PROJECT EASTERN GREEN BEKASI | SMART BUILDING | ADHI KARYA PT | PCS | PRAKOSA TRIWIBOWO | DWI PUDJI IRAWATI |  | 30-NOV-17 | 30-NOV-19 | 18.88 | 21.38 | 2.5 | LEAD |  | 6850000000 | MEDIUM | 13/08/2018 15:28:15
PROJ1240 | PERUBAHAN LAYANAN DAN PENAMBAHAN LOKASI MANAGE SERVICE ASTINET LITE 212 LOKASI PT. CHAROEN POKPHAND | CONNECTIVITY | CHAROEN POKPHAND INDONESIA PT | MAS | YUSUF SARTONO | ANISAH SOFWATI |  | 27-MAR-18 | 26-MAR-19 | 44.4 | 26.5 | -17.9 | LAG |  | 5003200000 | ORDINARY | 09/08/2018 17:01:06
PROJ1285 | PEKERJAAN ELEKTRONIK DAN ELEKTRIKAL DI APARTEMEN ZAMZAM TOWER DEPOK | SMART BUILDING | WIJAYA KARYA | PCS | TEDDY AWALUDIN | NOVI ANDRIYANI | PT Infrastruktur Telekomunikasi Indonesia (TELKOMINFRA) | 01-JAN-18 | 30-JUN-18 | 100 | 0 | -100 | DELAY |  | 10200000000 | MEDIUM | 11/04/2018 10:56:29
PROJ1646 | Proyek Pembangunan B Residence, Serpong - Tangerang Pekerjaan Elektronik | SMART BUILDING | PT. MAJU GEMILANG SERPONG | PCS | NAZIRWAN, ST. M.KOM | SUNARTO AMSALOM SAIRO | PT PINS Indonesia | 15-JAN-18 | 15-SEP-19 |  |  |  | LEAD |  | 17985000000 | MEDIUM | 17/05/2018 11:38:36
PROJ1901 | Pembangunan dan Implementasi aplikasi iPerform | APPLICATION | ANGKASA PURA II (PERSERO) - BUISH | TMS | RIKA AMALIA SASANTY |  | PT Infomedia Nusantara, PT Infomedia Nusantara | 18-MAY-18 | 15-AUG-18 | 91.42 | 87.5 | -3.92 | DELAY |  | 388880000 | SMALL | 28/06/2018 14:26:52
PROJ211 | WIFI.ID BPD SUMATERA BARAT | CONNECTIVITY | BANGKOK BANK | BMS-2 | SRI NURFALAH | ARFAN SUATAN |  | 01-JAN-17 | 31-DEC-18 | 100.01 | 77 | -23.01 | LAG |  | 324000000 | REGULER | 09/08/2018 16:55:36
PROJ217 | PROJECT MEKANIKAL & ELEKTRIKAL PEKERJAAN CINERE TERRACE SUITES - APARTMENT & CITYWALK | SMART BUILDING | METROPOLITAN TOWER | PCS | TEDDY AWALUDIN | SUNARTO AMSALOM SAIRO | PT PINS Indonesia | 17-FEB-17 | 31-MAR-18 | 100 | 82.94 | -17.06 | DELAY | 8.CR (perubahan yang belum terkendali) & amandemen (customer) | 18568190000 | MEDIUM | 07/06/2018 13:44:50
PROJ44 | PROJECT LAYANAN VPN IP UNTUK KFC | CONNECTIVITY | FASTFOOD INDONESIA | THS | I DEWA MADE AGUS | ANAK AGUNG ARDHA CHANDRA DEWI |  | 01-JAN-16 | 31-DEC-18 | 100 | 86.4 | -13.6 | LAG | 2.Kesiapan lokasi ( customer) | 1032000000 | ORDINARY | 19/07/2018 16:41:29
PROJ808 | ERP SAP PT SEMEN BATURAJA | APPLICATION | SEMEN BATURAJA PT | MAS | KRSHNA SULANJANA | MUHAMMAD HANIS | PT Sigma Metrasys Solution, PT Sigma Metrasys Solution | 29-DEC-17 | 04-JAN-19 | 95.6 | 80 | -15.6 | LAG |  | 34771819125 | BIG | 13/08/2018 14:56:02