## Worksheet
ID PROJECT | PROJECT NAME | TYPE PROJECT | CLIENT | SEGMEN | PM NAME | AM NAME | PARTNERS | START DATE | END DATE | PLAN | ACHIEVEMENT | DEVIASI | STATUS | REASON OF DELAY | PROJECT VALUE | CATEGORY | LAST UPDATE
PROJ1117 | PROJECT ELEKTRIKAL DAN ELEKTRONIK GEDUNG BIOFARMA 2 BANDUNG | SMART BUILDING | PEMBANGUNAN PERUMAHAN PT | PCS | HADI TRIYONO | SHEINI CHRISTY |  | 26-FEB-18 | 27-MAY-19 | 34.2 | 5.0311 | -29.1689 | LAG | 1.Delivery barang/jasa (mitra) | 20800000000 | STRATEGIS | 04/07/2018 20:16:23
PROJ1387 | PENGADAAN BUKU PELAJARAN PURI PANCA PUJIBANGUN | CPE & OTHERS | PURI PANCA PUJIBANGUN, PT | MAS | HASBUR GHALI | RULLY AMAL PUTRA | PT Metra Digital Media | 23-APR-18 | 16-MAY-19 | 100 | 31 | -69 | LAG | 1.Delivery barang/jasa (mitra) | 34496231250 | BIG | 11/07/2018 10:42:36
PROJ1491 | REVITALISASI DAN PENGEMBANGAN DATA CENTER UNIVERSITAS SYIAH KUALA | CPE & OTHERS | UNIVERSITAS SYAHKUALA (UNSYIAH) | EMS | MASTAMAN ARABY | AGUS FRIADI | PT Infrastruktur Telekomunikasi Indonesia (TELKOMINFRA) | 06-APR-18 | 31-AUG-18 |  |  |  | LEAD |  | 4704000000 | MEDIUM | 30/04/2018 15:36:53
PROJ1545 | UPGRADE DAN PSB VPN IP DAN 2 BACKHAUL, PSB ASTINET LITE DAN 2 BACKHAUL, DAN MANAGED AP BANK BTPN | CONNECTIVITY | BANK BTPN | BMS-2 | M ISNAINI SAPUTRO | BERTHA DESVIANI PURBA | PT Teltranet Aplikasi Solusi (Telkom Telstra) | 07-MAY-18 | 31-AUG-18 |  |  |  | LEAD |  | 3445000000 | MEDIUM | 08/05/2018 11:26:25
PROJ171 | AIRPORT OPERATION CONTROL CENTER BANDARA SOEKARNO HATTA | APPLICATION | ANGKASA PURA II (PERSERO) - BUISH | TMS | ATAM RUSTAM | HIDAYAT KURNIAWAN | PT PINS Indonesia | 01-JAN-17 | 31-AUG-18 | 99.696 | 86.898 | -12.798 | LAG | 8.CR (perubahan yang belum terkendali) & amandemen (customer) | 93655243000 | STRATEGIS | 13/08/2018 14:54:08
PROJ18 | PROJECT VIMALA HILLS (PANIC BUTTON) | SMART BUILDING | PODOMORO GROUP | PCS | HERI IKHWAN DIANA | GERRY ROY MANAEK SIAHAAN | PT PINS Indonesia | 10-MAR-14 | 31-DEC-17 | 100 | 90.95 | -9.05 | DELAY | 2.Kesiapan lokasi ( customer) | 2100000000 | ORDINARY | 22/05/2018 17:01:06
PROJ19 | PROJECT CCTV VIMALA HILLS GADOG | SMART BUILDING | PODOMORO GROUP | PCS | HERI IKHWAN DIANA | NOVI ANDRIYANI | PT PRAMINDO IKAT NUSANTARA (PINS) | 07-AUG-14 | 31-DEC-17 | 100 | 91.37 | -8.63 | DELAY | 2.Kesiapan lokasi ( customer) | 2321000000 | MEDIUM | 22/05/2018 10:54:22
PROJ1944 | PENGADAAN JARINGAN DATA GRAHA INKA | CPE & OTHERS | INKA | IBS | RUDIONO |  | PT PINS Indonesia | 03-JUL-18 | 08-JUL-19 |  |  |  | LAG |  | 2680000000 | MEDIUM | 27/08/2018 17:49:20
PROJ204 | PROJECT RESUNAMI GRAND SENTRALAND KARAWANG | SMART BUILDING | PEMBANGUNAN PERUMAHAN PT | PCS | TEUKU HAMIZUL | RADIAN SIGIT DWIANANTO | PT Infomedia Nusantara | 31-OCT-16 | 30-JUN-18 | 99.997 | 82.009 | -17.988 | DELAY | 3.Perubahan desain/spek pelanggan (customer) | 23500000000 | BIG | 25/06/2018 16:28:32
PROJ21 | PROJECT CWJ 2 PHASE 1 | SMART BUILDING | CIPUTRA WORLD JAKARTA | PCS | IRWANDI | GERRY ROY MANAEK SIAHAAN | PT PRAMINDO IKAT NUSANTARA (PINS) | 26-SEP-14 | 31-DEC-17 | 99.695 | 99.699 | 0.0049 | DELAY |  | 23660990600 | BIG | 02/07/2018 15:19:35
PROJ213 | WIFI.ID BALAI PUSTAKA | CONNECTIVITY | BALAI PUSTAKA PT | EMS | SRI NURFALAH | GUSTI AYU MADE MAS MARHAENI |  | 01-JAN-17 | 31-DEC-18 | 100 | 70 | -30.009 | LAG |  | 216000000 | REGULER | 09/08/2018 16:56:20
PROJ2293 | PENGADAAN PENYEDIAAN JASA LAYANAN PAKET E-TICKETING PERUM DAMRI | APPLICATION | DAMRI PO | TMS | ARIEF SUSILO WIBOWO | ERSYHAD PRABAWA ADIGUNA |  | 05-JUN-18 | 05-JUN-20 | 43.65 | 16.65 | -27 | LAG |  | 22461600000 | BIG | 03/08/2018 16:50:38
PROJ236 | ROLL OUT I ERP PTPN IX (SEMARANG) | APPLICATION | PERKEBUNAN NUSANTARA IX | MAS | NURUL HIDAYATI | NANANG RUSTANDI | PT Sigma Metrasys Solution | 01-MAR-17 | 31-DEC-18 | 99.992 | 99.48 | -0.512 | LAG | 4.Keterlambatan BAST (customer) | 31017330000 | STRATEGIS | 21/05/2018 20:22:04
PROJ243 | BRANZ BSD ELECTRONIC GPON & ICT | SMART BUILDING | ALAM SUTERA REALTY | PCS | PRAKOSA TRIWIBOWO | HANDI JUNAEDI | PT PRAMINDO IKAT NUSANTARA (PINS) | 30-JAN-17 | 30-APR-18 | 99.999 | 85.275 | -14.7239 | DELAY | 1.Delivery barang/jasa (mitra) | 9614060207 | MEDIUM | 07/06/2018 14:37:34
PROJ32 | PROJECT PANIC BUTTON ORCHARD PARK BATAM | SMART BUILDING | PODOMORO GROUP | PCS | IRWANDI | NOVI ANDRIYANI | PT PINS Indonesia | 30-AUG-15 | 30-APR-18 | 100 | 62.67 | -37.33 | DELAY | 2.Kesiapan lokasi ( customer) | 2109703600 | SMALL | 02/07/2018 15:22:39
PROJ364 | IMPLEMENTASI ORACLE PRIMAVERA DI PT PAL INDONESIA | APPLICATION | PAL | IBS | SHEPTIAN KURNIA SALEH | FACHRUL INDRACAHYO | SIGMA SOLUSI INTEGRASI | 28-FEB-17 | 31-DEC-17 | 99.996 | 88 | -11.996 | DELAY | 2.Kesiapan lokasi ( customer) | 3044996000 | STRATEGIS | 30/05/2018 11:45:36
PROJ367 | LAYANAN INFOKOM MODERENISASI JARINGAN GRAND INDONESIA | SMART BUILDING | GRAND INDONESIA | PCS | TEDDY AWALUDIN | NOVI ANDRIYANI | PT. Bangtelindo | 01-DEC-16 | 30-APR-18 | 100.03 | 90.94 | -9.093 | DELAY | 1.Delivery barang/jasa (mitra) | 6685966305 | MEDIUM | 14/03/2018 11:43:30
PROJ384 | PROJECT WIFI.ID HOTEL HILTON | CONNECTIVITY | FOUR SEASON HOTEL AND RESORT | THS | SRI NURFALAH | RINO SUPRIADI PUTRA |  | 01-JAN-17 | 31-DEC-18 |  |  |  | LEAD |  | 756000000 | SMALL | 16/01/2018 13:55:15
PROJ385 | PROJECT WIFI.ID STARBUCK | CONNECTIVITY | MAP FOOD & BEVERAGE | THS | SRI NURFALAH | EVY YULIA RAMADHAN |  | 01-JAN-17 | 31-DEC-18 |  |  |  | LAG |  | 480000000 | REGULER | 09/08/2018 16:58:31
PROJ42 | PROJECT WIFI.ID GARUDA INDONESIA | CONNECTIVITY | GARUDA INDONESIA PT | TMS | SRI NURFALAH | NOSKI PANDAPOTAN SAMOSIR |  | 01-JAN-16 | 31-DEC-18 |  |  |  | LEAD |  | 162000000 | SMALL | 15/05/2018 12:59:31
PROJ429 | PEKERJAAN ELEKTRONIKA DAN GPON PROYEK GALLERIA VIVO MALL SENTUL | SMART BUILDING | ADHIBALADIKA AGUNG | PCS | AD STEFEN RATU EDA | HELVIANA | PT PINS Indonesia | 24-MAY-17 | 15-MAY-18 | 98.24 | 74.78 | -23.46 | DELAY | 1.Delivery barang/jasa (mitra) | 11363636363 | MEDIUM | 22/05/2018 11:07:05
PROJ457 | PROJECT GPON ICT DI CIPUTRA INTERNASIONAL | SMART BUILDING | CIPUTRA WORLD JAKARTA | PCS | IRWANDI | GERRY ROY MANAEK SIAHAAN | PT PRAMINDO IKAT NUSANTARA (PINS) | 02-NOV-16 | 31-DEC-17 | 69.82 | 60.77 | -9.05 | DELAY | 2.Kesiapan lokasi ( customer) | 5336000000 | SMALL | 02/01/2018 14:45:32
PROJ458 | PROJECT ELEKTRONIK APARTEMEN DI BORNEO BAY BALIKPAPAN | SMART BUILDING | PODOMORO GROUP | PCS | PRAKOSA TRIWIBOWO | NOVI ANDRIYANI | PT PRAMINDO IKAT NUSANTARA (PINS) | 01-JUL-17 | 22-OCT-18 | 98.788 | 32.782 | -66.006 | DELAY | 2.Kesiapan lokasi ( customer) | 14181818000 | MEDIUM | 07/05/2018 15:00:58
PROJ60 | PROJECT SMART BUILDING MENTENG PARK | SMART BUILDING | AGUNG SEDAYU PROPERTINDO | IBS | AD STEFEN RATU EDA | FURI DIAH AYU HAPSARI | PT PINS Indonesia | 02-MAY-16 | 15-MAY-18 | 99.81 | 78.25 | -21.56 | DELAY | 1.Delivery barang/jasa (mitra) | 19100000000 | MEDIUM | 22/05/2018 11:18:17
PROJ7 | PROJECT FTTH DUKUH GOLF KEMAYORAN BOUGENVILLE | SMART BUILDING | AGUNG SEDAYU PROPERTINDO | IBS | PRAKOSA TRIWIBOWO | FAHMI MUHAMMAD HUSIN | PT PRAMINDO IKAT NUSANTARA (PINS) | 18-SEP-14 | 30-SEP-16 | 99.986 | 99.997 | 0.011 | DELAY | 4.Keterlambatan BAST (customer) | 19043050000 | MEDIUM | 10/01/2018 10:54:08
PROJ740 | PROJECT PEKERJAAN PENGADAAN DAN IMPLEMENTASI ERP DI PT. KAWASAN INDUSTRI MEDAN (KIM) | APPLICATION | KAWASAN INDUSTRI MEDAN (KIM) | IBS | RIKA AMALIA SASANTY | FENNY NOVITA | PT Infomedia Nusantara | 01-NOV-17 | 30-JUN-18 | 100.01 | 97.79 | -2.22 | DELAY | 4.Keterlambatan BAST (customer) | 889345600 | REGULER | 08/06/2018 13:57:57
PROJ745 | ROLL OUT 2 PTPN 1 ACEH | APPLICATION | PERKEBUNAN NUSANTARA I PT | MAS | NURUL HIDAYATI | AGUS FRIADI | PT Sigma Metrasys Solution | 01-OCT-17 | 31-AUG-18 | 71.15 | 51 | -20.15 | LAG | 3.Perubahan desain/spek pelanggan (customer) | 12793140000 | MEDIUM | 21/05/2018 20:32:09
PROJ747 | ROLL OUT 2 PTPN 7 LAMPUNG | APPLICATION | PERKEBUNAN NUSANTARA VII PT | MAS | NURUL HIDAYATI | ADE NIRWANI | PT Sigma Metrasys Solution | 01-OCT-17 | 31-AUG-18 | 95.6 | 51 | -44.6 | LAG | 1.Delivery barang/jasa (mitra) | 33189750000 | STRATEGIS | 21/05/2018 20:45:21
PROJ751 | ROLL OUT 3 KPBN JAKARTA | APPLICATION | PERKEBUNAN NUSANTARA VII PT | MAS | NURUL HIDAYATI | ANWAR | PT Sigma Metrasys Solution | 01-OCT-17 | 31-DEC-18 | 100 | 92 | -8 | LAG | 1.Delivery barang/jasa (mitra) | 844830000 | STRATEGIS | 21/05/2018 14:11:55
PROJ813 | PENGADAAN MESIN SOA DAN UPGRADE AS-400 BTN | CPE & OTHERS | BANK TABUNGAN NEGARA (PERSERO) | BMS-1 | FAHMI RAHMANTHAHA NURDINSYAH | DISKAERI | PT Sigma Cipta Caraka, PT Sigma Cipta Caraka | 28-DEC-17 | 31-MAY-18 | 100 | 97.9 | -2.1 | DELAY | 4.Keterlambatan BAST (customer) | 109950000000 | STRATEGIS | 04/07/2018 09:33:44
PROJ824 | PROJECT PEKERJAAN JASA IMPLEMENTASI ENTERPRISE RESOURCE PLANNING (ERP) DI PERUM PERURI | APPLICATION | PERURI PERUM | FMS | IRWANDI | WIJAYANTO | PT Sigma Metrasys Solution, PT Sigma Metrasys Solution | 04-JAN-18 | 30-NOV-18 | 70.13 | 47 | -23.13 | LAG | 1.Delivery barang/jasa (mitra) | 54329137800 | STRATEGIS | 31/05/2018 10:53:36
PROJ825 | PROJECT RELOKASI BACKHAUL DANAMON | CONNECTIVITY | BANK DANAMON INDONESIA TBK | BMS-2 | WIM MUDJIONO | ARISTYA MEGA PUTRANTO |  | 08-JAN-18 | 31-DEC-18 | 98.5 | 89.14 | -9.36 | LAG |  | 0 | STRATEGIS | 09/08/2018 16:59:03
PROJ843 | NAC SOLUTION EDC DIAL UP BANK MANDIRI | CPE & OTHERS | BANK MANDIRI | BMS-1 | MUHAMMAD MASYHUDI | FERY KURNIAWAN | PT Sigma Cipta Caraka, PT Sigma Cipta Caraka | 21-SEP-17 | 07-SEP-18 | 100 | 32.07 | -67.93 | LAG |  | 39960000000 | STRATEGIS | 06/06/2018 14:19:58
PROJ95 | PROJECT ERP N-HOLDING LOKASI : PTPN V (PEKANBARU) | APPLICATION | PERKEBUNAN NUSANTARA V PT | MAS | NURUL HIDAYATI | SITI WIMA ADITYA MAHADINI | PT Sigma Metrasys Solution | 17-AUG-16 | 31-DEC-18 | 95.6 | 58.5 | -37.1 | LAG | 8.CR (perubahan yang belum terkendali) & amandemen (customer) | 35603550000 | STRATEGIS | 21/05/2018 14:02:21
PROJ1114 | PROJECT BALAI PUSTAKA | CPE & OTHERS | BALAI PUSTAKA PT | EMS | HASBUR GHALI | CAHYO BUWONO, ST | PT Balebat Dedikasi Prima, PT Balebat Dedikasi Prima | 15-FEB-18 | 31-MAR-19 | 99.95 | 65.6 | -34.35 | LAG | 1.Delivery barang/jasa (mitra) | 102125800000 | BIG | 21/05/2018 11:16:28
PROJ1269 | PENAMBAHAN INFRASUTRUKTUR DATA CENTER TERMINAL PETIKEMAS SEMARANG PT.PELINDO III | CPE & OTHERS | PELINDO III | MLS | HADI TRIYONO | AGUS HARI SUSANTO | PT Sigma Cipta Caraka, PT Sigma Cipta Caraka | 09-MAR-18 | 11-OCT-18 | 21.42 | 39.51 | 18.09 | LAG | 1.Delivery barang/jasa (mitra) | 8800000000 | STRATEGIS | 04/07/2018 20:23:29
PROJ1275 | PAKET SISTEM ELEKTRONIK APARTEMENT TOWER 1, HOTEL DAN MALL,PROYEK GREEN SEDAYU TAMAN PALEM JAKARTA | SMART BUILDING | AGUNG SEDAYU PROPERTINDO | IBS | HERU IRMAN | FAHMI MUHAMMAD HUSIN | PT PINS Indonesia, PT PINS Indonesia | 26-MAR-18 | 26-MAR-19 |  |  |  | LEAD |  | 26124999999 | BIG | 02/07/2018 10:49:01
PROJ1285 | PEKERJAAN ELEKTRONIK DAN ELEKTRIKAL DI APARTEMEN ZAMZAM TOWER DEPOK | SMART BUILDING | WIJAYA KARYA | PCS | TEDDY AWALUDIN | NOVI ANDRIYANI | PT Infrastruktur Telekomunikasi Indonesia (TELKOMINFRA) | 01-JAN-18 | 30-JUN-18 | 100 | 7.12 | -92.88 | DELAY | 1.Delivery barang/jasa (mitra) | 10200000000 | MEDIUM | 11/04/2018 10:56:29
PROJ182 | PROJECT IN BUILDING SOLUTION (IBS) KEMPINSKI HOTEL BALI | SMART BUILDING | GRAHA ALAM LESTARI | PCS | AD STEFEN RATU EDA | GERRY ROY MANAEK SIAHAAN | PT Dayamitra Telekomunikasi | 16-DEC-16 | 31-MAR-18 | 89.2 | 80.89 | -8.31 | DELAY | 1.Delivery barang/jasa (mitra) | 7100000000 | MEDIUM | 12/03/2018 12:24:35
PROJ1877 | PROJECT PEKERJAAN DIGITAL CORE PLATFORM DI PERUM PERURI | CPE & OTHERS | PERURI PERUM | FMS | IRWANDI | WIJAYANTO | PT Sigma Metrasys Solution | 07-JUN-18 | 22-DEC-18 |  |  |  | LEAD |  | 89318181818 | STRATEGIS | 25/06/2018 16:50:41
PROJ1903 | PENGADAAN HYPERCONVERGED STORAGE SERVER DENGAN VIRTUAL MACHINE GATEWAY SCADA PT. PLN | CPE & OTHERS | PERUSAHAAN LISTRIK NEGARA (PERSERO) PLN | ERS | DODI IRAWAN | NASHRI | PT Sigma Cipta Caraka, PT Sigma Cipta Caraka | 20-APR-18 | 25-SEP-18 | 53 | 34 | -19 | LAG | 1.Delivery barang/jasa (mitra) | 1475000000 | STRATEGIS | 02/07/2018 11:28:05
PROJ234 | ROLL OUT I ERP PTPN III (MEDAN) | APPLICATION | PERKEBUNAN NUSANTARA III PT | MAS | NURUL HIDAYATI | SIMON | PT Sigma Metrasys Solution | 01-MAR-17 | 31-DEC-18 | 100 | 99.95 | -0.05 | LAG | 4.Keterlambatan BAST (customer) | 65172600000 | STRATEGIS | 30/05/2018 13:19:49
PROJ261 | BRANZ SIMATUPANG ELECTRONIC GPON & ICT | SMART BUILDING | SUMMITMAS PROPERTY | PCS | PRAKOSA TRIWIBOWO | RADIAN SIGIT DWIANANTO | PT PRAMINDO IKAT NUSANTARA (PINS) | 30-JAN-17 | 14-DEC-18 | 100 | 68.12 | -31.88 | DELAY | 2.Kesiapan lokasi ( customer) | 12357698601 | MEDIUM | 24/05/2018 15:04:09
PROJ27 | PROJECT CEMINDO TOWER | SMART BUILDING | CEMINDO TOWER | PCS | NAZIRWAN, ST. M.KOM | MUHAMMAD SIDIK | PT TELKOM AKSES | 01-SEP-14 | 31-DEC-17 | 100.05 | 100.25 | 0.1951 | DELAY | 4.Keterlambatan BAST (customer) | 13900000000 | MEDIUM | 02/08/2017 16:23:32
PROJ376 | PROJECT WIFI.ID DOMINO PIZZA | CONNECTIVITY | MAP FOOD & BEVERAGE | THS | SRI NURFALAH | EVY YULIA RAMADHAN |  | 01-JAN-17 | 31-DEC-18 |  |  |  | LAG |  | 21000000 | REGULER | 09/08/2018 16:57:31
PROJ379 | PROJECT WIFI.ID KFC | CONNECTIVITY | FASTFOOD INDONESIA | THS | SRI NURFALAH | ANAK AGUNG ARDHA CHANDRA DEWI |  | 01-JAN-17 | 31-DEC-18 |  |  |  | LEAD |  | 237000000 | SMALL | 09/01/2018 18:41:31
PROJ386 | PROJECT WIFI.ID PIZZA HUT | CONNECTIVITY | MAP FOOD & BEVERAGE | THS | SRI NURFALAH | EVY YULIA RAMADHAN |  | 01-JAN-17 | 31-DEC-18 |  |  |  | LAG |  | 186000000 | REGULER | 09/08/2018 16:58:46
PROJ453 | WIFI.ID VIP PARKING BATCH 2 | CONNECTIVITY | VIP PARKING INDONESIA | THS | SRI NURFALAH | KASRIYADI NUR |  | 01-JAN-17 | 31-DEC-18 |  |  |  | LEAD |  | 26000000 | SMALL | 09/01/2018 18:50:07
PROJ51 | PROJECT WIFI.ID WHIZ PRIME HOTEL 180 TITIK | CONNECTIVITY | WHIZ HOTEL GROUP | THS | SRI NURFALAH | ANAK AGUNG ARDHA CHANDRA DEWI |  | 01-JAN-16 | 31-DEC-18 | 100 | 27 | -73.008 | LAG |  | 1122000000 | ORDINARY | 09/08/2018 16:53:34
PROJ672 | PENYEDIAAN JARINGAN DATA PT. JCO DONUT & COFFEE | CONNECTIVITY | JOHNY ANDREAN GROUP | THS | ROBIYANTO | EVY YULIA RAMADHAN | PT Patra Telekomunikasi Indonesia | 25-SEP-17 | 29-DEC-17 | 90 | 100 | 10 | DELAY |  | 606277680 | SMALL | 11/04/2018 11:44:58
PROJ810 | PENGADAAN CONTACT CENTER BANK ACEH | APPLICATION | BANK ACEH SYARIAH | BMS-2 | TEUKU HAMIZUL | AGUS FRIADI | PT Infomedia Nusantara | 03-JAN-18 | 08-JUN-18 | 100 | 99 | -1 | DELAY | 8.CR (perubahan yang belum terkendali) & amandemen (customer) | 3936089726 | MEDIUM | 16/07/2018 20:38:04
PROJ82 | PROJECT ELECTRONIC & FTTH COUNTRY CLUB NAVAPARK | SMART BUILDING | SINAR MAS WISESA | PCS | TEDDY AWALUDIN |  | PT PINS Indonesia | 01-FEB-16 | 30-MAY-18 | 100 | 100 | 0 | DELAY | 8.CR (perubahan yang belum terkendali) & amandemen (customer) | 2430000000 | MEDIUM | 10/04/2018 12:32:25
PROJ834 | JASA PENGADAAN DAN PEMASANGAN BACKBONE FO DATA CENTER DI PERUM PERURI | CPE & OTHERS | PERURI PERUM | FMS | IRWANDI | WIJAYANTO | Koperasi Metropolitan | 19-DEC-17 | 19-MAR-18 | 100 | 100 | 0 | DELAY |  | 443117000 | SMALL | 11/04/2018 16:05:01
PROJ844 | PROJECT PEKERJAAN SISTEM TICKETING LRT SUMATERA SELATAN | APPLICATION | KERETA API INDONESIA | TMS | NAZIRWAN, ST. M.KOM | VINO HARSADITYA SAPUTRA | PT Sigma Cipta Caraka, PT Sigma Cipta Caraka | 29-JAN-18 | 28-JUL-18 | 99.97 | 100 | 0.03 | DELAY | 4.Keterlambatan BAST (customer) | 19074599500 | BIG | 30/05/2018 15:24:14
PROJ847 | PENGADAAN DAN PEMASANGAN PERANGKAT BCM KONTER DAN MESIN AUTOGATE DI BANDARA I GUSTI NGURAH RAI | CPE & OTHERS | ANGKASAPURA I | TMS | ADRID | HUSNI MUBARAK, ST | PT Signet Pratama | 30-JAN-18 | 01-SEP-18 | 100 | 95.08 | -4.92 | LAG | 2.Kesiapan lokasi ( customer) | 64093880000 | STRATEGIS | 27/08/2018 09:12:36
PROJ2179 | LAYANAN MIGRASI VSAT KE VPN IP PT. PEGADAIAN | CONNECTIVITY | PEGADAIAN PT | FMS | FACHRI | ANDIKA PRATAMA PUTRA |  | 01-JUL-18 | 31-OCT-18 |  |  |  | LEAD |  | 248640300000 | STRATEGIS
PROJ1115 | PROJECT PUSTAKA MULIA | CPE & OTHERS | PUSTAKA MULIA | EMS | HASBUR GHALI | ARROZAQ AVE | PT Balebat Dedikasi Prima, PT Balebat Dedikasi Prima, PT Balebat Dedikasi Prima | 21-DEC-17 | 31-DEC-18 | 98.23 | 63.67 | -34.56 | LAG | 1.Delivery barang/jasa (mitra) | 108995000000 | BIG | 09/07/2018 10:10:30
PROJ1194 | PROJECT PENGEMBANGAN ERP MERAH PUTIH DI PT. VIRAMA KARYA (PERSERO) | APPLICATION | VIRAMA KARYA PT | PCS | RIKA AMALIA SASANTY | MASRUL DINAR |  | 15-FEB-18 | 14-AUG-18 | 99.98 | 97.7 | -2.28 | DELAY |  | 1135766181 | SMALL | 22/05/2018 09:14:37
PROJ13 | PROJECT ERP SAP INALUM | APPLICATION | INDONESIA ASAHAN ALUMUNIUM | MAS | RISTYAWAN FAUZI MUBAROK | SIMON | PT Sigma Metrasys Solution | 01-JUL-15 | 24-AUG-18 | 100 | 100 | 0 | DELAY | 4.Keterlambatan BAST (customer) | 32284783041 | STRATEGIS | 13/08/2018 11:31:48
PROJ137 | PROJECT JASA KONSULTASI PENDAMPINGAN ICT PT. PAL INDONESIA (PERSERO) | APPLICATION | PAL | IBS | NURUL HIDAYATI | VALENTINA NAINGGOLAN | PT Sigma Cipta Caraka | 01-DEC-16 | 31-DEC-18 | 101.28 | 66.1 | -35.18 | LAG | 2.Kesiapan lokasi ( customer) | 1350000000 | STRATEGIS | 31/05/2018 14:33:32
PROJ1494 | PENGADAAN MATERIAL ELECTRICAL DAN PLUMBING PROYEK RUMAH SUSUN PASAR RUMPUT MANGGARAI JAKARTA SELATAN | SMART BUILDING | PT. LINKADATA CITRA MANDIRI | PCS | HERU IRMAN | FERY KURNIAWAN | PT Sigma Cipta Caraka | 30-APR-18 | 01-MAY-18 |  |  |  | DELAY | 1.Delivery barang/jasa (mitra) | 34296609465 | BIG | 19/07/2018 11:42:39
PROJ207 | WIFI.ID ANGKASA PURA I (NGURAH RAI) TAHAP 2 | CONNECTIVITY | ANGKASAPURA I | TMS | SRI NURFALAH | ONHI YULIARTI SEMARA |  | 01-JAN-17 | 31-DEC-18 |  |  |  | LAG |  | 2394000000 | ORDINARY | 09/08/2018 16:54:46
PROJ363 | RENEWAL NETWORK CONNECTION ASURANSI AVRIST | CONNECTIVITY | AVRIST | HWS | SYARMAD HANING | DARU LUGAS PAMUNGKAS | TELKOMTELSTRA | 17-FEB-17 | 31-OCT-17 |  |  |  | DELAY |  | 1005480000 | MEDIUM | 16/10/2017 17:28:33
PROJ377 | PROJECT WIFI.ID DUNKIN DONUT | CONNECTIVITY | DUNKIN DONUT | THS | SRI NURFALAH | Noviyan Setiadi |  | 01-JAN-17 | 31-DEC-18 |  |  |  | LAG |  | 5500000 | REGULER | 09/08/2018 16:58:02
PROJ416 | WIFI.ID RUMAH SAKIT MITRA KELUARGA | CONNECTIVITY | RUMAH SAKIT MITRA KELUARGA | HWS | SRI NURFALAH | SAPHIRA DIELLA VARIANTY |  | 01-JAN-17 | 31-DEC-18 |  |  |  | LEAD |  | 509914080 | SMALL | 09/01/2018 18:48:22
PROJ609 | PROJECT PABX JAKARTA INTERNATIONAL VELODROME | SMART BUILDING | WIJAYA KARYA | PCS | TEUKU HAMIZUL | NOVI ANDRIYANI | PT PINS Indonesia | 06-JUL-17 | 31-MAY-18 | 100 | 100 | 0 | DELAY | 2.Kesiapan lokasi ( customer) | 634448361 | STRATEGIS | 01/06/2018 14:50:11
PROJ821 | PENGADAAN MANAGE SERVICE PEREMAJAAN ROUTER KANTOR CABANG BANK BTN | CPE & OTHERS | BANK TABUNGAN NEGARA (PERSERO) | BMS-1 | RUDIONO | DISKAERI | PT Multimedia Nusantara, PT Multimedia Nusantara | 21-DEC-17 | 30-JUN-18 | 100 | 100 | 0 | DELAY | 4.Keterlambatan BAST (customer) | 42900000000 | STRATEGIS | 04/07/2018 14:53:02
PROJ829 | PROJECT APARTEMEN GRAND JATI JUNCTION MEDAN | SMART BUILDING | PEMBANGUNAN PERUMAHAN PT | PCS | NAZIRWAN, ST. M.KOM | RADIAN SIGIT DWIANANTO | PT PINS Indonesia, PT PINS Indonesia | 01-SEP-17 | 31-OCT-18 | 99.89 | 36.3 | -63.59 | DELAY |  | 50270000000 | BIG | 07/05/2018 15:06:33
PROJ977 | PEKERJAAN MEKANIKAL, ELEKTRIKAL & PLUMBING PROYEK TEKNOPLEX LIVING APARTMENT | SMART BUILDING | PT.MULTI KARYA UTAMA ABADI -BANDUNG TECHNOPLEX LIVING | PCS | TEUKU HAMIZUL | RADIAN SIGIT DWIANANTO | PT Infrastruktur Telekomunikasi Indonesia (TELKOMINFRA), PT Infrastruktur Telekomunikasi Indonesia (TELKOMINFRA) | 31-OCT-17 | 24-OCT-18 | 84.025 | 22.5 | -61.525 | LAG | 2.Kesiapan lokasi ( customer) | 55000000000 | BIG | 16/07/2018 20:35:28
PROJ1109 | PENGADAAN PERANGKAT COMMAND CENTER PT ADHI KARYA (PERSERO) TBK | CPE & OTHERS | ADHI KARYA PT | PCS | ROBIYANTO | DWI PUDJI IRAWATI |  | 03-MAY-18 | 30-APR-18 | 95 | 70 | -25 | DELAY |  | 107890000 | SMALL | 20/04/2018 10:21:37
PROJ1901 | PEMBANGUNAN DAN IMPLEMENTASI APLIKASI IPERFORM | APPLICATION | ANGKASA PURA II (PERSERO) - BUISH | TMS | RIKA AMALIA SASANTY |  | PT Infomedia Nusantara, PT Infomedia Nusantara | 18-MAY-18 | 15-AUG-18 | 92.84 | 95 | 2.16 | DELAY |  | 388880000 | SMALL | 28/06/2018 14:26:52
PROJ209 | WIFI.ID BTDC NUSA DUA TAHAP 2 | CONNECTIVITY | BTDC NUSA DUA | THS | SRI NURFALAH | I MADE BUDIANA, SE, MM |  | 01-JAN-17 | 31-DEC-18 | 99.996 | 95 | -4.996 | LAG |  | 20000000 | REGULER | 09/08/2018 16:55:15
PROJ217 | PROJECT MEKANIKAL & ELEKTRIKAL PEKERJAAN CINERE TERRACE SUITES - APARTMENT & CITYWALK | SMART BUILDING | METROPOLITAN TOWER | PCS | TEDDY AWALUDIN | SUNARTO AMSALOM SAIRO | PT PINS Indonesia | 17-FEB-17 | 31-MAR-18 | 100 | 93.8 | -6.2 | DELAY | 8.CR (perubahan yang belum terkendali) & amandemen (customer) | 18568190000 | MEDIUM | 07/06/2018 13:44:50
PROJ222 | UPGRADE VPN IP & MIGRASI FO SUMMIT OTO FINANCE | CONNECTIVITY | SUMMIT OTO FINANCE | FMS | ARI WIDIYANTO | ARISTYA MEGA PUTRANTO |  | 18-FEB-17 | 01-MAY-17 |  |  |  | DELAY |  | 10753500000 | MEDIUM | 23/10/2017 22:42:39
PROJ227 | RELOKASI DATA CENTER JTPM BURSA EFEK INDONESIA | CONNECTIVITY | BEI (BURSA EFEK INDONESIA) | FMS | SOLEH MGS | CINDY ARINI | PT PINS Indonesia | 23-FEB-17 | 30-APR-18 | 100 | 99 | -1 | DELAY |  | 682148750 | SMALL | 06/06/2018 10:08:38
PROJ237 | ROLL OUT I ERP PTPN XII (SURABAYA) | APPLICATION | PERKEBUNAN NUSANTARA XII PT | MAS | NURUL HIDAYATI | JUNED DRAJAT PRASETYO | PT Sigma Metrasys Solution | 01-MAR-17 | 08-OCT-18 | 96 | 53 | -43 | LAG | 3.Perubahan desain/spek pelanggan (customer) | 19793160000 | STRATEGIS | 05/06/2018 11:53:42
PROJ30 | PROJECT PEKERJAAN SALURAN PENANGGAL BAWAH TANAH DI PROYEK BOULEVARD BUSINESS CENTER | SMART BUILDING | ADHI KARYA PT | PCS | IRWANDI | MUHAMMAD SIDIK | PT TELKOM AKSES | 19-NOV-14 | 31-JUL-17 | 100 | 41.25 | -58.75 | DELAY | 2.Kesiapan lokasi ( customer) | 472727273 | SMALL | 02/07/2018 15:21:50
PROJ405 | PROJECT PENGADAAN DAN PEMASANGAN GATE BARRIER SELURUH GERBANG CLUSTER PROYEK ORCHARD PARK BATAM | SMART BUILDING | PODOMORO GROUP | PCS | IRWANDI | NOVI ANDRIYANI | PT PRAMINDO IKAT NUSANTARA (PINS) | 01-APR-17 | 01-APR-18 | 100 | 84.05 | -15.95 | DELAY |  | 1000000000 | MEDIUM | 10/04/2018 13:30:14
PROJ409 | LISENSI DAN IMPLEMENTASI ERP ORACLE CLOUD KALLA GROUP | APPLICATION | HAKA SARANA INVESTAMA | IBS | DODI IRAWAN | BINDA ANISSA | SIGMA SOLUSI INTEGRASI | 08-MAY-17 | 15-DEC-18 | 100 | 93.7 | -6.3 | LAG | 3.Perubahan desain/spek pelanggan (customer) | 33710373799 | BIG | 13/08/2018 14:55:28
PROJ455 | WIFI.ID SWISS BELL HOTEL MANADO | CONNECTIVITY | SWISS BELL HOTEL MANADO | THS | SRI NURFALAH | JOKO SULISTIYO |  | 28-JUL-17 | 31-DEC-18 |  |  |  | LEAD |  | 90000000 | SMALL | 09/01/2018 18:51:31
PROJ574 | PROJECT BPO INSTALASI SISTEM GAS PROCESSING PLANT | CPE & OTHERS | PT GREEN ENERGY NATURAL GAS | ERS | RISTYAWAN FAUZI MUBAROK | TITIS WENING | PT Sigma Cipta Caraka | 01-SEP-17 | 30-APR-18 | 96.11 | 48.68 | -47.43 | DELAY | 3.Perubahan desain/spek pelanggan (customer) | 80663661600 | MEGA | 05/07/2018 11:06:31
PROJ59 | PROJECT ICT FTTH GPON (VERTIKAL DAN HORIZONTAL) DI APARTMENT BINTARO ICON | SMART BUILDING | ADITYA TOA DEV / MENARA THAMRIN | PCS | ATAM RUSTAM | NADIAH LIESTYASARI | PT PINS Indonesia | 01-MAY-16 | 31-DEC-17 | 99.97 | 89.85 | -10.12 | DELAY | 1.Delivery barang/jasa (mitra) | 5744549322 | MEDIUM | 08/05/2018 16:35:26
PROJ621 | PEKERJAAN PENATAAN KAWASAN GBK ZONA 1 | SMART BUILDING | ADHI KARYA PT | PCS | ADRID | DWI PUDJI IRAWATI | PT PINS Indonesia | 01-SEP-17 | 30-DEC-17 | 100 | 100 | 0 | DELAY |  | 19500000000 | BIG | 14/08/2018 10:48:14
PROJ71 | PROJECT WIFI.ID TRANS COFFEE (COFFEE BEAN) | CONNECTIVITY | TRANS COFFEE | THS | SRI NURFALAH | RINO SUPRIADI PUTRA |  | 01-JUN-16 | 31-DEC-18 | 100 | 58 | -42.001 | LAG | 2.Kesiapan lokasi ( customer) | 666000000 | SMALL | 09/01/2018 18:42:56
PROJ8 | PROJECT WIFI ID SAMSUNG EXPERIENCE STORE 106 LOKASI | CONNECTIVITY | SAMSUNG ELECTRONIC INDONESIA | IBS | KARDJUNETRO | ANDI SYAHRUDDIN |  | 01-APR-14 | 31-DEC-18 |  |  |  | LAG |  | 111600000 | REGULER | 09/08/2018 16:52:59
PROJ816 | PENGADAAN FIREWALL KANTOR CABANG BTN DENGAN METODE MANAGE SERVICE | CPE & OTHERS | BANK TABUNGAN NEGARA (PERSERO) | BMS-1 | RUDIONO | DISKAERI | PT Sigma Cipta Caraka, PT Sigma Cipta Caraka | 28-DEC-17 | 24-SEP-18 | 100 | 90.19 | -9.81 | LAG | 4.Keterlambatan BAST (customer) | 44950000000 | STRATEGIS | 23/08/2018 11:19:41
PROJ107 | PROJECT WIFI.ID RICHEESE FACTORY | CONNECTIVITY | PT RICHEESE KULINER INDONESIA | THS | SRI NURFALAH | Noviyan Setiadi |  | 01-JUL-16 | 31-DEC-18 | 70.32 | 0 | -70.32 | LAG |  | 150000000 | REGULER | 09/08/2018 16:54:05
PROJ1169 | PENGADAAN JASA PENGEMBANG APLIKASI E-PAS & INFRASTRUKTUR PENDUKUNGNYA PT PUPUK SRIWIDJAJA PALEMBANG | APPLICATION | PUPUK SRIWIJAYA | MAS | RIKA AMALIA SASANTY | MUHAMMAD HANIS | PT Infomedia Nusantara | 23-MAR-18 | 28-DEC-18 | 53 | 44.3 | -8.7 | LAG |  | 523800000 | STRATEGIS | 11/07/2018 10:49:03
PROJ1240 | PERUBAHAN LAYANAN DAN PENAMBAHAN LOKASI MANAGE SERVICE ASTINET LITE 212 LOKASI PT. CHAROEN POKPHAND | CONNECTIVITY | CHAROEN POKPHAND INDONESIA PT | MAS | YUSUF SARTONO | ANISAH SOFWATI |  | 27-MAR-18 | 26-MAR-19 | 51.8 | 28.6 | -23.2 | LAG |  | 5003200000 | ORDINARY | 09/08/2018 17:01:06
PROJ1581 | PENGADAAN PERANGKAT GATE DAN PENDUKUNG SISTEM TIKET ELEKTRONIK DI PT TRANPORTASI JAKARTA | CPE & OTHERS | PT. TRANSPORTASI JAKARTA | TMS | DODI IRAWAN | ERSYHAD PRABAWA ADIGUNA | PT. Nutech Integrasi | 19-APR-18 | 04-SEP-18 | 100 | 98.1 | -1.9 | LAG | 8.CR (perubahan yang belum terkendali) & amandemen (customer) | 8507262000 | BIG | 03/08/2018 17:07:40
PROJ1646 | PROYEK PEMBANGUNAN B RESIDENCE, SERPONG - TANGERANG PEKERJAAN ELEKTRONIK | SMART BUILDING | PT. MAJU GEMILANG SERPONG | PCS | NAZIRWAN, ST. M.KOM | SUNARTO AMSALOM SAIRO | PT PINS Indonesia | 15-JAN-18 | 15-SEP-19 |  |  |  | LEAD |  | 17985000000 | MEDIUM | 17/05/2018 11:38:36
PROJ212 | WIFI.ID KIMIA FARMA (TAHAP 2) | CONNECTIVITY | KIMIA FARMA PT | HWS | SRI NURFALAH | MELANY ULFA |  | 01-JAN-17 | 31-DEC-18 | 99.997 | 89 | -10.997 | LAG |  | 318000000 | REGULER | 09/08/2018 16:55:57
PROJ2398 | PEKERJAAN ELEKTRONIK PROJEK TRANS PARK BEKASI | SMART BUILDING | ADHI KARYA PT | PCS | IMAM ZAHIR | DWI PUDJI IRAWATI | PT PINS Indonesia | 26-JUL-18 | 20-JUL-19 |  |  |  | LEAD |  | 20300000156 | BIG | 13/08/2018 15:47:56
PROJ26 | PROJECT SMART BUILDING SENTRALAND SEMARANG | SMART BUILDING | PERUMNAS PERUM | PCS | HADI TRIYONO | RADIAN SIGIT DWIANANTO | PT PINS Indonesia | 16-JAN-15 | 31-MAR-18 | 100 | 87.181 | -12.8182 | DELAY | 1.Delivery barang/jasa (mitra) | 4129738470 | BIG | 04/06/2018 14:34:07
PROJ29 | PROJECT GRAND TARUMA KARAWANG | SMART BUILDING | ADHI KARYA PT | PCS | TEDDY AWALUDIN | NOVI ANDRIYANI | PT PINS Indonesia | 09-MAY-14 | 31-MAR-18 | 100 | 99.44 | -0.56 | DELAY | 8.CR (perubahan yang belum terkendali) & amandemen (customer) | 2888000000 | SMALL | 14/03/2018 10:54:07
PROJ31 | PROJECT INTERNATIONAL FINANCIAL CENTER 2 | SMART BUILDING | INTERNATIONAL FINANCIAL CENTER | PCS | HERI IKHWAN DIANA | DWI PUDJI IRAWATI | PT PRAMINDO IKAT NUSANTARA (PINS) | 18-AUG-15 | 30-SEP-17 | 100 | 95.67 | -4.33 | DELAY | 5.Keterlambatan SPK ke mitra (di awal) (Telkom) | 2484600427 | SMALL | 04/10/2017 18:37:28
PROJ37 | PROJECT SMART BUILDING MARIGOLD NAVAPARK - BSD | SMART BUILDING | ADHI KARYA PT | PCS | TEDDY AWALUDIN |  | PT PINS Indonesia | 05-FEB-16 | 31-AUG-18 | 99.934 | 35.491 | -64.4424 | LAG | 8.CR (perubahan yang belum terkendali) & amandemen (customer) | 16500000000 | MEDIUM | 06/04/2018 22:30:19
PROJ459 | PROJECT TRAINING FACILITY GBK | SMART BUILDING | PEMBANGUNAN PERUMAHAN PT | PCS | NAZIRWAN, ST. M.KOM | SHEINI CHRISTY | PT GRAHA SARANA DUTA | 01-APR-17 | 01-SEP-18 | 99.508 | 100 | 0.492 | LAG |  | 3750000000 | STRATEGIS | 06/02/2018 16:26:36
PROJ656 | PROJECT CCTV ORCHARD PARK BATAM | SMART BUILDING | PENGUSAHAAN DAERAH INDUSTRI PULAU BATAM PT | PCS | IRWANDI | AGUS WIDIANTARA |  | 13-OCT-17 | 30-MAR-18 | 100 | 60.06 | -39.94 | DELAY |  | 1468000000 | SMALL | 22/05/2018 08:58:46
PROJ659 | IMPLEMENTASI SISTEM ERP PT. HUTAMA KARYA (PERSERO) | APPLICATION | HUTAMA KARYA PT | PCS | RIKA AMALIA SASANTY | NURUL RIZKI UTAMI | PT Sigma Metrasys Solution | 25-OCT-17 | 25-MAY-19 | 100 | 93.5 | -6.5 | LAG |  | 14120376710 | STRATEGIS | 09/07/2018 10:38:01
PROJ790 | PEKERJAAN SEWA OUTSOURCING EDC DAN PERANGKAT PENDUKUNG OPERASIONAL BANK SUMSEL BABEL | CPE & OTHERS | BPD SUMATERA SELATAN (BANK SUMSEL) | BMS-2 | HASBUR GHALI | EVI NOVIARNI | PT PINS Indonesia | 30-OCT-17 | 30-OCT-20 | 100 | 91.02 | -8.987 | LAG | 3.Perubahan desain/spek pelanggan (customer) | 3518405000 | SMALL | 09/07/2018 10:14:08
PROJ1118 | PROJECT AZZURE STACK PT. ASURANSI JIWA BUMIPUTERA | CPE & OTHERS | ASURANSI JIWA BERSAMA BUMI PUTERA 1912 PT | HWS | ROBIYANTO | WIDIATMOKO | PT Teltranet Aplikasi Solusi (Telkom Telstra) | 15-JAN-18 | 15-JAN-19 | 100 | 75 | -25 | LAG |  | 367057200 | SMALL | 24/04/2018 16:14:50
PROJ1517 | PENGADAAN ENHANCEMENT PORTAL BTN PROPERTI PHASE 2 | CPE & OTHERS | BANK TABUNGAN NEGARA (PERSERO) | BMS-1 | SHEPTIAN KURNIA SALEH | DISKAERI |  | 28-MAR-18 | 28-SEP-18 | 95.79 | 70 | -25.79 | LAG |  | 4086363636 | STRATEGIS | 07/08/2018 14:55:05
PROJ203 | ERP N-HOLDING | APPLICATION | PERKEBUNAN NUSANTARA III PT | MAS | NURUL HIDAYATI | ADRI SYAFMA PUTRA | PT Sigma Metrasys Solution | 17-AUG-16 | 31-DEC-18 | 97.202 | 70.76 | -26.442 | LAG |  | 10888000000 | STRATEGIS | 02/07/2018 17:43:34
PROJ2411 | PROJECT VSAT CSTS BINTUNI | CONNECTIVITY | CSTS | PCS | HARI MULYA | GERRY ROY MANAEK SIAHAAN | PT Patra Telekomunikasi Indonesia, PT Patra Telekomunikasi Indonesia | 15-JAN-18 | 01-AUG-21 |  |  |  | LEAD |  | 27001818182 | BIG | 13/08/2018 17:49:15
PROJ35 | PROJECT PAKET PEKERJAAN ELEKTRONIK UNTUK TUNJUNGAN PLAZA 6 | SMART BUILDING | PAKUWON JATI | PCS | AD STEFEN RATU EDA | YAFRINO, ST, M.M | PT PINS Indonesia | 12-JAN-16 | 30-JUN-18 | 99.99 | 47.553 | -52.4361 | DELAY | 1.Delivery barang/jasa (mitra) | 16640000000 | MEDIUM | 22/05/2018 11:54:12
PROJ442 | PROJECT PROPRIETARY LOYALTY PROGRAM PT PERTAMINA PERSERO | APPLICATION | PERTAMINA PT | ERS | HERU IRMAN |  | PT FINNET INDONESIA | 11-JUL-17 | 11-JUL-22 | 50.96 | 29 | -21.96 | LAG | 1.Delivery barang/jasa (mitra) | 61862540000 | STRATEGIS | 12/04/2018 10:06:50
PROJ449 | PURI MANSION APARTMENT | SMART BUILDING | AGUNG SEDAYU PROPERTINDO | IBS | HERU IRMAN | FAHMI MUHAMMAD HUSIN | Cv Dwi Mandiri Berjaya | 10-JUL-17 | 07-OCT-17 | 100 | 76 | -24 | DELAY | 3.Perubahan desain/spek pelanggan (customer) | 8301000000 | MEDIUM | 22/05/2018 15:29:45
PROJ743 | PENGADAAN SEWA EDC PERUNTUKAN BANSOS BANK BTN | CPE & OTHERS | BANK TABUNGAN NEGARA (PERSERO) | BMS-1 | SHEPTIAN KURNIA SALEH | DISKAERI | PT Sigma Cipta Caraka, PT Sigma Cipta Caraka | 22-SEP-17 | 31-AUG-18 | 100 | 70 | -30 | LAG | 2.Kesiapan lokasi ( customer) | 7265454545 | STRATEGIS | 08/06/2018 14:13:52
PROJ775 | PENGADAAN TEKNOLOGI BIG DATA UNTUK BRI | APPLICATION | BANK RAKYAT INDONESIA (PERSERO) | BMS-1 | ADRID | RUDY WIBOWO | PT Metra-Net | 09-NOV-17 | 31-AUG-18 | 99.991 | 97.718 | -2.273 | LAG | 1.Delivery barang/jasa (mitra) | 25704545454 | STRATEGIS | 27/08/2018 08:27:18
PROJ779 | PROJECT CORE INSURANCE SYSTEM ASKRINDO | APPLICATION | ASURANSI KREDIT INDONESIA | HWS | ZAKY AHMAD | JOKO PADANG RAHINO | PT Sigma Cipta Caraka, PT Sigma Cipta Caraka | 14-NOV-17 | 15-JAN-19 | 70.22 | 51.95 | -18.27 | LAG | 8.CR (perubahan yang belum terkendali) & amandemen (customer) | 10792188000 | STRATEGIS | 05/07/2018 18:46:24
PROJ801 | PROJECT DIGITALISASI KIMIA FARMA | CPE & OTHERS | KIMIA FARMA PT | HWS | ADRID | MELANY ULFA | PT Sigma Cipta Caraka | 27-DEC-17 | 01-SEP-18 | 100 | 98 | -2 | LAG | 1.Delivery barang/jasa (mitra) | 787000000000 | STRATEGIS | 27/08/2018 08:35:30
PROJ832 | PENGADAAN SEWA SALURAN KOMUNIKASI PEJABAT KREDIT LINI APLIKASI BRISPOT DAN MYBRI | CPE & OTHERS | BANK RAKYAT INDONESIA (PERSERO) | BMS-1 | I DEWA MADE AGUS | RUDY WIBOWO | PT Telekomunikasi Selular, PT Telekomunikasi Selular | 21-DEC-17 | 08-JUN-18 | 100 | 98.76 | -1.24 | DELAY | 1.Delivery barang/jasa (mitra) | 250000000000 | STRATEGIS | 07/06/2018 11:44:37
PROJ833 | PEKERJAAN LAYANAN VPN DAN INTERNET 100MBPS AIRNAV | CONNECTIVITY | LEMBAGA PENYELENGGARA PELAYANAN NAVIGASI PENERBANGAN INDONESIA PERUM | TMS | RETNO KURNIAWATI | MOHAMMAD TAUFAN | PT PINS Indonesia, PT PINS Indonesia | 21-DEC-17 | 21-FEB-19 |  |  |  | LEAD |  | 2753841200 | SMALL | 09/02/2018 11:36:08
PROJ89 | ICT FTTH GPON ANANDAMAYA RESIDENCE | SMART BUILDING | ADHI KARYA PT | PCS | ATAM RUSTAM | SHERA MAYANGSARI SUWITO | PT PRAMINDO IKAT NUSANTARA (PINS) | 28-JUL-16 | 31-JAN-18 | 100.06 | 47.56 | -52.501 | DELAY | 1.Delivery barang/jasa (mitra) | 2285000000 | MEDIUM | 31/07/2018 16:31:33
PROJ903 | PROJECT 5000 AKSES POINT WIFI PEGADAIAN | CONNECTIVITY | PEGADAIAN PT | FMS | DWI WIDYA SAKTI | ANDIKA PRATAMA PUTRA |  | 22-FEB-18 | 31-DEC-18 |  |  |  | LAG |  | 18000000000 | BIG | 09/08/2018 17:00:38
PROJ11 | PROJECT PARK LAND AVENUE | SMART BUILDING | SUMMARECON AGUNG TBK | IBS | PRAKOSA TRIWIBOWO | ACHMAD SUTARJONO | PT PRAMINDO IKAT NUSANTARA (PINS) | 01-NOV-15 | 30-DEC-18 | 92.175 | 76.89 | -15.285 | DELAY | 11.Komitmen mitra(termasuk deal harga)(mitra) | 3550000000 | SMALL | 25/04/2018 10:19:49
PROJ132 | PROJECT ASTINET SME BFI FINANCE INDONESIA | CONNECTIVITY | BUNAS FINANCE INDONESIA PT | FMS | NUR WIJAYANTO | YENI SUPARTINI |  | 28-NOV-16 | 31-JAN-18 | 100 | 96.5 | -3.504 | DELAY |  | 3462520000 | SMALL | 15/01/2018 15:18:48
PROJ1492 | ORACLE ENTERPRISE BUSINESS SUITE (EBS) SUPPLY CHAIN MANAGEMENT`MODULE PT. PELNI (PERSERO) | APPLICATION | PELAYARAN NASIONAL INDONESIA (PELNI) PT | MLS | ADRID | NAWIN |  | 06-MAR-18 | 21-SEP-18 | 67.5 | 55.9 | -11.6 | LAG |  | 8935000000 | STRATEGIS | 27/08/2018 09:02:06
PROJ235 | ROLL OUT I ERP PTPN IV (MEDAN) | APPLICATION | PERKEBUNAN NUSANTARA IV PT | MAS | NURUL HIDAYATI | SIMON | PT Sigma Metrasys Solution | 01-MAR-17 | 31-DEC-18 | 99.992 | 99.8 | -0.192 | LAG | 3.Perubahan desain/spek pelanggan (customer) | 55638090000 | STRATEGIS | 30/05/2018 13:23:45
PROJ34 | PROJECT HOTEL U JENEVELLA BANDUNG | SMART BUILDING | ADHI KARYA PT | PCS | NAZIRWAN, ST. M.KOM | NURUL RIZKI UTAMI | PT INFOMEDIA NUSANTARA | 05-JAN-16 | 31-AUG-16 | 100 | 50 | -50 | DELAY | 3.Perubahan desain/spek pelanggan (customer) | 2520145000 | SMALL | 26/10/2017 10:44:50
PROJ36 | PROJECT SMART BUILDING HOTEL KEMPINSKI | SMART BUILDING | GRAHA ALAM LESTARI | PCS | AD STEFEN RATU EDA | GERRY ROY MANAEK SIAHAAN | PT PINS Indonesia | 11-FEB-16 | 30-JUN-18 | 97.37 | 61.29 | -36.08 | DELAY | 11.Komitmen mitra(termasuk deal harga)(mitra) | 23000000000 | BIG | 22/05/2018 11:21:02
PROJ414 | PROJECT PENGADAAN LIFT UNTUK BANK SUMUT | CPE & OTHERS | BANK SUMATERA UTARA | BMS-2 | IRWANDI | ERWIN ULONG NAINGGOLAN | PT PINS Indonesia | 15-MAY-17 | 31-MAR-18 | 100 | 100 | 0 | DELAY | 10.Keterbatasan kapabilitas mitra (mitra) | 3616900000 | SMALL | 22/05/2018 08:52:38
PROJ572 | PROJECT CHANGE REQUEST E PROCUREMENT PTPN III | APPLICATION | PERKEBUNAN NUSANTARA III PT | MAS | NURUL HIDAYATI | ADRI SYAFMA PUTRA | PT Sigma Cipta Caraka | 28-AUG-17 | 31-DEC-18 | 100 | 100 | 0 | LAG |  | 222612575 | STRATEGIS | 21/05/2018 14:06:13
PROJ643 | PEKERJAAN PROYEK RUSUNAMI JAKABARING TOWER 3 | SMART BUILDING | PEMBANGUNAN PERUMAHAN PT | PCS | NAZIRWAN, ST. M.KOM | RADIAN SIGIT DWIANANTO | PT GRAHA SARANA DUTA | 02-OCT-17 | 28-MAR-18 | 99.83 | 99.26 | -0.57 | DELAY |  | 8900000000 | SMALL | 18/04/2018 12:56:06
PROJ744 | ROLL OUT 2 PTPN 6 JAMBI | APPLICATION | PERKEBUNAN NUSANTARA VI PT | MAS | NURUL HIDAYATI | ANWAR | PT Sigma Metrasys Solution | 01-OCT-17 | 31-DEC-18 | 100 | 67 | -33 | LAG | 3.Perubahan desain/spek pelanggan (customer) | 30896640000 | STRATEGIS | 02/07/2018 17:25:31
PROJ746 | ROLL OUT 2 PTPN 2 MEDAN | APPLICATION | PERKEBUNAN NUSANTARA II PT | MAS | NURUL HIDAYATI | SIMON | PT Sigma Metrasys Solution | 01-OCT-17 | 31-AUG-18 | 73.75 | 51 | -22.75 | LAG | 3.Perubahan desain/spek pelanggan (customer) | 31982850000 | BIG | 21/05/2018 14:08:25
PROJ749 | ROLL OUT 3 PTPN 13 PONTIANAK | APPLICATION | PERKEBUNAN NUSANTARA XIII | MAS | NURUL HIDAYATI | HAMIDONG | PT Sigma Metrasys Solution | 01-OCT-17 | 30-NOV-18 | 73.75 | 51 | -22.75 | LAG | 1.Delivery barang/jasa (mitra) | 18103500000 | BIG | 21/05/2018 14:09:46
PROJ750 | ROLL OUT 3 PTPN XIV MAKASAR | APPLICATION | ABC PRESIDENT INDONESIA, PT | MAS | NURUL HIDAYATI | NADIAH LIESTYASARI | PT Sigma Metrasys Solution | 01-OCT-17 | 30-NOV-18 | 73.75 | 51 | -22.75 | LAG |  | 9172440000 | STRATEGIS | 21/05/2018 14:11:32
PROJ771 | PROJECT E-DAPEM TASPEN | APPLICATION | TASPEN PT | HWS | ZAKY AHMAD | ELMAN HASIHOLAN SIANTURI, IR.MT. | PT Sigma Cipta Caraka | 17-OCT-17 | 18-OCT-21 | 97.7 | 86.24 | -11.46 | LAG | 3.Perubahan desain/spek pelanggan (customer) | 585728682000 | STRATEGIS | 05/07/2018 18:44:58
PROJ774 | PENGADAAN EDGE ROUTER MPLS & CELLULER, DAN CORE ROUTER | CPE & OTHERS | BANK RAKYAT INDONESIA (PERSERO) | BMS-1 | FAHMI RAHMANTHAHA NURDINSYAH | RUDY SETYO NUGROHO | PT PINS Indonesia, PT PINS Indonesia | 04-DEC-17 | 02-FEB-18 | 100 | 99 | -1 | DELAY | 4.Keterlambatan BAST (customer) | 15300000000 | STRATEGIS | 04/07/2018 09:43:52
PROJ808 | ERP SAP PT SEMEN BATURAJA | APPLICATION | SEMEN BATURAJA PT | MAS | KRSHNA SULANJANA | MUHAMMAD HANIS | PT Sigma Metrasys Solution, PT Sigma Metrasys Solution | 29-DEC-17 | 04-JAN-19 | 96.2 | 80 | -16.2 | LAG |  | 34771819125 | BIG | 13/08/2018 14:56:02
PROJ815 | PROJECT REPLACEMENT OF OBSOLETE NETWORK BACKBONE EQUIPMENTS DC SURABAYA BTN | CPE & OTHERS | BANK TABUNGAN NEGARA (PERSERO) | BMS-1 | FAHMI RAHMANTHAHA NURDINSYAH | DISKAERI | PT Sigma Cipta Caraka, PT Sigma Cipta Caraka | 29-DEC-17 | 31-MAY-18 | 97.08 | 99.04 | 1.96 | DELAY | 4.Keterlambatan BAST (customer) | 36900000000 | STRATEGIS | 04/07/2018 17:03:32
PROJ823 | PEKERJAAN PENGADAAN 25 UNIT MESIN ATM PT BANK NTB | CPE & OTHERS | BANK PEMBANGUNAN DAERAH NTB | FMS | IRWANDI | FERDINAND YOHANNIS MARKUS | PT Sigma Cipta Caraka, PT Sigma Cipta Caraka | 11-JAN-18 | 31-MAY-18 | 100 | 82 | -18 | DELAY | 2.Kesiapan lokasi ( customer) | 3243722500 | SMALL | 31/05/2018 11:07:55
PROJ928 | PENGADAAN SEWA 12.000 UNIT EDC BNI UNTUK PT. BRINGIN GIGANTARA | CPE & OTHERS | BANK NEGARA INDONESIA 46TBK(BNI 46) | BMS-1 | RUDIONO | ARJANI ROSALINA, RADEN | PT Sigma Cipta Caraka | 15-JAN-18 | 31-DEC-18 | 55 | 50.477 | -4.523 | LAG | 2.Kesiapan lokasi ( customer) | 57000000000 | BIG | 23/04/2018 14:44:50
PROJ114 | PROJECT IMPLEMENTASI MICROSOFT DYNAMIC AX ERP PT. PPI | APPLICATION | PERUSAHAAN PERDAGANGAN INDONESIA (PERSERO) | TDS | NURUL HIDAYATI | CAHAYA RUMENTA | PT Signet Pratama | 21-DEC-15 | 31-AUG-18 | 100 | 80 | -20 | LAG | 7.SoW belum sepakat (Telkom) | 21600000000 | STRATEGIS | 21/06/2018 17:07:00
PROJ1361 | PENYEDIAAN MINING VEHICLE DENGAN TRACKING SYSTEM UNTUK KEBUTUHAN STOCK PILE DI AREA TAMBANG KINTAP PT ARUTMIN INDONESIA | CPE & OTHERS | BUMI RESOURCES TBK | ERS | ARIEF SUSILO WIBOWO | TITIS WENING | PT Sigma Cipta Caraka | 01-MAR-18 | 31-DEC-18 | 81.44 | 59.91 | -21.53 | LAG | 3.Perubahan desain/spek pelanggan (customer) | 32934893200 | BIG | 20/04/2018 11:43:57
PROJ141 | PROJECT SEAT MANAGEMENT PT. PELABUHAN INDONESIA (PELINDO) III | CPE & OTHERS | PELINDO III | MLS | TEDDY AWALUDIN | RIFANDA PUTRI INDRESWARI | PT PINS Indonesia | 01-JAN-17 | 31-DEC-19 | 71.475 | 66.29 | -5.185 | LAG | 3.Perubahan desain/spek pelanggan (customer) | 13868640000 | STRATEGIS | 14/03/2018 11:25:56
PROJ1489 | PENGADAAN PERSONAL COMPUTER (PC) DAN MANAGE SERVICE DI PT BANK DKI TAHAP II | CPE & OTHERS | BANK DKI | BMS-2 | HASBUR GHALI | NADIA PRIMASARI | PT PINS Indonesia | 30-APR-18 | 31-AUG-18 | 93.67 | 98.25 | 4.58 | LAG | 2.Kesiapan lokasi ( customer) | 7840000000 | ORDINARY | 06/08/2018 15:09:35
PROJ1755 | PENGADAAN PERANGKAT HARDWARE UNTUK KEBUTUHAN ADMIN KAPAL, KANTOR PUSAT DAN CABANG DENGAN MENGGUNAKAN SKEMA SEAT MANAGEMENT | CPE & OTHERS | PELAYARAN NASIONAL INDONESIA (PELNI) PT | MLS | FAHMI RAHMANTHAHA NURDINSYAH | NAWIN | PT Sigma Cipta Caraka | 26-JUN-18 | 26-JUN-21 | 10 | 20 | 10 | LAG |  | 16205288400 | MEDIUM | 30/05/2018 11:16:04
PROJ183 | PENGADAAN LICENSE DAN IMPLEMENTASI ORACLE FUSION ERP CLOUD SOLUTION PT. BUKAKA | APPLICATION | POSO ENERGY | IBS | DODI IRAWAN | BUDIMAN | SIGMA SOLUSI INTEGRASI, SIGMA SOLUSI INTEGRASI | 28-DEC-16 | 10-JAN-18 | 100 | 99.5 | -0.501 | DELAY | 10.Keterbatasan kapabilitas mitra (mitra) | 7870860487 | ORDINARY | 25/06/2018 15:59:55
PROJ211 | WIFI.ID BPD SUMATERA BARAT | CONNECTIVITY | BANGKOK BANK | BMS-2 | SRI NURFALAH | ARFAN SUATAN |  | 01-JAN-17 | 31-DEC-18 | 100.01 | 77 | -23.01 | LAG |  | 324000000 | REGULER | 09/08/2018 16:55:36
PROJ2396 | PROJECT EASTERN GREEN BEKASI | SMART BUILDING | ADHI KARYA PT | PCS | PRAKOSA TRIWIBOWO | DWI PUDJI IRAWATI |  | 30-NOV-17 | 30-NOV-19 | 26.18 | 21.38 | -4.8 | LAG | 2.Kesiapan lokasi ( customer) | 6850000000 | MEDIUM | 13/08/2018 15:28:15
PROJ375 | PROJECT WIFI.ID BANK RAKYAT INDONESIA | CONNECTIVITY | BANK RAKYAT INDONESIA (PERSERO) | BMS-1 | SRI NURFALAH | RUDY SETYO NUGROHO |  | 01-JAN-17 | 31-DEC-18 |  |  |  | LAG |  | 138772727 | REGULER | 09/08/2018 16:56:58
PROJ44 | PROJECT LAYANAN VPN IP UNTUK KFC | CONNECTIVITY | FASTFOOD INDONESIA | THS | I DEWA MADE AGUS | ANAK AGUNG ARDHA CHANDRA DEWI |  | 01-JAN-16 | 31-DEC-18 | 100 | 86.4 | -13.6 | LAG | 2.Kesiapan lokasi ( customer) | 1032000000 | ORDINARY | 19/07/2018 16:41:29
PROJ456 | ICT DAN ELECTRONIC INSTALLATION DI THE WILADATIKA RESIDENCE | SMART BUILDING | ARTHA TELEKOMINDO | PCS | TEDDY AWALUDIN | GOGATAMA DESENWA PRAYOGA | PT PINS Indonesia | 01-DEC-15 | 31-MAR-18 | 100 | 48.49 | -51.51 | DELAY | 5.Keterlambatan SPK ke mitra (di awal) (Telkom) | 5100000000 | MEDIUM | 14/03/2018 11:46:28
PROJ5 | PROJECT SAHID JOGJA LIFESTYLE | SMART BUILDING | GE OPERATIONS INDONESIA | IBS | HADI TRIYONO | TRINIL ANJAR LESTARI, ST | PT PINS Indonesia | 26-MAR-15 | 28-FEB-18 | 100 | 95.39 | -4.61 | DELAY | 4.Keterlambatan BAST (customer) | 1700000000 | SMALL | 30/05/2018 14:27:33
PROJ615 | PROJECT PASANG BARU VPN IP 1.040 LOKASI DAN UPGRADE 900 LOKASI UNTUK BRI VIA SATKOM | CONNECTIVITY | BANK RAKYAT INDONESIA (PERSERO) | BMS-1 | NUR WIJAYANTO | RUDY SETYO NUGROHO |  | 07-SEP-17 | 31-JAN-18 | 100 | 94.39 | -5.61 | DELAY |  | 47255820000 | BIG | 05/04/2018 10:35:05
PROJ640 | PROJECT RELOKASI DAN UPGRADE DWDM BANK DANAMON | CONNECTIVITY | BANK DANAMON INDONESIA TBK | BMS-2 | WIM MUDJIONO | ARISTYA MEGA PUTRANTO |  | 17-OCT-17 | 30-NOV-17 | 100 | 94.5 | -5.5 | DELAY |  | 2169980331 | MEDIUM | 14/05/2018 16:32:14
PROJ642 | PEKERJAAN PROYEK RUSUNAMI JAKABARING TOWER 1 DAN 2 | SMART BUILDING | PEMBANGUNAN PERUMAHAN PT | PCS | NAZIRWAN, ST. M.KOM | RADIAN SIGIT DWIANANTO | PT GRAHA SARANA DUTA | 02-OCT-17 | 28-MAR-18 | 99.33 | 100.63 | 1.305 | DELAY |  | 6000000000 | SMALL | 04/06/2018 12:02:40
PROJ748 | ROLL OUT 3 PTPN 8 BANDUNG | APPLICATION | PERKEBUNAN NUSANTARA VIII PT | MAS | NURUL HIDAYATI | NURI FAJARIYANAH | PT Sigma Metrasys Solution | 01-OCT-17 | 30-NOV-18 | 95.6 | 51 | -44.6 | LAG | 3.Perubahan desain/spek pelanggan (customer) | 65776050000 | STRATEGIS | 21/05/2018 14:09:05
PROJ753 | PEKERJAAN INFRASTRUKTUR GPON GALAXY MALL 3 SURABAYA | SMART BUILDING | SINAR GALAXI | TDS | ATAM RUSTAM | SUCI ERNANINGTYAS | PT PRAMINDO IKAT NUSANTARA (PINS) | 17-NOV-17 | 28-FEB-18 | 99.85 | 88.77 | -11.08 | DELAY |  | 2300000000 | SMALL | 18/05/2018 14:16:29
PROJ835 | PEKERJAAN JASA IMPLEMENTASI ENTERPRISE RESOURCES PLANNING (ERP) MODUL KEUANGAN DI PERUM LPPNPI | APPLICATION | LEMBAGA PENYELENGGARA PELAYANAN NAVIGASI PENERBANGAN INDONESIA PERUM | TMS | RIKA AMALIA SASANTY | MOHAMMAD TAUFAN | PT Infomedia Nusantara, PT Infomedia Nusantara | 20-DEC-17 | 29-AUG-18 | 100 | 63.03 | -36.97 | LAG | 3.Perubahan desain/spek pelanggan (customer) | 439728300 | REGULER | 11/07/2018 10:48:22
PROJ852 | PENYEDIAAN DIGITAL MENU BOARD BURGER KING INDONESIA 159 STORE | CPE & OTHERS | MAP FOOD & BEVERAGE | THS | HASBUR GHALI | EVY YULIA RAMADHAN | PT Teltranet Aplikasi Solusi (Telkom Telstra), PT Teltranet Aplikasi Solusi (Telkom Telstra) | 01-FEB-18 | 30-NOV-19 | 68.22 | 59.12 | -9.1 | LAG | 2.Kesiapan lokasi ( customer) | 3728736000 | SMALL | 04/04/2018 10:31:03
PROJ99 | PEKERJAAN MANAGE SERVICE KIOSK LAYANAN PPOB DAN MANAGE SERVICE NFC READER SMART CARD NON KIOSK | APPLICATION | PT. JARING SOLUSI APLIKASI | TMS | NURUL HIDAYATI | ERSYHAD PRABAWA ADIGUNA | PT Infomedia Nusantara | 12-AUG-16 | 12-AUG-21 | 99.555 | 78.91 | -20.645 | LAG | 3.Perubahan desain/spek pelanggan (customer) | 53426340000 | BIG | 30/05/2018 12:57:15
PROJ1680 | ICT LIVING WORLD PEKANBARU (PT TIGA DUA DELAPAN - CC KAWAN LAMA GROUP) | SMART BUILDING | KAWAN LAMA SEJAHTERA | TDS | ATAM RUSTAM | YULISTIKA RAHAYU |  | 23-MAR-18 | 30-JUN-18 | 99.65 | 95.87 | -3.78 | DELAY |  | 1110000000 | MEDIUM | 05/06/2018 17:29:30
PROJ648 | PENGADAAN JARINGAN KOMUNIKASI TEKNOLOGI MULTI CARRIER ACCESS (MCA) | CPE & OTHERS | BANK MANDIRI | BMS-1 | ARI WIDIYANTO | FACHRUL INDRACAHYO |  | 20-OCT-17 | 20-DEC-17 |  |  |  | DELAY |  | 4200000000 | MEDIUM | 24/01/2018 14:16:38