## Worksheet
ID PROJECT | ID LOP | PROJECT NAME | TYPE PROJECT | CLIENT | SEGMEN | NOMOR KB | NOMOR KL | PM NAME | AM NAME | PARTNERS | START DATE | END DATE | PLAN | ACHIEVEMENT | DEVIASI | STATUS | REASON OF DELAY | PROJECT VALUE | CATEGORY | LAST UPDATE
PROJ1114 |  | PROJECT BALAI PUSTAKA | CPE & OTHERS | BALAI PUSTAKA PT | EMS |  |  | HASBUR GHALI | CAHYO BUWONO, ST | PT Balebat Dedikasi Prima, PT Balebat Dedikasi Prima | 15-FEB-18 | 30-NOV-18 | 100 | 77.6 | -22.4 | DELAY | 1.Delivery barang/jasa (mitra) | 102125800000 | MEGA | 15/10/2018 10:20:12
PROJ1581 | LOP102568 | PENGADAAN PERANGKAT GATE DAN PENDUKUNG SISTEM TIKET ELEKTRONIK DI PT TRANPORTASI JAKARTA | CPE & OTHERS | PT. TRANSPORTASI JAKARTA | TMS |  |  | DODI IRAWAN | ERSYHAD PRABAWA ADIGUNA | PT. Nutech Integrasi | 19-APR-18 | 31-OCT-18 | 100 | 100 | 0 | DELAY | 8.CR (perubahan yang belum terkendali) & amandemen (customer) | 8507262000 | ORDINARY | 26/11/2018 15:10:06
PROJ21 |  | PROJECT CWJ 2 PHASE 1 | SMART BUILDING | CIPUTRA WORLD JAKARTA | PCS |  |  | IRWANDI | GERRY ROY MANAEK SIAHAAN | PT PINS Indonesia | 26-SEP-14 | 31-DEC-17 | 99.695 | 99.699 | 0.0049 | DELAY | 2.Kesiapan lokasi ( customer) | 23660990600 | BIG | 30/11/2018 11:16:39
PROJ2155 | LOP105438 | PENGADAAN ADMINISTRATIVE SERVICE ONLY PT. JALIN PEMBAYARAN NUSANTARA | CPE & OTHERS | PT JALIN PEMBAYARAN NUSANTARA | BMS-1 |  |  | DODI IRAWAN |  | PT Administrasi Medika | 03-JUL-18 | 31-DEC-18 | 78.48 | 8 | -70.48 | LAG | 1.Delivery barang/jasa (mitra) | 120000000 | REGULAR | 26/11/2018 11:37:26
PROJ234 |  | ROLL OUT I ERP PTPN III (MEDAN) | APPLICATION | PERKEBUNAN NUSANTARA III PT | MAS |  |  | NURUL HIDAYATI | SIMON | PT Sigma Metrasys Solution | 01-MAR-17 | 31-DEC-18 | 100 | 99.98 | -0.02 | LAG | 4.Keterlambatan BAST (customer) | 65172600000 | MEGA | 29/10/2018 19:20:29
PROJ236 |  | ROLL OUT I ERP PTPN IX (SEMARANG) | APPLICATION | PERKEBUNAN NUSANTARA IX | MAS |  |  | NURUL HIDAYATI | NANANG RUSTANDI | PT Sigma Metrasys Solution | 01-MAR-17 | 31-DEC-18 | 99.992 | 99.52 | -0.472 | LAG | 4.Keterlambatan BAST (customer) | 31017330000 | BIG | 29/10/2018 19:16:54
PROJ237 |  | ROLL OUT I ERP PTPN XII (SURABAYA) | APPLICATION | PERKEBUNAN NUSANTARA XII PT | MAS |  |  | NURUL HIDAYATI | JUNED DRAJAT PRASETYO | PT Sigma Metrasys Solution | 01-MAR-17 | 08-OCT-18 | 100 | 77.5 | -22.5 | DELAY | 2.Kesiapan lokasi ( customer) | 19793160000 | ORDINARY | 19/10/2018 18:51:02
PROJ2443 | LOP106326 | SEWA LAYANAN LAN EXTENSION ASSET 5 |  | PERTAMINA PT | ERS |  |  | IKA SADERA M |  | PT Nusantara Compnet Integrator, PT Wave Communication Indonesia | 26-OCT-18 | 28-DEC-18 |  |  |  | LAG |  | 5992332000 | ORDINARY | 13/11/2018 16:10:56
PROJ2486 | LOP106379 | PEKERJAAN INSTALASI ELEKTRIKAL PADA PROYEK PEMBANGUNAN GEDUNG HK OFFICE | SMART BUILDING | HUTAMA KARYA PT | PCS |  |  | AD STEFEN RATU EDA |  | PT PINS Indonesia | 13-AUG-18 | 15-DEC-18 | 76.77 | 28.02 | -48.75 | LAG | 11.Komitmen mitra(termasuk deal harga)(mitra) | 7425000000 | ORDINARY | 26/11/2018 11:21:43
PROJ2583 | LOP106720 | JASA MIGRASI PORT DARI LAYANAN VSAT KE MPLS DI 244 REMOTE | CONNECTIVITY | BANK RAKYAT INDONESIA (PERSERO) | BMS-1 |  |  | NUR WIJAYANTO |  | PT Multimedia Nusantara | 31-AUG-18 | 31-DEC-18 |  |  |  | LEAD |  | 142450000 | REGULAR | 27/11/2018 14:48:39
PROJ2643 | LOP106895 | CONTACT CENTER PT. ANUGERAH PHARMINDO LESTARI | CPE & OTHERS | ANUGERAH PHARMINDO LESTARI | HWS |  |  | SHEPTIAN KURNIA SALEH | QUVIN NOLA PRIHANDANI | PT Infomedia Nusantara | 27-AUG-18 | 07-JAN-19 | 44.35 | 46 | 1.65 | LAG | 3.Perubahan desain/spek pelanggan (customer) | 2609196400 | ORDINARY | 28/11/2018 18:02:10
PROJ27 |  | PROJECT CEMINDO TOWER | SMART BUILDING | CEMINDO TOWER | PCS |  |  | NAZIRWAN, ST. M.KOM | MUHAMMAD SIDIK | PT TELKOM AKSES | 01-SEP-14 | 31-DEC-17 | 100.05 | 100.25 | 0.2021 | DELAY | 4.Keterlambatan BAST (customer) | 13900000000 | ORDINARY | 12/09/2018 10:26:05
PROJ2710 | LOP106868 | CCTV, ALARM AND ACCESS DOOR PT.OTO MULTIARTHA | CPE & OTHERS | PT OTO MULTIARTHA | FMS |  |  | HARI MULYA |  | PT Datalink Solution | 30-AUG-18 | 29-DEC-18 | 110.62 | 75.89 | -34.73 | LAG | 1.Delivery barang/jasa (mitra) | 6626436750 | ORDINARY | 31/10/2018 20:14:46
PROJ2805 | LOP107255 | PEKERJAAN ELEKTRONIK PEMBANGUNAN MENARA BINAKARSA KUNINGAN | SMART BUILDING | PT ADHICON PERKASA | PCS |  |  | TEDDY AWALUDIN |  | PT PINS Indonesia | 20-AUG-18 | 31-DEC-18 | 78.6 | 24.3 | -54.3 | LAG |  | 5370000000 | ORDINARY | 23/11/2018 10:22:37
PROJ3160 | LOP108197 | PENGADAAN PENGEMBANGAN SISTEM APLIKASI OFFICE AUTOMATION JAMKRINDO | APPLICATION | GD. JAMKRINDO | FMS |  |  | SHEPTIAN KURNIA SALEH | MULYADI, ST | PT Sigma Cipta Caraka | 08-OCT-18 | 28-DEC-18 | 67.04 | 37.5 | -29.54 | LAG | 8.CR (perubahan yang belum terkendali) & amandemen (customer) | 953447000 | REGULAR | 23/11/2018 10:01:51
PROJ3185 | LOP108406 | PENGADAAN MITRA PENGELOLA UNIT LAYANAN BPJS KETENAGAKERJAAN | CPE & OTHERS | BPJS KETENAGAKERJAAN | HWS |  |  | ADRID | SUSILO IRAWAN | PT Infomedia Nusantara | 12-OCT-18 | 31-JAN-19 | 69.65 | 27 | -42.65 | LAG | 1.Delivery barang/jasa (mitra) | 50000000000 | MEGA | 25/11/2018 08:52:36
PROJ642 |  | PEKERJAAN PROYEK RUSUNAMI JAKABARING TOWER 1 DAN 2 | SMART BUILDING | PEMBANGUNAN PERUMAHAN PT | PCS |  |  | NAZIRWAN, ST. M.KOM | RADIAN SIGIT DWIANANTO | PT Graha Sarana Duta | 02-OCT-17 | 28-MAR-18 | 99.33 | 100.63 | 1.305 | DELAY | 13.Kendala Finansial ( Customer ) | 6000000000 | ORDINARY | 12/09/2018 10:13:13
PROJ747 |  | ROLL OUT 2 PTPN 7 LAMPUNG | APPLICATION | PERKEBUNAN NUSANTARA VII PT | MAS |  |  | NURUL HIDAYATI | ADE NIRWANI | PT Sigma Metrasys Solution | 01-OCT-17 | 02-OCT-18 | 100 | 60 | -40 | DELAY | 8.CR (perubahan yang belum terkendali) & amandemen (customer) | 33189750000 | BIG | 29/10/2018 18:55:19
PROJ813 | LOP105398 | PENGADAAN MESIN SOA DAN UPGRADE AS-400 BTN | CPE & OTHERS | BANK TABUNGAN NEGARA (PERSERO) | BMS-1 |  |  | FAHMI RAHMANTHAHA NURDINSYAH | DISKAERI | PT Sigma Cipta Caraka | 28-DEC-17 | 31-MAY-18 | 100 | 99.9 | -0.1 | DELAY | 4.Keterlambatan BAST (customer) | 109950000000 | MEGA | 05/11/2018 18:24:30
PROJ824 |  | PROJECT PEKERJAAN JASA IMPLEMENTASI ENTERPRISE RESOURCE PLANNING (ERP) DI PERUM PERURI | APPLICATION | PERURI PERUM | FMS |  |  | IRWANDI | WIJAYANTO | PT Sigma Metrasys Solution | 04-JAN-18 | 30-NOV-18 | 99.45 | 74 | -25.45 | DELAY | 1.Delivery barang/jasa (mitra) | 54329137800 | MEGA | 30/11/2018 10:13:07
PROJ847 | LOP102741 | PENGADAAN DAN PEMASANGAN PERANGKAT BCM KONTER DAN MESIN AUTOGATE DI BANDARA I GUSTI NGURAH RAI | CPE & OTHERS | ANGKASAPURA I | TMS |  |  | ADRID | HUSNI MUBARAK, ST | PT Signet Pratama | 30-JAN-18 | 01-SEP-18 | 100 | 100 | 0 | DELAY | 4.Keterlambatan BAST (customer) | 64093880000 | MEGA | 27/11/2018 11:23:33
PROJ3528 |  | DELIVERY LAYANAN DATIN FIBER OPTIC UNTUK PT INDOMARCO PRISMATAMA (INDOMARET GROUP) | CONNECTIVITY | INDOMARCO PRISMATAMA 2 | TDS |  |  | AGUS SOLEH | SYAFRIANDI |  | 21-NOV-18 | 31-DEC-18 |  |  |  | LEAD |  | 0 | REGULAR | 27/11/2018 20:08:41
PROJ375 |  | PROJECT WIFI.ID BANK RAKYAT INDONESIA | CONNECTIVITY | BANK RAKYAT INDONESIA (PERSERO) | BMS-1 |  |  | SRI NURFALAH | RUDY SETYO NUGROHO |  | 01-JAN-17 | 31-DEC-18 | 82 | 10 | -72 | LAG |  | 138772727 | REGULAR | 09/11/2018 17:03:55
PROJ2794 | LOP9 | DISASTER RECOVERY CENTER ERP ANTAM (PROJECT TEST) | APPLICATION | ANEKA TAMBANG PT | ERS | 456 | ["1212","abc"] | HASBUR GHALI | DITO BARATA JUNANTO |  | 01-JAN-18 | 27-DEC-18 | 87.5 | 36 | -51.5 | LAG | 1.Delivery barang/jasa (mitra) | 50000000 | REGULAR | 29/11/2018 05:15:29
PROJ3510 |  | AKTIVASI LINK ASTINET LITE PT SISTELINDO MITRALINTAS UNTUK PT RICHEESE KULINER INDONESIA | CONNECTIVITY | SISTELINDO MITRALINTAS | MCS |  |  | YUSUF SARTONO | PUTREN PUSPITASARI |  | 26-OCT-18 | 31-DEC-18 |  |  |  | LEAD |  | 0 | REGULAR | 27/11/2018 14:06:43
PROJ211 |  | WIFI.ID BPD SUMATERA BARAT | CONNECTIVITY | BANGKOK BANK | BMS-2 |  |  | SRI NURFALAH | ARFAN SUATAN |  | 01-JAN-17 | 31-DEC-18 | 100.01 | 80 | -20.01 | LAG |  | 324000000 | REGULAR | 09/11/2018 17:06:16
PROJ1194 |  | PROJECT PENGEMBANGAN ERP MERAH PUTIH DI PT. VIRAMA KARYA (PERSERO) | APPLICATION | VIRAMA KARYA PT | PCS |  |  | RIKA AMALIA SASANTY | MASRUL DINAR | PT Global Sukses Solusi | 15-FEB-18 | 31-OCT-18 | 92.68 | 97.7 | 5.02 | DELAY | 4.Keterlambatan BAST (customer) | 1135766181 | ORDINARY | 13/11/2018 12:10:31
PROJ1275 | LOP102281 | PAKET SISTEM ELEKTRONIK APARTEMENT TOWER 1, HOTEL DAN MALL,PROYEK GREEN SEDAYU TAMAN PALEM JAKARTA | SMART BUILDING | AGUNG SEDAYU PROPERTINDO | IBS |  |  | HERU IRMAN | FAHMI MUHAMMAD HUSIN | PT PINS Indonesia, PT PINS Indonesia | 26-MAR-18 | 26-MAR-19 | 56.03 | 19.593 | -36.4364 | LAG | 1.Delivery barang/jasa (mitra) | 26124999999 | BIG | 31/10/2018 15:35:43
PROJ137 |  | PROJECT JASA KONSULTASI PENDAMPINGAN ICT PT. PAL INDONESIA (PERSERO) | APPLICATION | PAL | IBS |  |  | NURUL HIDAYATI | VALENTINA NAINGGOLAN | PT Sigma Cipta Caraka | 01-DEC-16 | 31-DEC-18 | 101.28 | 67 | -34.28 | LAG | 2.Kesiapan lokasi ( customer) | 1350000000 | ORDINARY | 29/10/2018 19:28:40
PROJ1545 |  | UPGRADE DAN PSB VPN IP DAN 2 BACKHAUL, PSB ASTINET LITE DAN 2 BACKHAUL, DAN MANAGED AP BANK BTPN | CONNECTIVITY | BANK BTPN | BMS-2 |  |  | M ISNAINI SAPUTRO | BERTHA DESVIANI PURBA | PT Teltranet Aplikasi Solusi (Telkom Telstra) | 07-MAY-18 | 07-DEC-18 | 422.71 | 80.34 | -342.37 | LAG |  | 103745000000 | MEGA | 12/11/2018 14:44:09
PROJ2326 | LOP105965 | PENGADAAN JASA MASTER PLAN PT. KIMIA FARMA (PERSERO) | APPLICATION | KIMIA FARMA PT | HWS |  |  | HASBUR GHALI |  | PT Sigma Cipta Caraka | 10-JUL-18 | 08-OCT-18 | 100 | 100 | 0 | DELAY | 4.Keterlambatan BAST (customer) | 427500000 | REGULAR | 28/11/2018 11:12:34
PROJ2487 | LOP106420 | PAKET PEMBANGUNAN DATA CENTER PT. INKA (PERSERO) | CPE & OTHERS | INKA | IBS |  |  | RUDIONO |  | PT Sigma Cipta Caraka | 16-AUG-18 | 02-JAN-19 | 91.4 | 12.41 | -78.99 | LAG | 1.Delivery barang/jasa (mitra) | 3624500000 | ORDINARY | 27/11/2018 11:30:49
PROJ2542 | LOP106618 | PENGADAAN APLIKASI PENDUKUNG PROGRAM PROMO BERKAH ENERGI PERTAMINA | APPLICATION | PERTAMINA PT | ERS |  |  | HERU IRMAN |  | PT Finnet Indonesia, PT Sigma Metrasys Solution | 30-AUG-18 | 08-AUG-19 |  |  |  | LEAD |  | 22570000000 | BIG | 31/10/2018 15:28:02
PROJ2582 | LOP106719 | JASA MIGRASI PORT DARI LAYANAN VSAT KE MPLS UNTUK 134 LOKASI | CONNECTIVITY | BANK RAKYAT INDONESIA (PERSERO) | BMS-1 |  |  | NUR WIJAYANTO |  | PT Multimedia Nusantara | 31-AUG-18 | 31-DEC-18 |  |  |  | LEAD |  | 81620000 | REGULAR | 27/11/2018 14:53:28
PROJ2789 | LOP107494 | PERPANJANGAN JASA DEDICATED COLOCATION DATA CENTER UNTUK BANK SYARIAH MANDIRI | CPE & OTHERS | BANK SYARIAH MANDIRI | BMS-1 |  |  | FAHMI RAHMANTHAHA NURDINSYAH |  | PT Sigma Cipta Caraka | 01-FEB-18 | 31-JAN-19 |  |  |  | LEAD |  | 6500000000 | ORDINARY | 19/10/2018 18:29:45
PROJ30 |  | PROJECT PEKERJAAN SALURAN PENANGGAL BAWAH TANAH DI PROYEK BOULEVARD BUSINESS CENTER | SMART BUILDING | ADHI KARYA PT | PCS |  |  | IRWANDI | MUHAMMAD SIDIK | PT Telkom Akses | 19-NOV-14 | 31-JUL-17 | 100 | 41.25 | -58.75 | DELAY | 2.Kesiapan lokasi ( customer) | 472727273 | REGULAR | 30/11/2018 11:13:23
PROJ3062 | LOP108175 | PENGADAAN UPGRADE 230 SERVER DI DC GTI DAN TABANAN UNTUK PT. BANK RAKYAT INDONESIA (PERSERO), TBK | CPE & OTHERS | BANK RAKYAT INDONESIA (PERSERO) | BMS-1 |  |  | RUDIONO | RUDY SETYO NUGROHO | PT Signet Pratama | 12-OCT-18 | 11-JAN-19 | 74.86 | 3 | -71.86 | LAG |  | 64200235314 | MEGA | 27/11/2018 08:08:40
PROJ3107 | LOP108271 | PEKERJAAN SISTEM ELEKTRONIK PROYEK SEDAYU CITY APARTEMEN @ KELAPA GADING APARTEMENT JAKARTA | SMART BUILDING | AGUNG SEDAYU PROPERTINDO | IBS |  |  | HADI TRIYONO | FAHMI MUHAMMAD HUSIN | PT PINS Indonesia | 01-OCT-18 | 25-DEC-19 |  |  |  | LEAD |  | 18984900000 | ORDINARY | 06/11/2018 13:49:02
PROJ35 |  | PROJECT PAKET PEKERJAAN ELEKTRONIK UNTUK TUNJUNGAN PLAZA 6 | SMART BUILDING | PAKUWON JATI | PCS |  |  | AD STEFEN RATU EDA | YAFRINO, ST, M.M | PT PINS Indonesia, PT PINS Indonesia | 12-JAN-16 | 31-OCT-18 | 100 | 55.883 | -44.1195 | DELAY | 1.Delivery barang/jasa (mitra) | 16640000000 | ORDINARY | 26/11/2018 12:30:59
PROJ7 |  | PROJECT FTTH DUKUH GOLF KEMAYORAN BOUGENVILLE | SMART BUILDING | AGUNG SEDAYU PROPERTINDO | IBS |  |  | PRAKOSA TRIWIBOWO | FAHMI MUHAMMAD HUSIN | PT PINS Indonesia, PT PINS Indonesia | 18-SEP-14 | 30-SEP-16 | 99.986 | 99.997 | 0.011 | DELAY | 4.Keterlambatan BAST (customer) | 19043050000 | ORDINARY | 10/01/2018 10:54:08
PROJ750 |  | ROLL OUT 3 PTPN XIV MAKASAR | APPLICATION | ABC PRESIDENT INDONESIA, PT | MAS |  |  | NURUL HIDAYATI | NADIAH LIESTYASARI | PT Sigma Metrasys Solution | 01-OCT-17 | 30-NOV-18 | 96 | 67 | -29 | DELAY | 2.Kesiapan lokasi ( customer) | 9172440000 | ORDINARY | 28/11/2018 19:38:11
PROJ753 |  | PEKERJAAN INFRASTRUKTUR GPON GALAXY MALL 3 SURABAYA | SMART BUILDING | SINAR GALAXI | TDS |  |  | ATAM RUSTAM | SUCI ERNANINGTYAS | PT PINS Indonesia, PT PINS Indonesia | 17-NOV-17 | 30-NOV-18 | 100 | 89.55 | -10.45 | DELAY | 1.Delivery barang/jasa (mitra) | 2300000000 | ORDINARY | 14/11/2018 17:14:12
PROJ771 |  | PROJECT E-DAPEM TASPEN | APPLICATION | TASPEN PT | HWS |  |  | ZAKY AHMAD | ELMAN HASIHOLAN SIANTURI, IR.MT. | PT Sigma Cipta Caraka | 17-OCT-17 | 16-DEC-18 | 98.29 | 98.24 | -0.05 | LAG | 3.Perubahan desain/spek pelanggan (customer) | 585728682000 | MEGA | 28/11/2018 17:32:45
PROJ775 |  | PENGADAAN TEKNOLOGI BIG DATA UNTUK BRI | APPLICATION | BANK RAKYAT INDONESIA (PERSERO) | BMS-1 |  |  | ADRID | RUDY WIBOWO | PT Metra-Net | 09-NOV-17 | 30-NOV-18 | 99.019 | 99.008 | -0.011 | DELAY | 3.Perubahan desain/spek pelanggan (customer) | 25704545454 | BIG | 28/11/2018 09:15:59
PROJ779 |  | PROJECT CORE INSURANCE SYSTEM ASKRINDO | APPLICATION | ASURANSI KREDIT INDONESIA | HWS |  |  | ZAKY AHMAD | JOKO PADANG RAHINO | PT Sigma Cipta Caraka, PT Sigma Cipta Caraka | 14-NOV-17 | 15-JAN-19 | 82.66 | 57.59 | -25.07 | LAG | 8.CR (perubahan yang belum terkendali) & amandemen (customer) | 10792188000 | ORDINARY | 29/11/2018 11:15:44
PROJ82 |  | PROJECT ELECTRONIC & FTTH COUNTRY CLUB NAVAPARK | SMART BUILDING | SINAR MAS WISESA | PCS |  |  | TEDDY AWALUDIN |  | PT PINS Indonesia, PT PINS Indonesia | 01-FEB-16 | 30-NOV-18 | 100 | 100 | 0 | DELAY | 8.CR (perubahan yang belum terkendali) & amandemen (customer) | 2430000000 | ORDINARY | 23/11/2018 10:47:33
PROJ977 |  | PEKERJAAN MEKANIKAL, ELEKTRIKAL & PLUMBING PROYEK TEKNOPLEX LIVING APARTMENT | SMART BUILDING | PT.MULTI KARYA UTAMA ABADI -BANDUNG TECHNOPLEX LIVING | PCS |  |  | TEUKU HAMIZUL | RADIAN SIGIT DWIANANTO | PT Infrastruktur Telekomunikasi Indonesia (TELKOMINFRA) | 31-OCT-17 | 31-MAY-19 | 94.55 | 32.308 | -62.242 | LAG | 2.Kesiapan lokasi ( customer) | 55000000000 | MEGA | 12/11/2018 19:15:07
PROJ386 |  | PROJECT WIFI.ID PIZZA HUT | CONNECTIVITY | MAP FOOD & BEVERAGE | THS |  |  | SRI NURFALAH | EVY YULIA RAMADHAN |  | 01-JAN-17 | 31-DEC-18 | 82 | 50 | -32 | LAG |  | 186000000 | REGULAR | 09/11/2018 16:59:35
PROJ453 |  | WIFI.ID VIP PARKING BATCH 2 | CONNECTIVITY | VIP PARKING INDONESIA | THS |  |  | SRI NURFALAH | KASRIYADI NUR |  | 01-JAN-17 | 31-DEC-18 | 78.83 | 100 | 21.17 | LAG |  | 26000000 | REGULAR | 30/10/2018 10:54:49
PROJ209 |  | WIFI.ID BTDC NUSA DUA TAHAP 2 | CONNECTIVITY | BTDC NUSA DUA | THS |  |  | SRI NURFALAH | I MADE BUDIANA, SE, MM |  | 01-JAN-17 | 31-DEC-18 | 99.996 | 95 | -4.996 | LAG |  | 20000000 | REGULAR | 09/08/2018 16:55:15
PROJ379 |  | PROJECT WIFI.ID KFC | CONNECTIVITY | FASTFOOD INDONESIA | THS |  |  | SRI NURFALAH | ANAK AGUNG ARDHA CHANDRA DEWI |  | 01-JAN-17 | 31-DEC-18 | 82 | 20 | -62 | LAG |  | 237000000 | REGULAR | 09/11/2018 17:03:09
PROJ3522 |  | ASTINET LITE 93 LOKASI UNTUK PT. INDOMOBIL FINANCE INDONESIA | CONNECTIVITY | INDOMOBIL GROUP | IBS |  |  | ARI WIDIYANTO | ANDI SYAHRUDDIN |  | 04-OCT-18 | 31-DEC-18 |  |  |  | LEAD |  | 2136901944 | ORDINARY | 27/11/2018 18:30:39
PROJ903 |  | PROJECT 5000 AKSES POINT WIFI PEGADAIAN | CONNECTIVITY | PEGADAIAN PT | FMS |  |  | DWI WIDYA SAKTI | ANDIKA PRATAMA PUTRA |  | 22-FEB-18 | 31-DEC-18 | 80.8 | 25 | -55.8 | LAG |  | 18000000000 | ORDINARY | 13/09/2018 17:21:24
PROJ377 |  | PROJECT WIFI.ID DUNKIN DONUT | CONNECTIVITY | DUNKIN DONUT | THS |  |  | SRI NURFALAH | Noviyan Setiadi |  | 01-JAN-17 | 31-DEC-18 | 82 | 25 | -57 | LAG |  | 5500000 | REGULAR | 09/11/2018 17:03:20
PROJ114 |  | PROJECT IMPLEMENTASI MICROSOFT DYNAMIC AX ERP PT. PPI | APPLICATION | PERUSAHAAN PERDAGANGAN INDONESIA (PERSERO) | TDS |  |  | NURUL HIDAYATI | CAHAYA RUMENTA | PT Signet Pratama | 21-DEC-15 | 31-AUG-18 | 100 | 80 | -20 | DELAY | 8.CR (perubahan yang belum terkendali) & amandemen (customer) | 21600000000 | BIG | 13/11/2018 20:02:08
PROJ1169 | LOP101909 | PENGADAAN JASA PENGEMBANG APLIKASI E-PAS & INFRASTRUKTUR PENDUKUNGNYA PT PUPUK SRIWIDJAJA PALEMBANG | APPLICATION | PUPUK SRIWIJAYA | MAS |  |  | RIKA AMALIA SASANTY | MUHAMMAD HANIS | PT Infomedia Nusantara | 23-MAR-18 | 28-DEC-18 | 92 | 64.22 | -27.78 | LAG | 3.Perubahan desain/spek pelanggan (customer) | 523800000 | REGULAR | 30/11/2018 10:39:10
PROJ141 |  | PROJECT SEAT MANAGEMENT PT. PELABUHAN INDONESIA (PELINDO) III | CPE & OTHERS | PELINDO III | MLS |  |  | TEDDY AWALUDIN | RIFANDA PUTRI INDRESWARI | PT PINS Indonesia | 01-JAN-17 | 31-DEC-19 | 76.584 | 78.2 | 1.616 | LAG | 3.Perubahan desain/spek pelanggan (customer) | 13868640000 | ORDINARY | 23/11/2018 10:45:37
PROJ1680 |  | ICT LIVING WORLD PEKANBARU (PT TIGA DUA DELAPAN - CC KAWAN LAMA GROUP) | SMART BUILDING | KAWAN LAMA SEJAHTERA | TDS |  |  | ATAM RUSTAM | YULISTIKA RAHAYU | PT Telkom Akses, PT Telkom Akses | 23-MAR-18 | 30-NOV-18 | 99.65 | 100 | 0.35 | DELAY |  | 1110000000 | ORDINARY | 14/11/2018 17:19:59
PROJ2706 |  | INSTALASI INFRASTRUKTUR JARINGAN DATA REDUNDANT FASILITAS DATA CENTER DAN DISASTER RECOVERY CENTER PT BIO FARMA | CPE & OTHERS | BIO FARMA PERSERO | HWS |  |  | SOPIYAN SOPIYANA | EKO ARDIANSYAH PUTRA | PT PINS Indonesia | 15-AUG-18 | 15-FEB-19 | 83.179 | 44.852 | -38.3264 | LAG |  | 3609451200 | ORDINARY | 19/11/2018 17:09:19
PROJ2833 | LOP107284 | PENGADAAN MANAGED SERVICES ACCSESS CONTROL, CCTV DAN IPPABX PT. JALIN PEMBAYARAN NUSANTARA - PT. TELEKOMUNIKASI INDONESIA, TBK | CPE & OTHERS | PT JALIN PEMBAYARAN NUSANTARA | BMS-1 |  |  | DODI IRAWAN |  | PT PINS Indonesia | 08-OCT-18 | 06-SEP-21 | 81.78 | 40.66 | -41.12 | LAG | 2.Kesiapan lokasi ( customer) | 3150000000 | ORDINARY | 21/11/2018 16:12:21
PROJ409 | LOP25082 | LISENSI DAN IMPLEMENTASI ERP ORACLE CLOUD KALLA GROUP | APPLICATION | HAKA SARANA INVESTAMA | IBS |  |  | DODI IRAWAN | BINDA ANISSA | SIGMA SOLUSI INTEGRASI | 08-MAY-17 | 15-DEC-18 | 100 | 93.7 | -6.3 | LAG | 1.Delivery barang/jasa (mitra) | 33710373799 | BIG | 26/11/2018 15:34:40
PROJ429 |  | PEKERJAAN ELEKTRONIKA DAN GPON PROYEK GALLERIA VIVO MALL SENTUL | SMART BUILDING | ADHIBALADIKA AGUNG | PCS |  |  | AD STEFEN RATU EDA | HELVIANA | PT PINS Indonesia, PT PINS Indonesia | 24-MAY-17 | 31-AUG-18 | 93.2 | 81.822 | -11.3771 | DELAY | 1.Delivery barang/jasa (mitra) | 12500000000 | ORDINARY | 26/11/2018 12:16:51
PROJ442 |  | PROJECT PROPRIETARY LOYALTY PROGRAM PT PERTAMINA PERSERO | APPLICATION | PERTAMINA PT | ERS |  |  | HERU IRMAN |  | PT Finnet Indonesia | 11-JUL-17 | 11-JUL-22 | 56.68 | 47 | -9.68 | LAG | 8.CR (perubahan yang belum terkendali) & amandemen (customer) | 61862540000 | MEGA | 31/10/2018 15:48:06
PROJ574 |  | PROJECT BPO INSTALASI SISTEM GAS PROCESSING PLANT | CPE & OTHERS | PT GREEN ENERGY NATURAL GAS | ERS |  |  | RISTYAWAN FAUZI MUBAROK | TITIS WENING | PT Infomedia Nusantara | 01-SEP-17 | 29-MAR-19 | 70.8 | 72.78 | 1.98 | LAG | 3.Perubahan desain/spek pelanggan (customer) | 80663661600 | MEGA | 19/10/2018 14:40:00
PROJ659 |  | IMPLEMENTASI SISTEM ERP PT. HUTAMA KARYA (PERSERO) | APPLICATION | HUTAMA KARYA PT | PCS |  |  | RIKA AMALIA SASANTY | NURUL RIZKI UTAMI | PT Sigma Metrasys Solution | 25-OCT-17 | 25-MAY-19 | 91.67 | 98.48 | 6.81 | LAG | 4.Keterlambatan BAST (customer) | 14120376710 | ORDINARY | 13/11/2018 12:16:48
PROJ746 |  | ROLL OUT 2 PTPN 2 MEDAN | APPLICATION | PERKEBUNAN NUSANTARA II PT | MAS |  |  | NURUL HIDAYATI | SIMON | PT Sigma Metrasys Solution | 01-OCT-17 | 31-DEC-18 | 96 | 62 | -34 | LAG | 8.CR (perubahan yang belum terkendali) & amandemen (customer) | 31982850000 | BIG | 29/10/2018 18:59:02
PROJ790 |  | PEKERJAAN SEWA OUTSOURCING EDC DAN PERANGKAT PENDUKUNG OPERASIONAL BANK SUMSEL BABEL | CPE & OTHERS | BPD SUMATERA SELATAN (BANK SUMSEL) | BMS-2 |  |  | HASBUR GHALI | EVI NOVIARNI | PT PINS Indonesia | 30-OCT-17 | 30-OCT-20 | 100 | 93.52 | -6.487 | LAG | 8.CR (perubahan yang belum terkendali) & amandemen (customer) | 3518405000 | ORDINARY | 01/10/2018 17:18:46
PROJ89 |  | ICT FTTH GPON ANANDAMAYA RESIDENCE | SMART BUILDING | ADHI KARYA PT | PCS |  |  | ATAM RUSTAM | SHERA MAYANGSARI SUWITO | PT PINS Indonesia, PT PINS Indonesia | 28-JUL-16 | 17-NOV-18 | 100.06 | 94.15 | -5.911 | DELAY | 1.Delivery barang/jasa (mitra) | 2285000000 | ORDINARY | 07/11/2018 10:57:21
PROJ928 | LOP25066 | PENGADAAN SEWA 12.000 UNIT EDC BNI UNTUK PT. BRINGIN GIGANTARA | CPE & OTHERS | BANK RAKYAT INDONESIA (PERSERO) | BMS-1 |  |  | RUDIONO | RUDY WIBOWO | PT Sigma Cipta Caraka | 15-JAN-18 | 31-DEC-19 | 87.5 | 34.13 | -53.37 | LAG | 2.Kesiapan lokasi ( customer) | 57000000000 | MEGA | 16/11/2018 14:34:08
PROJ376 |  | PROJECT WIFI.ID DOMINO PIZZA | CONNECTIVITY | MAP FOOD & BEVERAGE | THS |  |  | SRI NURFALAH | EVY YULIA RAMADHAN |  | 01-JAN-17 | 31-DEC-18 | 82 | 10 | -72 | LAG |  | 21000000 | REGULAR | 09/11/2018 17:03:39
PROJ213 | LOP6312 | WIFI.ID BALAI PUSTAKA | CONNECTIVITY | BALAI PUSTAKA PT | EMS |  |  | SRI NURFALAH | GUSTI AYU MADE MAS MARHAENI |  | 01-JAN-17 | 31-DEC-18 | 100 | 80 | -20.009 | LAG |  | 216000000 | REGULAR | 09/11/2018 17:05:00
PROJ1361 | LOP102771 | PENYEDIAAN MINING VEHICLE DENGAN TRACKING SYSTEM UNTUK KEBUTUHAN STOCK PILE DI AREA TAMBANG KINTAP PT ARUTMIN INDONESIA | CPE & OTHERS | BUMI RESOURCES TBK | ERS |  |  | ARIEF SUSILO WIBOWO | TITIS WENING | PT Sigma Cipta Caraka | 01-MAR-18 | 31-DEC-18 | 99.8 | 76.16 | -23.64 | LAG | 3.Perubahan desain/spek pelanggan (customer) | 32934893200 | BIG | 11/10/2018 11:50:39
PROJ2293 |  | PENGADAAN PENYEDIAAN JASA LAYANAN PAKET E-TICKETING PERUM DAMRI | APPLICATION | DAMRI PO | TMS |  |  | ARIEF SUSILO WIBOWO | ERSYHAD PRABAWA ADIGUNA | PT NUTECH INTEGRASI | 05-JUN-18 | 30-NOV-18 | 100 | 48.5 | -51.5 | DELAY | 2.Kesiapan lokasi ( customer) | 22461600000 | BIG | 14/11/2018 12:33:07
PROJ2319 | LOPUP268 | PEKERJAAN PENGADAAN JASA SEWA MESIN ATM PT. BANK JATIM | CPE & OTHERS | BANK JATIM | FMS |  |  | IRWANDI |  | PT Sigma Cipta Caraka | 27-JUL-18 | 28-SEP-18 | 93.85 | 87.7 | -6.15 | DELAY | 4.Keterlambatan BAST (customer) | 7797600000 | ORDINARY | 30/11/2018 09:59:37
PROJ2392 | LOP104964 | PENGADAAN PEMBANGUNAN DATA CENTER KERETA COMMUTER INDONESIA | CPE & OTHERS | KERETA COMMUTER INDONESIA | TMS |  |  | ARIEF SUSILO WIBOWO |  | PT Sigma Cipta Caraka | 13-AUG-18 | 31-OCT-18 | 100 | 31.9 | -68.1 | DELAY | 1.Delivery barang/jasa (mitra) | 1749000000 | ORDINARY | 28/11/2018 14:08:22
PROJ2396 |  | PROJECT EASTERN GREEN BEKASI | SMART BUILDING | ADHI KARYA PT | PCS |  |  | PRAKOSA TRIWIBOWO | DWI PUDJI IRAWATI | PT PINS Indonesia | 30-NOV-17 | 30-NOV-19 | 97.599 | 45.92 | -51.679 | LAG | 2.Kesiapan lokasi ( customer) | 6850000000 | ORDINARY | 23/11/2018 14:53:02
PROJ2628 | LOP106868 | ASTINET LITE OTO MULTIARTHA 19 LOKASI | CONNECTIVITY | PT OTO MULTIARTHA | FMS |  |  | HARI MULYA |  | PT Datalink Solution, PT Datalink Solution | 30-AUG-18 | 31-OCT-18 | 97.5 | 95 | -2.5 | DELAY | 1.Delivery barang/jasa (mitra) | 981450400 | REGULAR | 05/11/2018 23:02:00
PROJ2889 | LOP107834 | PENGADAAN PEKERJAAN PERAWATAN E-TICKETING BULAN AGUSTUS S/D DESEMBER 2018 | CPE & OTHERS | KERETA COMMUTER INDONESIA | TMS |  |  | ARIEF SUSILO WIBOWO |  | PT NUTECH INTEGRASI, PT Sigma Cipta Caraka | 01-AUG-18 | 31-DEC-18 |  |  |  | LEAD |  | 14345270135 | ORDINARY | 01/11/2018 13:59:31
PROJ31 |  | PROJECT INTERNATIONAL FINANCIAL CENTER 2 | SMART BUILDING | INTERNATIONAL FINANCIAL CENTER | PCS |  |  | HERI IKHWAN DIANA | DWI PUDJI IRAWATI | PT PRAMINDO IKAT NUSANTARA (PINS) | 18-AUG-15 | 30-SEP-17 | 100 | 95.67 | -4.33 | DELAY | 5.Keterlambatan SPK ke mitra (di awal) (Telkom) | 2484600427 | ORDINARY | 19/10/2018 16:18:35
PROJ3146 | LOP108542 | LAN & IPPBX FIELD SUBANG COLL PERTAMINA EP ASSET 3 SUBANG FIELD | CPE & OTHERS | PERTAMINA PT | ERS |  |  | HADI TRIYONO | REIKA ERMANSA | PT Nusantara Compnet Integrator | 22-OCT-18 | 21-DEC-18 |  |  |  | LEAD |  | 7735000000 | ORDINARY | 26/10/2018 15:16:16
PROJ32 |  | PROJECT PANIC BUTTON ORCHARD PARK BATAM | SMART BUILDING | PODOMORO GROUP | PCS |  |  | IRWANDI | NOVI ANDRIYANI | PT PINS Indonesia, PT PINS Indonesia | 30-AUG-15 | 30-APR-18 | 100 | 118.71 | 18.71 | DELAY | 2.Kesiapan lokasi ( customer) | 2109703600 | ORDINARY | 30/11/2018 11:12:24
PROJ3348 | LOP21683 | JASA SYSTEM MANAGEMENT MONITORING PRODUCTION PERUM PERURI | APPLICATION | PERURI PERUM | FMS |  |  | DODI IRAWAN | MULYADI, ST | PT PINS Indonesia, PT PINS Indonesia | 12-NOV-18 | 11-FEB-19 |  |  |  | LEAD |  | 680454545 | REGULAR | 27/11/2018 13:59:30
PROJ458 |  | PROJECT ELEKTRONIK APARTEMEN DI BORNEO BAY BALIKPAPAN | SMART BUILDING | PODOMORO GROUP | PCS |  |  | PRAKOSA TRIWIBOWO | NOVI ANDRIYANI | PT PINS Indonesia, PT PINS Indonesia | 01-JUL-17 | 22-OCT-18 | 98.788 | 57.09 | -41.698 | DELAY | 2.Kesiapan lokasi ( customer) | 14181818000 | ORDINARY | 23/11/2018 15:08:29
PROJ801 |  | PROJECT DIGITALISASI KIMIA FARMA | CPE & OTHERS | KIMIA FARMA PT | HWS |  |  | ADRID | MELANY ULFA | PT Sigma Cipta Caraka | 27-DEC-17 | 31-DEC-18 | 100 | 80.6 | -19.4 | LAG | 10.Keterbatasan kapabilitas mitra (mitra) | 787000000000 | MEGA | 26/11/2018 10:02:02
PROJ808 |  | ERP SAP PT SEMEN BATURAJA | APPLICATION | SEMEN BATURAJA PT | MAS |  |  | KRSHNA SULANJANA | MUHAMMAD HANIS | PT Sigma Metrasys Solution | 29-DEC-17 | 04-JAN-19 | 98.8 | 91.52 | -7.28 | LAG | 8.CR (perubahan yang belum terkendali) & amandemen (customer) | 34771819125 | BIG | 26/11/2018 08:53:54
PROJ95 |  | PROJECT ERP N-HOLDING LOKASI : PTPN V (PEKANBARU) | APPLICATION | PERKEBUNAN NUSANTARA V PT | MAS |  |  | NURUL HIDAYATI | SITI WIMA ADITYA MAHADINI | PT Sigma Metrasys Solution | 17-AUG-16 | 31-DEC-18 | 100 | 93.5 | -6.5 | LAG | 8.CR (perubahan yang belum terkendali) & amandemen (customer) | 35603550000 | BIG | 29/10/2018 19:32:40
PROJ212 |  | WIFI.ID KIMIA FARMA (TAHAP 2) | CONNECTIVITY | KIMIA FARMA PT | HWS |  |  | SRI NURFALAH | MELANY ULFA |  | 01-JAN-17 | 31-DEC-18 | 99.997 | 92 | -7.997 | LAG |  | 318000000 | REGULAR | 09/11/2018 17:05:32
PROJ44 |  | PROJECT LAYANAN VPN IP UNTUK KFC | CONNECTIVITY | FASTFOOD INDONESIA | THS |  |  | I DEWA MADE AGUS | ANAK AGUNG ARDHA CHANDRA DEWI |  | 01-JAN-16 | 31-DEC-18 | 100 | 86.7 | -13.3 | LAG | 2.Kesiapan lokasi ( customer) | 1032000000 | ORDINARY | 08/10/2018 10:05:31
PROJ8 |  | PROJECT WIFI ID SAMSUNG EXPERIENCE STORE 106 LOKASI | CONNECTIVITY | SAMSUNG ELECTRONIC INDONESIA | IBS |  |  | SRI NURFALAH | ANDI SYAHRUDDIN |  | 01-APR-14 | 31-DEC-18 |  |  |  | LAG |  | 111600000 | REGULAR | 29/10/2018 16:37:04
PROJ384 |  | PROJECT WIFI.ID HOTEL HILTON | CONNECTIVITY | FOUR SEASON HOTEL AND RESORT | THS |  |  | SRI NURFALAH | RINO SUPRIADI PUTRA |  | 01-JAN-17 | 31-DEC-18 | 82 | 20 | -62 | LAG |  | 756000000 | REGULAR | 09/11/2018 17:02:53
PROJ455 |  | WIFI.ID SWISS BELL HOTEL MANADO | CONNECTIVITY | SWISS BELL HOTEL MANADO | THS |  |  | SRI NURFALAH | JOKO SULISTIYO |  | 28-JUL-17 | 31-DEC-18 | 95.3 | 100 | 4.7 | LAG |  | 90000000 | REGULAR | 05/11/2018 10:20:49
PROJ385 |  | PROJECT WIFI.ID STARBUCK | CONNECTIVITY | MAP FOOD & BEVERAGE | THS |  |  | SRI NURFALAH | EVY YULIA RAMADHAN |  | 01-JAN-17 | 31-DEC-18 | 82 | 30 | -52 | LAG |  | 480000000 | REGULAR | 09/11/2018 17:00:42
PROJ11 |  | PROJECT PARK LAND AVENUE | SMART BUILDING | SUMMARECON AGUNG TBK | IBS |  |  | PRAKOSA TRIWIBOWO | ACHMAD SUTARJONO | PT PINS Indonesia | 01-NOV-15 | 30-DEC-18 | 99.07 | 75.58 | -23.49 | LAG | 11.Komitmen mitra(termasuk deal harga)(mitra) | 3550000000 | ORDINARY | 23/11/2018 15:13:48
PROJ1491 |  | REVITALISASI DAN PENGEMBANGAN DATA CENTER UNIVERSITAS SYIAH KUALA | CPE & OTHERS | UNIVERSITAS SYAHKUALA (UNSYIAH) | EMS |  |  | MASTAMAN ARABY | AGUS FRIADI | PT Infrastruktur Telekomunikasi Indonesia (TELKOMINFRA) | 06-APR-18 | 27-NOV-18 | 100 | 37.644 | -62.356 | DELAY | 10.Keterbatasan kapabilitas mitra (mitra) | 4704000000 | ORDINARY | 10/09/2018 12:10:26
PROJ183 |  | PENGADAAN LICENSE DAN IMPLEMENTASI ORACLE FUSION ERP CLOUD SOLUTION PT. BUKAKA | APPLICATION | POSO ENERGY | IBS |  |  | DODI IRAWAN | BUDIMAN | SIGMA SOLUSI INTEGRASI, SIGMA SOLUSI INTEGRASI | 28-DEC-16 | 10-JAN-18 | 100 | 99.5 | -0.501 | DELAY | 10.Keterbatasan kapabilitas mitra (mitra) | 7870860487 | ORDINARY | 21/11/2018 16:41:28
PROJ1877 | LOP104326 | PROJECT PEKERJAAN DIGITAL CORE PLATFORM DI PERUM PERURI | CPE & OTHERS | PERURI PERUM | FMS |  |  | IRWANDI | WIJAYANTO | PT Sigma Metrasys Solution | 05-JUL-18 | 30-JAN-19 | 55.76 | 36.35 | -19.41 | LAG | 1.Delivery barang/jasa (mitra) | 89318181818 | MEGA | 30/11/2018 10:09:56
PROJ2141 | LOP105334 | PENYEDIAAN ICT, PABX, DATA, CCTV, SOUND SYSTEM, FIRE ALARM & IPTV PROYEK RSKIA KOTA BANDUNG | SMART BUILDING | ADHI KARYA PT | PCS |  |  | PRAKOSA TRIWIBOWO |  | PT PINS Indonesia | 04-JUN-18 | 28-DEC-18 | 48.36 | 29.7 | -18.66 | LAG | 1.Delivery barang/jasa (mitra) | 7650000000 | ORDINARY | 23/11/2018 15:01:44
PROJ217 |  | PROJECT MEKANIKAL & ELEKTRIKAL PEKERJAAN CINERE TERRACE SUITES - APARTMENT & CITYWALK | SMART BUILDING | METROPOLITAN TOWER | PCS |  |  | TEDDY AWALUDIN | SUNARTO AMSALOM SAIRO | PT PINS Indonesia, PT PINS Indonesia | 17-FEB-17 | 31-AUG-18 | 100 | 95.61 | -4.39 | DELAY | 8.CR (perubahan yang belum terkendali) & amandemen (customer) | 18568190000 | ORDINARY | 23/11/2018 10:43:33
PROJ2214 | LOP105689 | APLIKASI E-OFFICE UNTUK SURVEYOR INDONESIA | APPLICATION | SURVEYOR INDONESIA | IBS |  |  | RIKA AMALIA SASANTY |  | PT Sigma Cipta Caraka, PT Sigma Cipta Caraka, PT Sigma Cipta Caraka | 09-JUL-18 | 08-OCT-18 | 98 | 100 | 2 | DELAY | 2.Kesiapan lokasi ( customer) | 282000000 | REGULAR | 30/11/2018 10:41:03
PROJ2256 | LOP105769 | JASA IMPLEMENTASI SAP PT KIMIA FARMA SUNGWUN PHARMACOPIA | APPLICATION | KIMIA FARMA PT | HWS |  |  | HASBUR GHALI |  | PT Sigma Metrasys Solution | 10-JUL-18 | 05-DEC-18 | 100 | 97.5 | -2.5 | LAG | 3.Perubahan desain/spek pelanggan (customer) | 2475600000 | ORDINARY | 16/11/2018 16:20:31
PROJ2596 | LOP106759 | JASA MIGRASI PORT DARI LAYANAN VSAT KE MPLS DI 20 REMOTE EX PROVIDER TENGARA | CONNECTIVITY | BANK RAKYAT INDONESIA (PERSERO) | BMS-1 |  |  | NUR WIJAYANTO |  | PT Multimedia Nusantara, PT Multimedia Nusantara | 03-SEP-18 | 31-DEC-18 |  |  |  | LEAD |  | 12210000 | REGULAR | 27/11/2018 14:46:52
PROJ36 |  | PROJECT SMART BUILDING HOTEL KEMPINSKI | SMART BUILDING | GRAHA ALAM LESTARI | PCS |  |  | AD STEFEN RATU EDA | GERRY ROY MANAEK SIAHAAN | PT PINS Indonesia, PT PINS Indonesia | 11-FEB-16 | 31-OCT-18 | 98.309 | 76.79 | -21.519 | DELAY | 11.Komitmen mitra(termasuk deal harga)(mitra) | 23000000000 | BIG | 26/11/2018 12:25:43
PROJ405 |  | PROJECT PENGADAAN DAN PEMASANGAN GATE BARRIER SELURUH GERBANG CLUSTER PROYEK ORCHARD PARK BATAM | SMART BUILDING | PODOMORO GROUP | PCS |  |  | IRWANDI | NOVI ANDRIYANI | PT PINS Indonesia, PT PINS Indonesia | 01-APR-17 | 01-APR-18 | 100 | 88.58 | -11.42 | DELAY | 2.Kesiapan lokasi ( customer) | 1000000000 | ORDINARY | 30/11/2018 11:06:21
PROJ414 |  | PROJECT PENGADAAN LIFT UNTUK BANK SUMUT | CPE & OTHERS | BANK SUMATERA UTARA | BMS-2 |  |  | IRWANDI | ERWIN ULONG NAINGGOLAN | PT PINS Indonesia | 15-MAY-17 | 31-MAR-18 | 100 | 100 | 0 | DELAY | 10.Keterbatasan kapabilitas mitra (mitra) | 3616900000 | ORDINARY | 30/11/2018 11:04:18
PROJ60 | LOP105856 | PEKERJAAN SISTEM ELEKTRONIK 2 ( TELEPHONE, DATA, CCV, MATV, ACCESS CARD DAN VIDEO PHONE ) PROYEK MENTENG PARK APARTEMENT - JAKARTA | SMART BUILDING | AGUNG SEDAYU PROPERTINDO | IBS |  |  | AD STEFEN RATU EDA | FURI DIAH AYU HAPSARI | PT PINS Indonesia, PT PINS Indonesia | 02-MAY-16 | 31-DEC-18 | 99.81 | 85.66 | -14.15 | LEAD | 1.Delivery barang/jasa (mitra) | 19100000000 | ORDINARY | 26/11/2018 12:24:52
PROJ621 |  | PEKERJAAN PENATAAN KAWASAN GBK ZONA 1 | SMART BUILDING | ADHI KARYA PT | PCS |  |  | ADRID | DWI PUDJI IRAWATI | PT PINS Indonesia | 01-SEP-17 | 30-DEC-17 | 100 | 100 | 0 | DELAY | 4.Keterlambatan BAST (customer) | 19500000000 | ORDINARY | 25/11/2018 09:17:57
PROJ823 |  | PEKERJAAN PENGADAAN 25 UNIT MESIN ATM PT BANK NTB | CPE & OTHERS | BANK PEMBANGUNAN DAERAH NTB | FMS |  |  | IRWANDI | FERDINAND YOHANNIS MARKUS | PT Sigma Cipta Caraka, PT Sigma Cipta Caraka | 11-JAN-18 | 31-MAY-18 | 100 | 100 | 0 | DELAY | 2.Kesiapan lokasi ( customer) | 3243722500 | ORDINARY | 30/11/2018 10:16:54
PROJ835 |  | PEKERJAAN JASA IMPLEMENTASI ENTERPRISE RESOURCES PLANNING (ERP) MODUL KEUANGAN DI PERUM LPPNPI | APPLICATION | LEMBAGA PENYELENGGARA PELAYANAN NAVIGASI PENERBANGAN INDONESIA PERUM | TMS |  |  | RIKA AMALIA SASANTY | MOHAMMAD TAUFAN | PT Infomedia Nusantara | 20-DEC-17 | 29-AUG-18 | 100 | 98.5 | -1.5 | DELAY | 3.Perubahan desain/spek pelanggan (customer) | 439728300 | REGULAR | 30/11/2018 10:42:57
PROJ71 |  | PROJECT WIFI.ID TRANS COFFEE (COFFEE BEAN) | CONNECTIVITY | TRANS COFFEE | THS |  |  | SRI NURFALAH | RINO SUPRIADI PUTRA |  | 01-JUN-16 | 31-DEC-18 | 100 | 58 | -42.001 | LAG | 2.Kesiapan lokasi ( customer) | 666000000 | REGULAR | 09/01/2018 18:42:56
PROJ3212 |  | LAYANAN REFRESHMENT INFRASTRUKTUR LAN PT PUPUK ISKANDAR MUDA (PIM) | CPE & OTHERS | PUPUK ISKANDAR MUDA | MAS |  |  | RANDY NOARY | MULKI ZUCHRI |  | 13-OCT-18 | 10-FEB-19 |  |  |  | LEAD |  | 4791949310 | ORDINARY | 01/11/2018 13:56:56
PROJ1117 |  | PROJECT ELEKTRIKAL DAN ELEKTRONIK GEDUNG BIO FARMA 2 BANDUNG | SMART BUILDING | PEMBANGUNAN PERUMAHAN PT | PCS |  |  | HADI TRIYONO | SHEINI CHRISTY | PT Infrastruktur Telekomunikasi Indonesia (TELKOMINFRA) | 26-FEB-18 | 27-MAY-19 | 56.43 | 11.45 | -44.98 | LAG | 1.Delivery barang/jasa (mitra) | 20800000000 | BIG | 16/11/2018 19:50:35
PROJ1517 | LOP102419 | PENGADAAN ENHANCEMENT PORTAL BTN PROPERTI PHASE 2 | CPE & OTHERS | BANK TABUNGAN NEGARA (PERSERO) | BMS-1 |  |  | SHEPTIAN KURNIA SALEH | DISKAERI | PT Sigma Cipta Caraka | 28-MAR-18 | 23-JAN-19 | 100 | 87.6 | -12.4 | LAG | 1.Delivery barang/jasa (mitra) | 4086363636 | ORDINARY | 28/11/2018 18:16:44
PROJ171 |  | AIRPORT OPERATION CONTROL CENTER BANDARA SOEKARNO HATTA | APPLICATION | ANGKASA PURA II (PERSERO) - BUISH | TMS |  |  | ATAM RUSTAM | HIDAYAT KURNIAWAN | PT PINS Indonesia | 01-JAN-17 | 23-NOV-18 | 100.02 | 97.373 | -2.6491 | DELAY | 8.CR (perubahan yang belum terkendali) & amandemen (customer) | 93655243000 | MEGA | 26/11/2018 09:52:01
PROJ182 |  | PROJECT IN BUILDING SOLUTION (IBS) KEMPINSKI HOTEL BALI | SMART BUILDING | GRAHA ALAM LESTARI | PCS |  |  | AD STEFEN RATU EDA | GERRY ROY MANAEK SIAHAAN | PT Dayamitra Telekomunikasi, PT Dayamitra Telekomunikasi | 16-DEC-16 | 30-NOV-18 | 99.39 | 87.06 | -12.33 | DELAY | 2.Kesiapan lokasi ( customer) | 7100000000 | ORDINARY | 26/11/2018 12:23:02
PROJ2161 | LOP105406 | PROYEK PENGADAAN MATERIAL MEKANIKAL, ELEKTRIKAL, ELEKTRONIK PROYEK PADINA APARTEMENT | SMART BUILDING | PT PATRA BANGUN PROPERTI | PCS |  |  | HERU IRMAN |  | PT Sandhy PutraMakmur | 23-JUL-18 | 31-DEC-18 | 61.439 | 54.08 | -7.359 | LAG | 1.Delivery barang/jasa (mitra) | 34875496682 | BIG | 14/11/2018 17:19:24
PROJ235 |  | ROLL OUT I ERP PTPN IV (MEDAN) | APPLICATION | PERKEBUNAN NUSANTARA IV PT | MAS |  |  | NURUL HIDAYATI | SIMON | PT Sigma Metrasys Solution | 01-MAR-17 | 31-DEC-18 | 99.992 | 99.83 | -0.162 | LAG | 3.Perubahan desain/spek pelanggan (customer) | 55638090000 | MEGA | 29/10/2018 19:18:19
PROJ2584 | LOP106718 | JASA MIGRASI PORT DARI LAYANAN VSAT KE MPLS UNTUK KEBUTUHAN 215 LOKASI ATM | CONNECTIVITY | BANK RAKYAT INDONESIA (PERSERO) | BMS-1 |  |  | NUR WIJAYANTO |  | PT Multimedia Nusantara | 31-AUG-18 | 31-DEC-18 |  |  |  | LEAD |  | 128260000 | REGULAR | 27/11/2018 14:54:22
PROJ2585 | LOP106715 | JASA MIGRASI PORT DARI LAYANAN VSAT KE MPLS DI 99 REMOTE EX PROVIDER CSM | CONNECTIVITY | BANK RAKYAT INDONESIA (PERSERO) | BMS-1 |  |  | NUR WIJAYANTO |  | PT Multimedia Nusantara | 31-AUG-18 | 31-DEC-18 |  |  |  | LEAD |  | 62260000 | REGULAR | 27/11/2018 14:52:17
PROJ26 |  | PROJECT SMART BUILDING SENTRALAND SEMARANG | SMART BUILDING | PERUMNAS PERUM | PCS |  |  | HADI TRIYONO | RADIAN SIGIT DWIANANTO | PT PINS Indonesia, PT PINS Indonesia | 16-JAN-15 | 31-MAR-18 | 100 | 87.181 | -12.8182 | DELAY | 1.Delivery barang/jasa (mitra) | 4129738470 | ORDINARY | 05/10/2018 14:35:44
PROJ261 |  | BRANZ SIMATUPANG ELECTRONIC GPON & ICT | SMART BUILDING | SUMMITMAS PROPERTY | PCS |  |  | PRAKOSA TRIWIBOWO | RADIAN SIGIT DWIANANTO | PT PINS Indonesia | 30-JAN-17 | 14-DEC-18 | 100 | 95.02 | -4.98 | LAG | 2.Kesiapan lokasi ( customer) | 12357698601 | ORDINARY | 23/11/2018 15:10:39
PROJ2631 | LOP106550 | COLLOCATION, MANAGED SERVICE ROUTER DAN CONNECTIVITY PT JTI | CPE & OTHERS | JAYA TEKNOLOGI INTERNASIONAL, PT | MAS |  |  | ARIEF SUSILO WIBOWO |  | PT Sigma Cipta Caraka, PT Teltranet Aplikasi Solusi (Telkom Telstra) | 01-AUG-18 | 31-OCT-18 | 92.35 | 90 | -2.35 | DELAY | 1.Delivery barang/jasa (mitra) | 4545500000 | ORDINARY | 26/11/2018 11:19:53
PROJ2698 |  | PENGADAAN SERVER PRODUCTION UNTUK APLIKASI MANAGEMENT INFORMATION SYSTEM (MIS) PT PEGADAIAN (PERSERO) | CPE & OTHERS | PEGADAIAN PT | FMS |  |  | FAHMI RAHMANTHAHA NURDINSYAH | ANDIKA PRATAMA PUTRA | PT Sigma Metrasys Solution | 23-AUG-18 | 06-NOV-18 | 96.56 | 87.37 | -9.19 | DELAY | 1.Delivery barang/jasa (mitra) | 16045000000 | ORDINARY | 26/11/2018 16:32:23
PROJ2875 | LOP107762 | PENGADAAN CASH MANAGEMENT SYSTEM BANK MANTAP (BANK MANDIRI TASPEN POS) | CPE & OTHERS | BANK MANDIRI TASPEN POS (MANTAP) | BMS-1 |  |  | ZAKY AHMAD |  | PT Sigma Cipta Caraka | 27-SEP-18 | 06-DEC-18 | 46.6 | 42 | -4.6 | LAG | 5.Keterlambatan SPK ke mitra (di awal) (Telkom) | 1245000000 | ORDINARY | 29/11/2018 10:57:45
PROJ2940 | LOP108000 | ASTINET LITE BACKUP TELKOMSEL FLASH 12 GB DAN 32 GM (CARD ONLY) - PT HERO SUPERMARKET, TBK | CONNECTIVITY | HERO SUPERMARKET | TDS |  |  | YUSUF SARTONO |  | PT Telekomunikasi Selular, PT Telekomunikasi Selular, PT Telekomunikasi Selular | 05-OCT-18 | 06-NOV-18 | 66.64 | 39 | -27.64 | DELAY | 2.Kesiapan lokasi ( customer) | 3057600000 | ORDINARY | 26/11/2018 10:40:30
PROJ3041 | LOP108246 | PEMBANGUNAN DATA CENTER PT PERTAMINA EP ASSET 5 | CPE & OTHERS | PERTAMINA PT | ERS |  |  | IKA SADERA M | REIKA ERMANSA | PT Sigma Cipta Caraka | 20-SEP-18 | 18-JAN-19 |  |  |  | LEAD |  | 1497000000 | ORDINARY | 13/11/2018 15:55:31
PROJ5 |  | PROJECT SAHID JOGJA LIFESTYLE | SMART BUILDING | GE OPERATIONS INDONESIA | IBS |  |  | HADI TRIYONO | TRINIL ANJAR LESTARI, ST | PT PINS Indonesia, PT PINS Indonesia | 26-MAR-15 | 28-FEB-18 | 100 | 95.39 | -4.61 | DELAY | 4.Keterlambatan BAST (customer) | 1700000000 | ORDINARY | 24/07/2018 12:12:02
PROJ59 |  | PROJECT ICT FTTH GPON (VERTIKAL DAN HORIZONTAL) DI APARTMENT BINTARO ICON | SMART BUILDING | ADITYA TOA DEV / MENARA THAMRIN | PCS |  |  | ATAM RUSTAM | NADIAH LIESTYASARI | PT PINS Indonesia | 01-MAY-16 | 30-NOV-18 | 100 | 93.37 | -6.63 | DELAY | 1.Delivery barang/jasa (mitra) | 5744549322 | ORDINARY | 14/11/2018 16:49:25
PROJ643 |  | PEKERJAAN PROYEK RUSUNAMI JAKABARING TOWER 3 | SMART BUILDING | PEMBANGUNAN PERUMAHAN PT | PCS |  |  | NAZIRWAN, ST. M.KOM | RADIAN SIGIT DWIANANTO | PT Graha Sarana Duta, PT Graha Sarana Duta | 02-OCT-17 | 28-MAR-18 | 99.83 | 99.26 | -0.57 | DELAY | 13.Kendala Finansial ( Customer ) | 8900000000 | ORDINARY | 12/09/2018 10:10:22
PROJ748 |  | ROLL OUT 3 PTPN 8 BANDUNG | APPLICATION | PERKEBUNAN NUSANTARA VIII PT | MAS |  |  | NURUL HIDAYATI | NURI FAJARIYANAH | PT Sigma Metrasys Solution | 01-OCT-17 | 30-NOV-18 | 100 | 64 | -36 | DELAY | 3.Perubahan desain/spek pelanggan (customer) | 65776050000 | MEGA | 29/10/2018 18:51:01
PROJ749 |  | ROLL OUT 3 PTPN 13 PONTIANAK | APPLICATION | PERKEBUNAN NUSANTARA XIII | MAS |  |  | NURUL HIDAYATI | HAMIDONG | PT Sigma Metrasys Solution | 01-OCT-17 | 30-NOV-18 | 96 | 55 | -41 | DELAY | 2.Kesiapan lokasi ( customer) | 18103500000 | ORDINARY | 28/11/2018 19:56:59
PROJ852 |  | PENYEDIAAN DIGITAL MENU BOARD BURGER KING INDONESIA 159 STORE | CPE & OTHERS | MAP FOOD & BEVERAGE | THS |  |  | HASBUR GHALI | EVY YULIA RAMADHAN | PT Teltranet Aplikasi Solusi (Telkom Telstra), PT Teltranet Aplikasi Solusi (Telkom Telstra) | 01-FEB-18 | 30-NOV-19 | 74.72 | 77.72 | 3 | LEAD | 2.Kesiapan lokasi ( customer) | 3728736000 | ORDINARY | 29/10/2018 13:43:21
PROJ51 |  | PROJECT WIFI.ID WHIZ PRIME HOTEL 180 TITIK | CONNECTIVITY | WHIZ HOTEL GROUP | THS |  |  | SRI NURFALAH | ANAK AGUNG ARDHA CHANDRA DEWI |  | 01-JAN-16 | 31-DEC-18 | 100 | 27 | -73.008 | LAG |  | 1122000000 | ORDINARY | 09/08/2018 16:53:34
PROJ107 |  | PROJECT WIFI.ID RICHEESE FACTORY | CONNECTIVITY | PT RICHEESE KULINER INDONESIA | THS |  |  | SRI NURFALAH | Noviyan Setiadi |  | 01-JUL-16 | 31-DEC-18 | 78.64 | 0 | -78.64 | LAG |  | 150000000 | REGULAR | 09/08/2018 16:54:05
PROJ2179 |  | LAYANAN MIGRASI VSAT KE VPN IP PT. PEGADAIAN | CONNECTIVITY | PEGADAIAN PT | FMS |  |  | FACHRI | ANDIKA PRATAMA PUTRA |  | 01-JUL-18 | 31-DEC-18 |  |  |  | LEAD |  | 248640300000 | MEGA | 06/11/2018 14:12:10
PROJ1285 | LOP25267 | PEKERJAAN ELEKTRONIK DAN ELEKTRIKAL DI APARTEMEN ZAMZAM TOWER DEPOK | SMART BUILDING | WIJAYA KARYA | PCS |  |  | TEDDY AWALUDIN | NOVI ANDRIYANI | PT Infrastruktur Telekomunikasi Indonesia (TELKOMINFRA) | 01-JAN-18 | 30-NOV-18 | 100 | 85.31 | -14.69 | DELAY | 1.Delivery barang/jasa (mitra) | 10200000000 | ORDINARY | 23/11/2018 10:28:02
PROJ1646 | LOP103401 | PROYEK PEMBANGUNAN B RESIDENCE, SERPONG - TANGERANG PEKERJAAN ELEKTRONIK | SMART BUILDING | PT. MAJU GEMILANG SERPONG | PCS |  |  | NAZIRWAN, ST. M.KOM | SUNARTO AMSALOM SAIRO | PT PINS Indonesia, PT PINS Indonesia | 15-JAN-18 | 15-SEP-19 | 15.624 | 19 | 3.376 | LEAD | 2.Kesiapan lokasi ( customer) | 17985000000 | ORDINARY | 27/11/2018 10:26:15
PROJ1944 | LOP104864 | PENGADAAN JARINGAN DATA GRAHA INKA | CPE & OTHERS | INKA | IBS |  |  | RUDIONO |  | PT PINS Indonesia | 03-JUL-18 | 31-DEC-18 | 100 | 69.69 | -30.311 | LAG | 1.Delivery barang/jasa (mitra) | 2585000000 | ORDINARY | 27/11/2018 09:57:45
PROJ2237 | LOP105044 | PEKERJAAN PEMBANGUNAN SMART BUILDING PADA KANTOR BARU DI BELAWAN PT. PELABUHAN INDONESIA I (PERSERO) | SMART BUILDING | PELINDO 1 | MLS |  |  | NAZIRWAN, ST. M.KOM |  | PT PINS Indonesia, PT PINS Indonesia | 28-JUN-18 | 26-OCT-18 | 100 | 29.982 | -70.019 | DELAY | 2.Kesiapan lokasi ( customer) | 10288470610 | ORDINARY | 28/11/2018 09:29:19
PROJ2398 |  | PEKERJAAN ELEKTRONIK PROJEK TRANS PARK BEKASI | SMART BUILDING | ADHI KARYA PT | PCS |  |  | IMAM ZAHIR | DWI PUDJI IRAWATI | PT PINS Indonesia | 26-JUL-18 | 20-JUL-19 |  |  |  | LEAD |  | 20300000156 | BIG | 05/11/2018 09:15:26
PROJ243 |  | BRANZ BSD ELECTRONIC GPON & ICT | SMART BUILDING | ALAM SUTERA REALTY | PCS |  |  | PRAKOSA TRIWIBOWO | HANDI JUNAEDI | PT PINS Indonesia | 30-JAN-17 | 30-APR-18 | 99.999 | 96.5 | -3.499 | DELAY | 1.Delivery barang/jasa (mitra) | 9614060207 | ORDINARY | 23/11/2018 15:12:30
PROJ2615 | LOP103465 | PAKET PEKERJAAN PUBLIKASI BRANDING PARIWISATA INDONESIA MELALUI KERJASAMA DENGAN PELAKU INDUSTRI ONLINE INTERNATIONAL - KEMENPAR | CPE & OTHERS | PENGEMBANGAN PEMASARAN PARIWISATA | THS |  |  | ADRID |  | PT Metra Digital Media | 29-AUG-18 | 26-DEC-18 | 78.65 | 51.51 | -27.14 | LAG | 10.Keterbatasan kapabilitas mitra (mitra) | 88833800000 | MEGA | 30/11/2018 11:00:43
PROJ2669 | LOP107004 | PENGADAAN KONEKSI DIGITAL UNTUK PASSENGER EXIT SURVEY - BPS | APPLICATION | PENGELOLA STATISTIK DISTRIBUSI DAN JASA | THS |  |  | IMAM ZAHIR |  | PT Metra Digital Media | 27-AUG-18 | 31-DEC-18 | 72.02 | 17.72 | -54.3 | LAG |  | 5681850000 | ORDINARY | 29/11/2018 09:18:05
PROJ3170 | LOP108588 | PKS RELOKASI COLOCATION BTPN SYARIAH | CPE & OTHERS | BANK BTPN | BMS-2 |  |  | HASBUR GHALI | BERTHA DESVIANI PURBA | PT Sigma Cipta Caraka | 10-OCT-18 | 07-DEC-18 | 74 | 10 | -64 | LAG |  | 7735000000 | ORDINARY | 21/11/2018 14:12:43
PROJ367 |  | LAYANAN INFOKOM MODERENISASI JARINGAN GRAND INDONESIA | SMART BUILDING | GRAND INDONESIA | PCS |  |  | TEDDY AWALUDIN | NOVI ANDRIYANI | PT. Bangtelindo | 01-DEC-16 | 31-DEC-18 | 100.03 | 93.48 | -6.553 | LAG | 1.Delivery barang/jasa (mitra) | 6685966305 | ORDINARY | 23/11/2018 10:41:27
PROJ37 |  | PROJECT SMART BUILDING MARIGOLD NAVAPARK - BSD | SMART BUILDING | ADHI KARYA PT | PCS |  |  | TEDDY AWALUDIN |  | PT PINS Indonesia, PT PINS Indonesia | 05-FEB-16 | 31-DEC-18 | 99.83 | 35.57 | -64.26 | LAG | 8.CR (perubahan yang belum terkendali) & amandemen (customer) | 16500000000 | ORDINARY | 23/11/2018 10:49:44
PROJ457 |  | PROJECT GPON ICT DI CIPUTRA INTERNASIONAL | SMART BUILDING | CIPUTRA WORLD JAKARTA | PCS |  |  | IRWANDI | GERRY ROY MANAEK SIAHAAN | PT PINS Indonesia | 02-NOV-16 | 31-DEC-17 | 69.82 | 89.42 | 19.6 | DELAY | 2.Kesiapan lokasi ( customer) | 5336000000 | ORDINARY | 30/11/2018 10:46:42
PROJ740 |  | PROJECT PEKERJAAN PENGADAAN DAN IMPLEMENTASI ERP DI PT. KAWASAN INDUSTRI MEDAN (KIM) | APPLICATION | KAWASAN INDUSTRI MEDAN (KIM) | IBS |  |  | RIKA AMALIA SASANTY | FENNY NOVITA | PT Infomedia Nusantara | 01-NOV-17 | 30-JUN-18 | 100 | 100 | 0 | DELAY | 4.Keterlambatan BAST (customer) | 889345600 | REGULAR | 05/09/2018 14:47:21
PROJ743 |  | PENGADAAN SEWA EDC PERUNTUKAN BANSOS BANK BTN | CPE & OTHERS | BANK TABUNGAN NEGARA (PERSERO) | BMS-1 |  |  | SHEPTIAN KURNIA SALEH | DISKAERI | PT Sigma Cipta Caraka, PT Sigma Cipta Caraka | 22-SEP-17 | 31-DEC-18 | 100 | 70 | -30 | LAG | 2.Kesiapan lokasi ( customer) | 7265454545 | ORDINARY | 01/11/2018 14:22:01
PROJ745 |  | ROLL OUT 2 PTPN 1 ACEH | APPLICATION | PERKEBUNAN NUSANTARA I PT | MAS |  |  | NURUL HIDAYATI | AGUS FRIADI | PT Sigma Metrasys Solution | 01-OCT-17 | 31-DEC-18 | 93.4 | 63 | -30.4 | LAG | 3.Perubahan desain/spek pelanggan (customer) | 12793140000 | ORDINARY | 29/10/2018 19:01:52
PROJ751 |  | ROLL OUT 3 KPBN JAKARTA | APPLICATION | PERKEBUNAN NUSANTARA VII PT | MAS |  |  | NURUL HIDAYATI | ANWAR | PT Sigma Metrasys Solution | 01-OCT-17 | 31-DEC-18 | 100 | 100 | 0 | LEAD | 1.Delivery barang/jasa (mitra) | 844830000 | REGULAR | 28/11/2018 18:57:23
PROJ774 |  | PENGADAAN EDGE ROUTER MPLS & CELLULER, DAN CORE ROUTER | CPE & OTHERS | BANK RAKYAT INDONESIA (PERSERO) | BMS-1 |  |  | FAHMI RAHMANTHAHA NURDINSYAH | RUDY SETYO NUGROHO | PT PINS Indonesia, PT PINS Indonesia | 04-DEC-17 | 02-FEB-18 | 100 | 100 | 0 | DELAY | 6.Masalah Administrasi & pembayaran mitra (Telkom) | 15300000000 | ORDINARY | 19/10/2018 18:25:42
PROJ829 |  | PROJECT APARTEMEN GRAND JATI JUNCTION MEDAN | SMART BUILDING | PEMBANGUNAN PERUMAHAN PT | PCS |  |  | NAZIRWAN, ST. M.KOM | RADIAN SIGIT DWIANANTO | PT Graha Sarana Duta, PT Graha Sarana Duta | 01-SEP-17 | 31-DEC-18 | 100 | 67.715 | -32.285 | LAG | 8.CR (perubahan yang belum terkendali) & amandemen (customer) | 35280000000 | BIG | 13/11/2018 08:36:31
PROJ843 |  | NAC SOLUTION EDC DIAL UP BANK MANDIRI | CPE & OTHERS | BANK MANDIRI | BMS-1 |  |  | MUHAMMAD MASYHUDI | FERY KURNIAWAN | PT Sigma Cipta Caraka | 21-SEP-17 | 31-OCT-18 | 100 | 89.21 | -10.79 | DELAY | 8.CR (perubahan yang belum terkendali) & amandemen (customer) | 39960000000 | BIG | 30/10/2018 01:19:15
PROJ416 |  | WIFI.ID RUMAH SAKIT MITRA KELUARGA | CONNECTIVITY | RUMAH SAKIT MITRA KELUARGA | HWS |  |  | SRI NURFALAH | SAPHIRA DIELLA VARIANTY |  | 01-JAN-17 | 31-DEC-18 | 82 | 100 | 18 | LAG |  | 509914080 | REGULAR | 30/10/2018 11:10:38
PROJ1240 |  | PERUBAHAN LAYANAN DAN PENAMBAHAN LOKASI MANAGE SERVICE ASTINET LITE 212 LOKASI PT. CHAROEN POKPHAND | CONNECTIVITY | CHAROEN POKPHAND INDONESIA PT | MAS |  |  | YUSUF SARTONO | ANISAH SOFWATI |  | 27-MAR-18 | 26-MAR-19 | 100 | 66 | -34 | LAG | 2.Kesiapan lokasi ( customer) | 5003200000 | ORDINARY | 26/11/2018 10:37:05
PROJ207 |  | WIFI.ID ANGKASA PURA I (NGURAH RAI) TAHAP 2 | CONNECTIVITY | ANGKASAPURA I | TMS |  |  | SRI NURFALAH | ONHI YULIARTI SEMARA |  | 01-JAN-17 | 31-DEC-18 |  |  |  | LAG |  | 2394000000 | ORDINARY | 09/08/2018 16:54:46
PROJ1115 |  | PROJECT PUSTAKA MULIA | CPE & OTHERS | PUSTAKA MULIA | EMS |  |  | HASBUR GHALI | ARROZAQ AVE | PT Balebat Dedikasi Prima | 21-DEC-17 | 30-NOV-18 | 98.23 | 100 | 1.77 | DELAY | 1.Delivery barang/jasa (mitra) | 108995000000 | MEGA | 28/11/2018 11:13:28
PROJ13 |  | PROJECT ERP SAP INALUM | APPLICATION | INDONESIA ASAHAN ALUMUNIUM | MAS |  |  | RISTYAWAN FAUZI MUBAROK | SIMON | PT Sigma Metrasys Solution | 01-JUL-15 | 24-AUG-18 | 100 | 100 | 0 | DELAY | 4.Keterlambatan BAST (customer) | 32284783041 | BIG | 19/10/2018 14:37:13
PROJ1492 | LOP24865 | ORACLE ENTERPRISE BUSINESS SUITE (EBS) SUPPLY CHAIN MANAGEMENT`MODULE PT. PELNI (PERSERO) | APPLICATION | PELAYARAN NASIONAL INDONESIA (PELNI) PT | MLS |  |  | ADRID | NAWIN | SIGMA SOLUSI INTEGRASI | 06-MAR-18 | 08-MAR-19 | 98.3 | 68.5 | -29.8 | LAG | 8.CR (perubahan yang belum terkendali) & amandemen (customer) | 8935000000 | ORDINARY | 26/11/2018 10:25:22
PROJ1755 | LOP103688 | PENGADAAN PERANGKAT HARDWARE UNTUK KEBUTUHAN ADMIN KAPAL, KANTOR PUSAT DAN CABANG DENGAN MENGGUNAKAN SKEMA SEAT MANAGEMENT | CPE & OTHERS | PELAYARAN NASIONAL INDONESIA (PELNI) PT | MLS |  |  | FAHMI RAHMANTHAHA NURDINSYAH | NAWIN | PT Sigma Cipta Caraka | 26-JUN-18 | 31-OCT-18 | 90 | 80 | -10 | DELAY | 1.Delivery barang/jasa (mitra) | 16205288400 | ORDINARY | 23/10/2018 14:09:35
PROJ18 |  | PROJECT VIMALA HILLS (PANIC BUTTON) | SMART BUILDING | PODOMORO GROUP | PCS |  |  | HERI IKHWAN DIANA | GERRY ROY MANAEK SIAHAAN | PT PINS Indonesia | 10-MAR-14 | 31-MAY-18 | 100 | 90.95 | -9.05 | DELAY | 8.CR (perubahan yang belum terkendali) & amandemen (customer) | 2100000000 | ORDINARY | 19/10/2018 16:06:43
PROJ19 |  | PROJECT CCTV VIMALA HILLS GADOG | SMART BUILDING | PODOMORO GROUP | PCS |  |  | HERI IKHWAN DIANA | NOVI ANDRIYANI | PT PRAMINDO IKAT NUSANTARA (PINS) | 07-AUG-14 | 31-DEC-17 | 100 | 100 | 0 | DELAY | 8.CR (perubahan yang belum terkendali) & amandemen (customer) | 2321000000 | ORDINARY | 19/10/2018 15:55:42
PROJ203 |  | ERP N-HOLDING | APPLICATION | PERKEBUNAN NUSANTARA III PT | MAS |  |  | NURUL HIDAYATI | ADRI SYAFMA PUTRA | PT Sigma Metrasys Solution | 17-AUG-16 | 31-DEC-18 | 98.802 | 74.86 | -23.942 | LAG | 3.Perubahan desain/spek pelanggan (customer) | 10888000000 | ORDINARY | 29/10/2018 19:22:22
PROJ204 |  | PROJECT RESUNAMI GRAND SENTRALAND KARAWANG | SMART BUILDING | PEMBANGUNAN PERUMAHAN PT | PCS |  |  | TEUKU HAMIZUL | RADIAN SIGIT DWIANANTO | PT Infomedia Nusantara, PT Infomedia Nusantara, PT Infomedia Nusantara | 31-OCT-16 | 30-JUN-18 | 99.997 | 82.009 | -17.988 | DELAY | 3.Perubahan desain/spek pelanggan (customer) | 23500000000 | BIG | 02/11/2018 18:58:17
PROJ2680 |  | PEKERJAAN SEAT MANAGEMENT ICON+ (PENGADAAN SEWA LAPTOP DAN DESKTOP) | CPE & OTHERS | ICON PLUS | ERS |  |  | NAZIRWAN, ST. M.KOM | DITO BARATA JUNANTO | PT Signet Pratama | 20-APR-18 | 31-DEC-18 | 81.51 | 79.5 | -2.01 | LAG | 7.SoW belum sepakat (Telkom) | 19935842400 | ORDINARY | 27/11/2018 10:16:09
PROJ2695 |  | PENGADAAN PEREMAJAAN PERANGKAT VIDEO CONFERENCE PT PEGADAIAN (PERSERO) TAHUN 2018 | CPE & OTHERS | PEGADAIAN PT | FMS |  |  | FAHMI RAHMANTHAHA NURDINSYAH | ANDIKA PRATAMA PUTRA | PT Sigma Metrasys Solution | 21-AUG-18 | 27-NOV-18 |  |  |  | DELAY |  | 5363636364 | ORDINARY | 19/10/2018 18:44:41
PROJ29 |  | PROJECT GRAND TARUMA KARAWANG | SMART BUILDING | ADHI KARYA PT | PCS |  |  | TEDDY AWALUDIN | NOVI ANDRIYANI | PT PINS Indonesia | 09-MAY-14 | 31-DEC-18 | 100 | 99.69 | -0.31 | LAG | 8.CR (perubahan yang belum terkendali) & amandemen (customer) | 2888000000 | ORDINARY | 23/11/2018 10:52:13
PROJ364 |  | IMPLEMENTASI ORACLE PRIMAVERA DI PT PAL INDONESIA | APPLICATION | PAL | IBS |  |  | NURUL HIDAYATI | FACHRUL INDRACAHYO | SIGMA SOLUSI INTEGRASI | 28-FEB-17 | 31-DEC-18 | 99.996 | 88.1 | -11.896 | LAG | 2.Kesiapan lokasi ( customer) | 3044996000 | ORDINARY | 27/11/2018 14:41:53
PROJ449 |  | PURI MANSION APARTMENT | SMART BUILDING | AGUNG SEDAYU PROPERTINDO | IBS |  |  | HERU IRMAN | FAHMI MUHAMMAD HUSIN | PT PINS Indonesia | 10-JUL-17 | 07-OCT-17 | 100 | 80 | -20 | DELAY | 3.Perubahan desain/spek pelanggan (customer) | 8301000000 | ORDINARY | 31/10/2018 15:40:35
PROJ456 |  | ICT DAN ELECTRONIC INSTALLATION DI THE WILADATIKA RESIDENCE | SMART BUILDING | ARTHA TELEKOMINDO | PCS |  |  | TEDDY AWALUDIN | GOGATAMA DESENWA PRAYOGA | PT PINS Indonesia | 01-DEC-15 | 28-FEB-19 | 100 | 66.03 | -33.97 | LAG | 5.Keterlambatan SPK ke mitra (di awal) (Telkom) | 5100000000 | ORDINARY | 23/11/2018 10:36:44
PROJ656 |  | PROJECT CCTV ORCHARD PARK BATAM | SMART BUILDING | PENGUSAHAAN DAERAH INDUSTRI PULAU BATAM PT | PCS |  |  | IRWANDI | AGUS WIDIANTARA | PT PINS Indonesia, PT PINS Indonesia | 13-OCT-17 | 30-MAR-18 | 100 | 89.5 | -10.5 | DELAY |  | 1468000000 | ORDINARY | 30/11/2018 10:40:11
PROJ744 |  | ROLL OUT 2 PTPN 6 JAMBI | APPLICATION | PERKEBUNAN NUSANTARA VI PT | MAS |  |  | NURUL HIDAYATI | ANWAR | PT Sigma Metrasys Solution | 01-OCT-17 | 31-DEC-18 | 100 | 100 | 0 | LAG | 3.Perubahan desain/spek pelanggan (customer) | 30896640000 | BIG | 29/10/2018 19:09:12
PROJ42 |  | PROJECT WIFI.ID GARUDA INDONESIA | CONNECTIVITY | GARUDA INDONESIA PT | TMS |  |  | SRI NURFALAH | NOSKI PANDAPOTAN SAMOSIR |  | 01-JAN-16 | 31-DEC-18 | 78.73 | 10 | -68.73 | LAG |  | 162000000 | REGULAR | 09/11/2018 17:06:44