## Worksheet
ID PROJECT | ID LOP | PROJECT NAME | TYPE PROJECT | CLIENT | SEGMEN | NOMOR KB | NOMOR KL | PM NAME | AM NAME | PARTNERS | START DATE | END DATE | PLAN | ACHIEVEMENT | DEVIASI | STATUS | REASON OF DELAY | PROJECT VALUE | CATEGORY | LAST UPDATE
PROJ4464 |  | PENYEDIAAN LAYANAN INTERNET WIFI ID DAN USEE TV CHANNELS | CONNECTIVITY | ASTON HOTEL BALI | THS |  |  | SRI NURFALAH | I MADE BUDIANA, SE, MM |  | 12-NOV-18 | 12-APR-19 |  | 0 |  | LEAD |  | 12000000 | REGULAR | 25/02/2019 10:53:34
PROJ3212 |  | LAYANAN REFRESHMENT INFRASTRUKTUR LAN PT PUPUK ISKANDAR MUDA (PIM) | CPE DEVICES | PUPUK ISKANDAR MUDA | MAS |  |  | RANDY NOARY | MULKI ZUCHRI |  | 13-OCT-18 | 10-FEB-19 |  | 0 |  | DELAY |  | 4791949310 | ORDINARY | 01/11/2018 13:56:56
PROJ3522 |  | ASTINET LITE 93 LOKASI UNTUK PT. INDOMOBIL FINANCE INDONESIA | CONNECTIVITY | INDOMOBIL GROUP | IBS |  |  | ARI WIDIYANTO | ANDI SYAHRUDDIN |  | 04-OCT-18 | 31-DEC-18 |  | 0 |  | DELAY |  | 2136901944 | ORDINARY | 27/11/2018 18:30:39
PROJ21 |  | PROJECT CWJ 2 PHASE 1 | SMART BUILDING | CIPUTRA WORLD JAKARTA | PCS |  | null | IRWANDI | GERRY ROY MANAEK SIAHAAN | PT PINS Indonesia | 26-SEP-14 | 31-DEC-17 | 99.695 | 99.7 | 0.005 | DELAY | 2.Kesiapan lokasi ( customer) | 23660990600 | BIG | 12/03/2019 15:57:35
PROJ31 |  | PROJECT INTERNATIONAL FINANCIAL CENTER 2 | SMART BUILDING | INTERNATIONAL FINANCIAL CENTER | PCS |  |  | HERI IKHWAN DIANA | DWI PUDJI IRAWATI | PT PINS Indonesia | 18-AUG-15 | 30-SEP-17 | 100 | 95.67 | -4.33 | DELAY | 5.Keterlambatan SPK ke mitra (di awal) (Telkom) | 2484600427 | ORDINARY | 19/10/2018 16:18:35
PROJ234 |  | ROLL OUT I ERP PTPN III (MEDAN) | APPLICATION | PERKEBUNAN NUSANTARA III PT | MAS |  | null | NURUL HIDAYATI | SIMON | PT Sigma Metrasys Solution | 01-MAR-17 | 30-JUN-19 | 100 | 99.989 | -0.011 | LAG | 8.CR (perubahan yang belum terkendali) & amandemen (customer) | 65172600000 | MEGA | 27/02/2019 17:58:25
PROJ456 |  | ICT DAN ELECTRONIC INSTALLATION DI THE WILADATIKA RESIDENCE | SMART BUILDING | ARTHA TELEKOMINDO | PCS |  |  | TEDDY AWALUDIN | GOGATAMA DESENWA PRAYOGA | PT PINS Indonesia | 01-DEC-15 | 28-FEB-19 |  | 94.71 |  | DELAY | 5.Keterlambatan SPK ke mitra (di awal) (Telkom) | 5100000000 | ORDINARY | 30/01/2019 11:39:27
PROJ852 |  | PENYEDIAAN DIGITAL MENU BOARD BURGER KING INDONESIA 159 STORE | CPE DEVICES | MAP FOOD & BEVERAGE | THS |  | null | HASBUR GHALI | EVY YULIA RAMADHAN | PT Teltranet Aplikasi Solusi (Telkom Telstra), PT Teltranet Aplikasi Solusi (Telkom Telstra), PT Teltranet Aplikasi Solusi (Telkom Telstra), PT Teltranet Aplikasi Solusi (Telkom Telstra), PT Teltranet Aplikasi Solusi (Telkom Telstra) | 01-FEB-18 | 30-NOV-19 | 82.22 | 89.94 | 7.72 | LAG | 2.Kesiapan lokasi ( customer) | 3728736000 | ORDINARY | 27/02/2019 11:37:38
PROJ2141 | LOP105334 | PENYEDIAAN ICT, PABX, DATA, CCTV, SOUND SYSTEM, FIRE ALARM & IPTV PROYEK RSKIA KOTA BANDUNG | SMART BUILDING | ADHI KARYA PT | PCS | K.TEL.06-0868/HK.810/DES-00/2018 | null | PRAKOSA TRIWIBOWO | DWI PUDJI IRAWATI | PT PINS Indonesia | 04-JUN-18 | 28-DEC-18 | 56.22 | 29.7 | -26.52 | DELAY | 1.Delivery barang/jasa (mitra) | 7650000000 | ORDINARY | 13/03/2019 14:37:17
PROJ2396 |  | PROJECT EASTERN GREEN BEKASI | SMART BUILDING | ADHI KARYA PT | PCS |  | null | PRAKOSA TRIWIBOWO | DWI PUDJI IRAWATI | PT PINS Indonesia | 30-NOV-17 | 30-NOV-19 | 100 | 45.92 | -54.08 | LAG | 2.Kesiapan lokasi ( customer) | 6850000000 | ORDINARY | 13/03/2019 14:31:48
PROJ2443 | LOP106326 | SEWA LAYANAN LAN EXTENSION ASSET 5 | CPE DEVICES | PERTAMINA PT | ERS | K.TEL.08-0209/HK.850/ DES-00/2018 | null | IKA SADERA M | REIKA ERMANSA | PT Nusantara Compnet Integrator, PT Wave Communication Indonesia | 26-OCT-18 | 31-JAN-19 | 56 | 90 | 34 | DELAY |  | 5992332000 | ORDINARY | 12/03/2019 15:18:16
PROJ2583 | LOP106720 | JASA MIGRASI PORT DARI LAYANAN VSAT KE MPLS DI 244 REMOTE | CONNECTIVITY | BANK RAKYAT INDONESIA (PERSERO) | BMS-1 |  | null | NUR WIJAYANTO | RUDY SETYO NUGROHO | PT Multimedia Nusantara | 31-AUG-18 | 31-DEC-18 |  | 0 |  | DELAY |  | 142450000 | REGULAR | 13/03/2019 14:25:25
PROJ2584 | LOP106718 | JASA MIGRASI PORT DARI LAYANAN VSAT KE MPLS UNTUK KEBUTUHAN 215 LOKASI ATM | CONNECTIVITY | BANK RAKYAT INDONESIA (PERSERO) | BMS-1 | K.TEL.03-0840/HK.850/DES-BMS1/2018 | null | NUR WIJAYANTO | RUDY SETYO NUGROHO | PT Multimedia Nusantara | 31-AUG-18 | 31-DEC-18 |  | 0 |  | DELAY |  | 128260000 | REGULAR | 13/03/2019 14:23:56
PROJ2789 | LOP107494 | PERPANJANGAN JASA DEDICATED COLOCATION DATA CENTER UNTUK BANK SYARIAH MANDIRI | CPE DEVICES | BANK SYARIAH MANDIRI | BMS-1 |  | null | FAHMI RAHMANTHAHA NURDINSYAH | FARAINY ADINDA GITAWARDHANI | PT Sigma Cipta Caraka | 01-FEB-18 | 31-JAN-19 |  | 0 |  | DELAY |  | 6500000000 | ORDINARY | 11/03/2019 16:15:11
PROJ2875 | LOP107762 | PENGADAAN CASH MANAGEMENT SYSTEM BANK MANTAP (BANK MANDIRI TASPEN POS) | CPE DEVICES | BANK MANDIRI TASPEN POS (MANTAP) | BMS-1 |  | null | ZAKY AHMAD | M. AGUSTINUS SIANTURI | PT Sigma Cipta Caraka | 27-SEP-18 | 16-APR-19 | 66.52 | 64.5 | -2.02 | LAG | 5.Keterlambatan SPK ke mitra (di awal) (Telkom) | 1245000000 | ORDINARY | 12/03/2019 17:07:29
PROJ2940 | LOP108000 | ASTINET LITE BACKUP TELKOMSEL FLASH 12 GB DAN 32 GM (CARD ONLY) - PT HERO SUPERMARKET, TBK | CONNECTIVITY | HERO SUPERMARKET | TDS |  |  | YUSUF SARTONO | POERBO SOESENO | PT Telekomunikasi Selular, PT Telekomunikasi Selular, PT Telekomunikasi Selular | 05-OCT-18 | 06-NOV-18 | 100 | 50.6 | -49.4 | DELAY | 2.Kesiapan lokasi ( customer) | 3057600000 | ORDINARY | 04/03/2019 14:08:50
PROJ3348 | LOP21683 | JASA SYSTEM MANAGEMENT MONITORING PRODUCTION PERUM PERURI | APPLICATION | PERURI PERUM | FMS | K.TEL.11-0905/HK.810/DES-FMS/2018 | null | DODI IRAWAN | MULYADI, ST | PT PINS Indonesia, PT PINS Indonesia | 12-NOV-18 | 31-MAR-19 | 100 | 91.55 | -8.45 | LAG | 1.Delivery barang/jasa (mitra) | 680454545 | REGULAR | 13/03/2019 14:23:08
PROJ3530 | LOP109710 | IMPLEMENTASI BIG DATA KIMIA FARMA | CPE DEVICES | KIMIA FARMA PT | HWS |  |  | ZAKY AHMAD | MELANY ULFA | PT Metra-Net | 22-NOV-18 | 22-NOV-19 | 68 | 41.6 | -26.4 | LAG | 10.Keterbatasan kapabilitas mitra (mitra) | 21720155875 | BIG | 12/03/2019 16:54:47
PROJ3598 | LOP109855 | PENGADAAN PROYEK RELOKASI & PENINGKATAN KAPASITAS DATA CENTER (COLOCATION) BANK BUKOPIN | CPE DEVICES | BANK BUKOPIN | BMS-2 |  | null | FAHMI RAHMANTHAHA NURDINSYAH | GALIH ABDUL RAUF | PT Sigma Cipta Caraka | 30-NOV-18 | 31-MAR-19 |  | 0 |  | LEAD |  | 94812000000 | MEGA | 29/01/2019 01:03:05
PROJ4201 |  | WIFI.ID ANGKASA PURA II 2018 - 2019 | CONNECTIVITY | ANGKASA PURA II (PERSERO) - BUISH | TMS |  | null | SRI NURFALAH | FERRYMANSYAH, ST |  | 16-JUL-18 | 17-JUL-19 | 26.95 | 92 | 65.05 | LAG |  | 9798840000 | ORDINARY | 12/03/2019 10:08:34
PROJ8 |  | PROJECT WIFI ID SAMSUNG EXPERIENCE STORE 106 LOKASI | CONNECTIVITY | SAMSUNG ELECTRONIC INDONESIA | IBS |  |  | SRI NURFALAH | ANDI SYAHRUDDIN |  | 01-APR-14 | 31-DEC-18 | 100 | 60 | -40 | DELAY |  | 111600000 | REGULAR | 05/03/2019 08:50:51
PROJ1240 |  | PERUBAHAN LAYANAN DAN PENAMBAHAN LOKASI MANAGE SERVICE ASTINET LITE 212 LOKASI PT. CHAROEN POKPHAND | CONNECTIVITY | CHAROEN POKPHAND INDONESIA PT | MAS |  |  | YUSUF SARTONO | ANISAH SOFWATI |  | 27-MAR-18 | 26-MAR-19 | 100 | 76 | -24 | LAG | 2.Kesiapan lokasi ( customer) | 5003200000 | ORDINARY | 04/03/2019 14:10:26
PROJ42 |  | PROJECT WIFI.ID GARUDA INDONESIA | CONNECTIVITY | GARUDA INDONESIA PT | TMS |  |  | SRI NURFALAH | NOSKI PANDAPOTAN SAMOSIR |  | 01-JAN-16 | 31-DEC-18 | 95 | 100 | 5 | DELAY |  | 162000000 | REGULAR | 31/12/2018 13:58:20
PROJ11 |  | PROJECT PARK LAND AVENUE | SMART BUILDING | SUMMARECON AGUNG TBK | IBS |  | null | PRAKOSA TRIWIBOWO | ACHMAD SUTARJONO | PT PINS Indonesia | 01-NOV-15 | 30-DEC-18 | 99.07 | 63.191 | -35.879 | DELAY | 11.Komitmen mitra(termasuk deal harga)(mitra) | 3550000000 | ORDINARY | 13/03/2019 14:48:23
PROJ18 |  | PROJECT VIMALA HILLS (PANIC BUTTON) | SMART BUILDING | PODOMORO GROUP | PCS |  |  | HERI IKHWAN DIANA | GERRY ROY MANAEK SIAHAAN | PT PINS Indonesia | 10-MAR-14 | 31-MAY-18 | 100 | 90.95 | -9.05 | DELAY | 8.CR (perubahan yang belum terkendali) & amandemen (customer) | 2100000000 | ORDINARY | 19/10/2018 16:06:43
PROJ82 |  | PROJECT ELECTRONIC & FTTH COUNTRY CLUB NAVAPARK | SMART BUILDING | SINAR MAS WISESA | PCS |  |  | TEDDY AWALUDIN |  | PT PINS Indonesia, PT PINS Indonesia | 01-FEB-16 | 30-NOV-18 |  | 100 |  | DELAY | 8.CR (perubahan yang belum terkendali) & amandemen (customer) | 2430000000 | ORDINARY | 27/12/2018 10:32:04
PROJ95 |  | PROJECT ERP N-HOLDING LOKASI : PTPN V (PEKANBARU) | APPLICATION | PERKEBUNAN NUSANTARA V PT | MAS |  | null | NURUL HIDAYATI | SITI WIMA ADITYA MAHADINI | PT Sigma Metrasys Solution | 17-AUG-16 | 30-JUN-19 | 100 | 94 | -6 | LAG | 8.CR (perubahan yang belum terkendali) & amandemen (customer) | 35603550000 | BIG | 27/02/2019 18:24:12
PROJ182 |  | PROJECT IN BUILDING SOLUTION (IBS) KEMPINSKI HOTEL BALI | SMART BUILDING | GRAHA ALAM LESTARI | PCS |  | null | AD STEFEN RATU EDA | GERRY ROY MANAEK SIAHAAN | PT Dayamitra Telekomunikasi, PT Dayamitra Telekomunikasi | 16-DEC-16 | 30-APR-19 | 100 | 95.36 | -4.64 | LAG | 2.Kesiapan lokasi ( customer) | 7100000000 | ORDINARY | 11/03/2019 14:11:12
PROJ236 |  | ROLL OUT I ERP PTPN IX (SEMARANG) | APPLICATION | PERKEBUNAN NUSANTARA IX | MAS |  | null | NURUL HIDAYATI | NANANG RUSTANDI | PT Sigma Metrasys Solution | 01-MAR-17 | 30-JUN-19 | 99.992 | 99.53 | -0.462 | LAG | 8.CR (perubahan yang belum terkendali) & amandemen (customer) | 31017330000 | BIG | 27/02/2019 19:24:09
PROJ237 |  | ROLL OUT I ERP PTPN XII (SURABAYA) | APPLICATION | PERKEBUNAN NUSANTARA XII PT | MAS |  | null | NURUL HIDAYATI | I GUSTI BAGUS YOGISWARA GHEARTHA | PT Sigma Metrasys Solution | 01-MAR-17 | 30-JUN-19 | 100 | 95 | -5 | LAG | 8.CR (perubahan yang belum terkendali) & amandemen (customer) | 19793160000 | ORDINARY | 27/02/2019 19:30:43
PROJ642 |  | PEKERJAAN PROYEK RUSUNAMI JAKABARING TOWER 1 DAN 2 | SMART BUILDING | PEMBANGUNAN PERUMAHAN PT | PCS |  | null | NAZIRWAN, ST. M.KOM | RADIAN SIGIT DWIANANTO | PT Graha Sarana Duta | 02-OCT-17 | 28-MAR-18 | 99.33 | 99.33 | 0 | DELAY | 13.Kendala Finansial ( Customer ) | 6000000000 | ORDINARY | 13/03/2019 13:14:26
PROJ643 |  | PEKERJAAN PROYEK RUSUNAMI JAKABARING TOWER 3 | SMART BUILDING | PEMBANGUNAN PERUMAHAN PT | PCS |  | null | NAZIRWAN, ST. M.KOM | RADIAN SIGIT DWIANANTO | PT Graha Sarana Duta, PT Graha Sarana Duta | 02-OCT-17 | 28-MAR-18 | 99.83 | 99.26 | -0.57 | DELAY | 13.Kendala Finansial ( Customer ) | 8900000000 | ORDINARY | 13/03/2019 12:32:26
PROJ746 |  | ROLL OUT 2 PTPN 2 MEDAN | APPLICATION | PERKEBUNAN NUSANTARA II PT | MAS |  | null | NURUL HIDAYATI | SIMON | PT Sigma Metrasys Solution | 01-OCT-17 | 30-JUN-19 | 79 | 92 | 13 | LAG | 8.CR (perubahan yang belum terkendali) & amandemen (customer) | 31982850000 | BIG | 27/02/2019 17:20:18
PROJ748 |  | ROLL OUT 3 PTPN 8 BANDUNG | APPLICATION | PERKEBUNAN NUSANTARA VIII PT | MAS |  | null | NURUL HIDAYATI | EKO ARDIANSYAH PUTRA | PT Sigma Metrasys Solution | 01-OCT-17 | 30-JUN-19 | 100 | 93 | -7 | LAG | 8.CR (perubahan yang belum terkendali) & amandemen (customer) | 65776050000 | MEGA | 27/02/2019 19:18:07
PROJ801 | LOP101832 | PROJECT DIGITALISASI KIMIA FARMA | CPE DEVICES | KIMIA FARMA PT | HWS |  | null | ADRID | MELANY ULFA | PT Sigma Cipta Caraka | 27-DEC-17 | 31-DEC-18 | 100 | 98 | -2 | DELAY | 10.Keterbatasan kapabilitas mitra (mitra) | 787000000000 | MEGA | 12/03/2019 22:08:49
PROJ1117 |  | PROJECT ELEKTRIKAL DAN ELEKTRONIK GEDUNG BIO FARMA 2 BANDUNG | SMART BUILDING | PEMBANGUNAN PERUMAHAN PT | PCS |  | null | HADI TRIYONO | SHEINI CHRISTY | PT Infrastruktur Telekomunikasi Indonesia (TELKOMINFRA) | 26-FEB-18 | 27-MAY-19 | 82.08 | 44.72 | -37.36 | LAG | 1.Delivery barang/jasa (mitra) | 20800000000 | BIG | 06/03/2019 16:56:27
PROJ1257 | LOP102059 | KFC 31 LOKASI WIFI ID + PROFILING | CONNECTIVITY | FASTFOOD INDONESIA | THS |  | null | SRI NURFALAH | RINO SUPRIADI PUTRA | PT Infomedia Nusantara | 01-JAN-19 | 31-DEC-19 | 41.8 | 55 | 13.2 | LEAD |  | 669600000 | REGULAR | 12/03/2019 10:04:00
PROJ1492 | LOP24865 | ORACLE ENTERPRISE BUSINESS SUITE (EBS) SUPPLY CHAIN MANAGEMENT`MODULE PT. PELNI (PERSERO) | APPLICATION | PELAYARAN NASIONAL INDONESIA (PELNI) PT | MLS |  |  | ADRID | NAWIN | SIGMA SOLUSI INTEGRASI | 06-MAR-18 | 08-MAR-19 | 100 | 71.2 | -28.8 | DELAY | 8.CR (perubahan yang belum terkendali) & amandemen (customer) | 8935000000 | ORDINARY | 12/03/2019 21:57:25
PROJ2161 | LOP105406 | PROYEK PENGADAAN MATERIAL MEKANIKAL, ELEKTRIKAL, ELEKTRONIK PROYEK PADINA APARTEMENT | SMART BUILDING | PT PATRA BANGUN PROPERTI | PCS | K.TEL.07-0292/HK.810/DES-00/2018 | null | HERU IRMAN |  | PT Sandhy PutraMakmur | 23-JUL-18 | 31-DEC-18 | 92.706 | 70.46 | -22.246 | DELAY | 1.Delivery barang/jasa (mitra) | 34875496682 | BIG | 12/03/2019 14:45:38
PROJ3296 | LOP108701 | PERANGKAT CCTV AREA HCC & JETTY RU II DUMAI | SMART BUILDING | PERTAMINA PT | ERS |  | null | HARI MULYA | REIKA ERMANSA | PT PINS Indonesia | 12-OCT-18 | 31-MAR-20 | 100 | 56.5 | -43.5 | LAG | 1.Delivery barang/jasa (mitra) | 7516950000 | ORDINARY | 11/03/2019 16:39:10
PROJ3594 | LOP109872 | PENGADAAN PENINGKATAN BUSINESS INTELEGENCE DI ATAS PLATFORM CLOUDERA (ATSCALE) | CPE DEVICES | BANK RAKYAT INDONESIA (PERSERO) | BMS-1 |  | null | ARIA OCTA | RUDY WIBOWO | PT Metra-Net | 27-NOV-18 | 27-MAY-19 | 91.62 | 94.43 | 2.81 | LAG | 2.Kesiapan lokasi ( customer) | 13600000000 | ORDINARY | 11/03/2019 15:06:45
PROJ4140 | LOP144181 | PENGADAAN LICENSE CLOUDERA UNTUK KEBUTUHAN ENTERPRISE DATA WAREHOUSE (EDW) | CPE DEVICES | BANK RAKYAT INDONESIA (PERSERO) | BMS-1 |  | null | ARIA OCTA | RUDY SETYO NUGROHO | PT Metra-Net | 31-DEC-18 | 31-JAN-19 |  | 0 |  | DELAY | 5.Keterlambatan SPK ke mitra (di awal) (Telkom) | 2763636364 | ORDINARY | 11/03/2019 14:48:27
PROJ4258 | LOP144611 | PENGADAAN MANAGED SERVICE OFFSITE DATA CENTER (ODC), DATA CENTER (DC) GTI RAGUNAN DAN TABANAN TAHAP 1(MENGACU PADA SPK B.79.P-PBJ/PIT/01/2019) | CPE DEVICES | BANK RAKYAT INDONESIA (PERSERO) | BMS-1 |  | null | RUDIONO | RUDY SETYO NUGROHO | PT Sigma Cipta Caraka | 23-JAN-19 | 30-MAY-19 | 91.18 | 71.99 | -19.19 | LAG | 1.Delivery barang/jasa (mitra) | 149500000000 | MEGA | 06/03/2019 16:44:57
PROJ3617 | LOP108934 | MERCURY PROJECT LAFARGE HOLCIM INDONESIA. | CONNECTIVITY | HOLCIM INDONESIA | MAS | K.TEL.11-0250/HK.810/DES-00/2018 | null | HARI MULYA | OCTORYZA PUTRA |  | 05-DEC-18 | 31-JAN-19 | 100 | 82.367 | -17.633 | DELAY |  | 19256400000 | ORDINARY | 11/03/2019 16:33:15
PROJ903 |  | PROJECT 5000 AKSES POINT WIFI PEGADAIAN | CONNECTIVITY | PEGADAIAN PT | FMS |  | null | DWI WIDYA SAKTI | ANDIKA PRATAMA PUTRA |  | 22-FEB-18 | 31-DEC-19 |  | 25 |  | LEAD |  | 18000000000 | ORDINARY | 02/01/2019 11:34:47
PROJ13 |  | PROJECT ERP SAP INALUM | APPLICATION | INDONESIA ASAHAN ALUMUNIUM | MAS |  |  | RISTYAWAN FAUZI MUBAROK | SIMON | PT Sigma Metrasys Solution | 01-JUL-15 | 24-AUG-18 | 100 | 100 | 0 | DELAY | 4.Keterlambatan BAST (customer) | 32284783041 | BIG | 12/02/2019 07:06:54
PROJ32 |  | PROJECT PANIC BUTTON ORCHARD PARK BATAM | SMART BUILDING | PODOMORO GROUP | PCS |  | null | IRWANDI | NOVI ANDRIYANI | PT PINS Indonesia, PT PINS Indonesia | 30-AUG-15 | 30-APR-18 | 100 | 75.78 | -24.22 | DELAY | 2.Kesiapan lokasi ( customer) | 2109703600 | ORDINARY | 12/03/2019 15:51:10
PROJ203 |  | ERP N-HOLDING | APPLICATION | PERKEBUNAN NUSANTARA III PT | MAS |  | null | NURUL HIDAYATI | ADRI SYAFMA PUTRA | PT Sigma Metrasys Solution | 17-AUG-16 | 30-JUN-19 | 83.804 | 81.3 | -2.504 | LAG | 8.CR (perubahan yang belum terkendali) & amandemen (customer) | 10888000000 | ORDINARY | 27/02/2019 20:12:49
PROJ217 |  | PROJECT MEKANIKAL & ELEKTRIKAL PEKERJAAN CINERE TERRACE SUITES - APARTMENT & CITYWALK | SMART BUILDING | METROPOLITAN TOWER | PCS |  | null | TEDDY AWALUDIN | SUNARTO AMSALOM SAIRO | PT PINS Indonesia, PT PINS Indonesia | 17-FEB-17 | 31-AUG-18 | 100 | 95.61 | -4.39 | DELAY | 8.CR (perubahan yang belum terkendali) & amandemen (customer) | 18568190000 | ORDINARY | 30/01/2019 11:50:03
PROJ235 |  | ROLL OUT I ERP PTPN IV (MEDAN) | APPLICATION | PERKEBUNAN NUSANTARA IV PT | MAS |  | null | NURUL HIDAYATI | SIMON | PT Sigma Metrasys Solution | 01-MAR-17 | 30-JUN-19 | 99.992 | 99.83 | -0.162 | LAG | 8.CR (perubahan yang belum terkendali) & amandemen (customer) | 55638090000 | MEGA | 27/02/2019 18:15:04
PROJ364 |  | IMPLEMENTASI ORACLE PRIMAVERA DI PT PAL INDONESIA | APPLICATION | PAL | IBS |  | null | NURUL HIDAYATI | I GUSTI BAGUS YOGISWARA GHEARTHA | SIGMA SOLUSI INTEGRASI | 28-FEB-17 | 31-DEC-18 | 99.996 | 88.1 | -11.896 | DELAY | 8.CR (perubahan yang belum terkendali) & amandemen (customer) | 3044996000 | ORDINARY | 27/02/2019 20:29:44
PROJ621 |  | PEKERJAAN PENATAAN KAWASAN GBK ZONA 1 | SMART BUILDING | ADHI KARYA PT | PCS |  | null | ADRID | DWI PUDJI IRAWATI | PT PINS Indonesia | 01-SEP-17 | 30-DEC-17 | 100 | 100 | 0 | DELAY | 4.Keterlambatan BAST (customer) | 19500000000 | ORDINARY | 12/03/2019 22:26:58
PROJ656 |  | PROJECT CCTV ORCHARD PARK BATAM | SMART BUILDING | PENGUSAHAAN DAERAH INDUSTRI PULAU BATAM PT | PCS |  | null | IRWANDI | AGUS WIDIANTARA | PT PINS Indonesia, PT PINS Indonesia | 13-OCT-17 | 30-MAR-18 | 100 | 89.5 | -10.5 | DELAY |  | 1468000000 | ORDINARY | 12/03/2019 15:45:20
PROJ659 |  | IMPLEMENTASI SISTEM ERP PT. HUTAMA KARYA (PERSERO) | APPLICATION | HUTAMA KARYA PT | PCS |  |  | RIKA AMALIA SASANTY | NURUL RIZKI UTAMI | PT Sigma Metrasys Solution | 25-OCT-17 | 25-MAY-19 | 91.67 | 98.48 | 6.81 | LAG | 4.Keterlambatan BAST (customer) | 14120376710 | ORDINARY | 13/11/2018 12:16:48
PROJ750 |  | ROLL OUT 3 PTPN XIV MAKASAR | APPLICATION | PERKEBUNAN NUSANTARA INDONESIA XIV, PT | MAS |  | null | NURUL HIDAYATI | NADIAH LIESTYASARI | PT Sigma Metrasys Solution | 01-OCT-17 | 30-JUN-19 | 100 | 92 | -8 | LAG | 8.CR (perubahan yang belum terkendali) & amandemen (customer) | 9172440000 | ORDINARY | 27/02/2019 19:54:27
PROJ751 |  | ROLL OUT 3 KPBN JAKARTA | APPLICATION | PERKEBUNAN NUSANTARA VII PT | MAS |  | null | NURUL HIDAYATI | ANWAR | PT Sigma Metrasys Solution | 01-OCT-17 | 30-JUN-19 | 100 | 99 | -1 | LAG | 8.CR (perubahan yang belum terkendali) & amandemen (customer) | 844830000 | REGULAR | 27/02/2019 20:21:43
PROJ977 |  | PEKERJAAN MEKANIKAL, ELEKTRIKAL & PLUMBING PROYEK TEKNOPLEX LIVING APARTMENT | SMART BUILDING | PT.MULTI KARYA UTAMA ABADI -BANDUNG TECHNOPLEX LIVING | PCS |  | null | TEUKU HAMIZUL | RADIAN SIGIT DWIANANTO | PT Infrastruktur Telekomunikasi Indonesia (TELKOMINFRA) | 31-OCT-17 | 31-MAY-19 | 95.91 | 32.308 | -63.602 | LAG | 2.Kesiapan lokasi ( customer) | 55000000000 | MEGA | 11/03/2019 20:23:51
PROJ1169 | LOP101909 | PENGADAAN JASA PENGEMBANG APLIKASI E-PAS & INFRASTRUKTUR PENDUKUNGNYA PT PUPUK SRIWIDJAJA PALEMBANG | APPLICATION | PUPUK SRIWIJAYA | MAS |  |  | RIKA AMALIA SASANTY | MUHAMMAD HANIS | PT Infomedia Nusantara | 23-MAR-18 | 28-DEC-18 | 100 | 81.5 | -18.5 | DELAY | 3.Perubahan desain/spek pelanggan (customer) | 523800000 | REGULAR | 28/02/2019 10:34:41
PROJ1646 | LOP103401 | PROYEK PEMBANGUNAN B RESIDENCE, SERPONG - TANGERANG PEKERJAAN ELEKTRONIK | SMART BUILDING | PT. MAJU GEMILANG SERPONG | PCS |  | null | NAZIRWAN, ST. M.KOM | SUNARTO AMSALOM SAIRO | PT PINS Indonesia, PT PINS Indonesia | 15-JAN-18 | 15-SEP-19 | 59.39 | 27.319 | -32.071 | LAG | 2.Kesiapan lokasi ( customer) | 17985000000 | ORDINARY | 13/03/2019 11:48:16
PROJ1877 | LOP104326 | PROJECT PEKERJAAN DIGITAL CORE PLATFORM DI PERUM PERURI | CPE DEVICES | PERURI PERUM | FMS | K.TEL.06-0826/HK.850/DES-A00000000/2018 | null | IRWANDI | WIJAYANTO | PT Sigma Metrasys Solution | 05-JUL-18 | 30-JAN-19 | 100 | 100 | 0 | DELAY | 1.Delivery barang/jasa (mitra) | 89318181818 | MEGA | 12/03/2019 15:38:02
PROJ1944 | LOP104864 | PENGADAAN JARINGAN DATA GRAHA INKA | CPE DEVICES | INKA | IBS |  | null | RUDIONO | FURI DIAH AYU HAPSARI | PT PINS Indonesia | 03-JUL-18 | 31-MAR-19 | 100 | 94.34 | -5.66 | LAG | 6.Masalah Administrasi & pembayaran mitra (Telkom) | 2585000000 | ORDINARY | 28/02/2019 13:08:31
PROJ2237 | LOP105044 | PEKERJAAN PEMBANGUNAN SMART BUILDING PADA KANTOR BARU DI BELAWAN PT. PELABUHAN INDONESIA I (PERSERO) | SMART BUILDING | PELINDO 1 | MLS |  | null | NAZIRWAN, ST. M.KOM | YETTI ASRI, SE | PT PINS Indonesia, PT PINS Indonesia, PT PINS Indonesia | 26-JUL-18 | 22-NOV-18 | 100 | 30.232 | -69.768 | DELAY | 2.Kesiapan lokasi ( customer) | 10288470610 | ORDINARY | 13/03/2019 11:29:03
PROJ2542 | LOP106618 | PENGADAAN APLIKASI PENDUKUNG PROGRAM PROMO BERKAH ENERGI PERTAMINA | APPLICATION | PERTAMINA PT | ERS | K.TEL.08-0615/HK.810/DES-00/2018 | null | HERU IRMAN |  | PT Finnet Indonesia, PT Sigma Metrasys Solution | 30-AUG-18 | 08-AUG-19 | 50 | 50 | 0 | LAG | 2.Kesiapan lokasi ( customer) | 22570000000 | BIG | 12/03/2019 14:36:40
PROJ3146 | LOP108542 | LAN & IPPBX FIELD SUBANG COLL PERTAMINA EP ASSET 3 SUBANG FIELD | SMART BUILDING | PERTAMINA PT | ERS |  | null | HADI TRIYONO | REIKA ERMANSA | PT Nusantara Compnet Integrator | 22-OCT-18 | 21-DEC-18 |  | 0 |  | DELAY | 2.Kesiapan lokasi ( customer) | 7735000000 | ORDINARY | 06/03/2019 16:40:20
PROJ3507 | LOP109718 | REVISI MITRA PENGADAAN JASA LAIN DISASTER RECOVERY CENTER (DRC) SAP S/4 HANA JASA MARGA (PERSERO) | CPE DEVICES | JASA MARGA (PERSERO) | TMS |  | null | ARIEF SUSILO WIBOWO | ERSYHAD PRABAWA ADIGUNA | PT Sigma Cipta Caraka, PT Sigma Metrasys Solution | 29-OCT-18 | 29-JAN-19 | 100 | 90 | -10 | DELAY | 2.Kesiapan lokasi ( customer) | 8024730000 | ORDINARY | 14/02/2019 12:06:36
PROJ3533 | LOP109736 | PEKERJAAN INSTALASI PUBLIC ADDRESSOR DAN INFRASTRUKTUR PENDUKUNG OPERASIONAL DI FIELD JATIBARANG DAN TAMBUN PT PERTAMINA EP ASSET 3 | SMART BUILDING | PERTAMINA PT | ERS |  | null | TEUKU HAMIZUL | REIKA ERMANSA | PT PINS Indonesia | 23-NOV-18 | 27-FEB-19 | 100 | 98.05 | -1.95 | DELAY |  | 1484746749 | ORDINARY | 11/03/2019 20:19:18
PROJ4018 | LOP143683 | PATRAJASA CIREBON - SMART TV DAN SHOWCASE MINI BARU | CPE DEVICES | HOTEL PATRAJASA | THS |  |  | TEUKU HAMIZUL | FEBRINA HANIFAH | PT PINS Indonesia | 28-DEC-18 | 28-MAR-19 | 78.804 | 100 | 21.196 | LAG |  | 1404922018 | ORDINARY | 11/03/2019 20:15:20
PROJ4177 | LOP144368 | SUPPLY AND INSTALLATION OF CCTV, PERSONAL COMPUTER, NOTEBOOK, AND LICENSE FOR PT NEW PRIOK CONTAINER TERMINAL ONE | CPE DEVICES | PT NEW PRIOK CONTAINER TERMINAL ONE | MLS |  | null | DODI IRAWAN | M. TEEZAR DWIPUTRA R | PT Sigma Cipta Caraka, PT Wave Communication Indonesia | 16-JAN-19 | 15-MAY-19 | 0 | 0 | 0 | LAG |  | 1875294586 | ORDINARY | 13/03/2019 14:14:10
PROJ4198 |  | WIFI.ID UNIVERSITAS NEGERI PADANG | CONNECTIVITY | UNIVERSITAS NEGERI PADANG | EMS |  |  | SRI NURFALAH | ARFAN SUATAN |  | 01-JAN-19 | 31-DEC-19 | 100 | 90 | -10 | LAG |  | 119350000 | REGULAR | 12/03/2019 10:02:26
PROJ379 |  | PROJECT WIFI.ID KFC | CONNECTIVITY | FASTFOOD INDONESIA | THS |  |  | SRI NURFALAH | ANAK AGUNG ARDHA CHANDRA DEWI |  | 01-JAN-17 | 31-DEC-18 | 100 | 75 | -25 | DELAY |  | 237000000 | REGULAR | 05/03/2019 08:49:41
PROJ386 |  | PROJECT WIFI.ID PIZZA HUT | CONNECTIVITY | MAP FOOD & BEVERAGE | THS |  | null | SRI NURFALAH | EVY YULIA RAMADHAN |  | 01-JAN-17 | 31-DEC-19 | 99.18 | 85 | -14.18 | LAG |  | 186000000 | REGULAR | 12/03/2019 10:04:47
PROJ29 |  | PROJECT GRAND TARUMA KARAWANG | SMART BUILDING | ADHI KARYA PT | PCS |  |  | TEDDY AWALUDIN | NOVI ANDRIYANI | PT PINS Indonesia | 09-MAY-14 | 31-DEC-18 | 100 | 99.7 | -0.3 | DELAY | 8.CR (perubahan yang belum terkendali) & amandemen (customer) | 2888000000 | ORDINARY | 30/01/2019 12:17:32
PROJ37 |  | PROJECT SMART BUILDING MARIGOLD NAVAPARK - BSD | SMART BUILDING | ADHI KARYA PT | PCS |  |  | TEDDY AWALUDIN |  | PT PINS Indonesia, PT PINS Indonesia | 05-FEB-16 | 31-DEC-18 | 99.83 | 35.57 | -64.26 | DELAY | 8.CR (perubahan yang belum terkendali) & amandemen (customer) | 16500000000 | ORDINARY | 30/01/2019 12:15:38
PROJ59 |  | PROJECT ICT FTTH GPON (VERTIKAL DAN HORIZONTAL) DI APARTMENT BINTARO ICON | SMART BUILDING | ADITYA TOA DEV / MENARA THAMRIN | PCS |  | null | ATAM RUSTAM | NADIAH LIESTYASARI | PT PINS Indonesia | 01-MAY-16 | 30-NOV-18 | 100 | 93.37 | -6.63 | DELAY | 1.Delivery barang/jasa (mitra) | 5744549322 | ORDINARY | 12/03/2019 00:34:29
PROJ60 | LOP105856 | PEKERJAAN SISTEM ELEKTRONIK 2 ( TELEPHONE, DATA, CCV, MATV, ACCESS CARD DAN VIDEO PHONE ) PROYEK MENTENG PARK APARTEMENT - JAKARTA | SMART BUILDING | AGUNG SEDAYU PROPERTINDO | IBS |  | ["K.TEL.1695\/HK.810\/DES-A1000000\/2016"] | AD STEFEN RATU EDA | FURI DIAH AYU HAPSARI | PT PINS Indonesia, PT PINS Indonesia | 02-MAY-16 | 31-DEC-18 |  | 85.66 |  | DELAY | 1.Delivery barang/jasa (mitra) | 19100000000 | ORDINARY | 06/03/2019 11:06:13
PROJ458 |  | PROJECT ELEKTRONIK APARTEMEN DI BORNEO BAY BALIKPAPAN | SMART BUILDING | PODOMORO GROUP | PCS | K.TEL.0617-0606/HK.810/DES-A1000000/2017 | null | PRAKOSA TRIWIBOWO | NOVI ANDRIYANI | PT PINS Indonesia, PT PINS Indonesia | 01-JUL-17 | 22-OCT-18 | 98.788 | 57.09 | -41.698 | DELAY | 2.Kesiapan lokasi ( customer) | 14181818000 | ORDINARY | 13/03/2019 14:42:47
PROJ2155 | LOP105438 | PENGADAAN ADMINISTRATIVE SERVICE ONLY PT. JALIN PEMBAYARAN NUSANTARA | CPE DEVICES | PT JALIN PEMBAYARAN NUSANTARA | BMS-1 |  | null | DODI IRAWAN | SUPADMI | PT Administrasi Medika | 09-AUG-18 | 08-JUL-21 | 79.92 | 45 | -34.92 | LAG | 1.Delivery barang/jasa (mitra) | 120000000 | REGULAR | 03/01/2019 14:27:25
PROJ2293 |  | PENGADAAN PENYEDIAAN JASA LAYANAN PAKET E-TICKETING PERUM DAMRI | APPLICATION | DAMRI PO | TMS |  | null | ARIEF SUSILO WIBOWO | ERSYHAD PRABAWA ADIGUNA | PT NUTECH INTEGRASI | 05-JUN-18 | 30-NOV-18 | 100 | 90 | -10 | DELAY | 2.Kesiapan lokasi ( customer) | 22461600000 | BIG | 11/03/2019 15:33:02
PROJ2392 | LOP104964 | PENGADAAN PEMBANGUNAN DATA CENTER KERETA COMMUTER INDONESIA | CPE DEVICES | KERETA COMMUTER INDONESIA | TMS |  |  | ARIEF SUSILO WIBOWO | VINO HARSADITYA SAPUTRA | PT Sigma Cipta Caraka | 13-AUG-18 | 31-OCT-18 | 100 | 99.81 | -0.19 | DELAY | 1.Delivery barang/jasa (mitra) | 1749000000 | ORDINARY | 21/02/2019 10:25:41
PROJ2487 | LOP106420 | PAKET PEMBANGUNAN DATA CENTER PT. INKA (PERSERO) | CPE DEVICES | INKA | IBS |  | null | RUDIONO | FURI DIAH AYU HAPSARI | PT Sigma Cipta Caraka | 16-AUG-18 | 31-MAR-19 | 94.63 | 88.52 | -6.11 | LAG | 3.Perubahan desain/spek pelanggan (customer) | 3624500000 | ORDINARY | 28/02/2019 13:26:27
PROJ2582 | LOP106719 | JASA MIGRASI PORT DARI LAYANAN VSAT KE MPLS UNTUK 134 LOKASI | CONNECTIVITY | BANK RAKYAT INDONESIA (PERSERO) | BMS-1 |  | null | NUR WIJAYANTO | RUDY SETYO NUGROHO | PT Multimedia Nusantara | 31-AUG-18 | 31-DEC-18 |  | 0 |  | DELAY |  | 81620000 | REGULAR | 13/03/2019 14:26:34
PROJ3041 | LOP108246 | PEMBANGUNAN DATA CENTER PT PERTAMINA EP ASSET 5 | CPE DEVICES | PERTAMINA PT | ERS | K.TEL.09-0739/HK.850/DES-ERS/2018 | null | IKA SADERA M | REIKA ERMANSA | PT Sigma Cipta Caraka | 20-SEP-18 | 18-JAN-19 |  | 0 |  | DELAY |  | 1497000000 | ORDINARY | 12/03/2019 15:13:12
PROJ3185 | LOP108406 | PENGADAAN MITRA PENGELOLA UNIT LAYANAN BPJS KETENAGAKERJAAN | CPE DEVICES | BPJS KETENAGAKERJAAN | HWS |  |  | ADRID | SUSILO IRAWAN | PT Infomedia Nusantara | 12-OCT-18 | 31-JAN-19 | 89 | 82.3 | -6.7 | DELAY | 1.Delivery barang/jasa (mitra) | 50000000000 | MEGA | 12/03/2019 21:51:26
PROJ3282 | LOP21842 | PAKET JASA IMPLEMENTASI SISTEM ENTERPRISE RESOURCE PLANNING (ERP) PT. PEGADAIAN | APPLICATION | PEGADAIAN PT | FMS |  | null | FAHMI RAHMANTHAHA NURDINSYAH | ANDIKA PRATAMA PUTRA | PT Sigma Metrasys Solution | 23-OCT-18 | 19-FEB-19 | 100 | 97.5 | -2.5 | DELAY |  | 177272727273 | MEGA | 11/03/2019 16:09:32
PROJ3284 | LOP108944 | PENGEMBANGAN DATA CENTER DAN DRC (KAPASITAS SERVER) UNTUK SERVER APLIKASI KERETA API INDONESIA | CPE DEVICES | KERETA API INDONESIA | TMS |  | null | ARIEF SUSILO WIBOWO | NURI FAJARIYANAH | PT Sigma Cipta Caraka | 06-NOV-18 | 03-FEB-19 | 82.5 | 70 | -12.5 | DELAY | 1.Delivery barang/jasa (mitra) | 9846000000 | ORDINARY | 11/03/2019 15:28:12
PROJ3385 | LOP109311 | PENGADAAN PENINGKATAN KAPASITAS CLUSTER CLOUDERA BIG DATA | CPE DEVICES | BANK RAKYAT INDONESIA (PERSERO) | BMS-1 |  | null | ARIA OCTA | RUDY SETYO NUGROHO | PT Metra-Net | 30-OCT-18 | 30-APR-19 | 99.37 | 0 | -99.37 | LAG | 2.Kesiapan lokasi ( customer) | 11220000000 | ORDINARY | 11/03/2019 15:11:47
PROJ4152 | LOP144253 | SEWA AKSES CONTROL SYSTEM DI PT PERTAMINA (PERSERO) RU IV CILACAP | SMART BUILDING | PERTAMINA PT | ERS |  |  | HARI MULYA | REIKA ERMANSA | PT PINS Indonesia | 21-JAN-19 | 22-JAN-19 |  | 0 |  | DELAY |  | 13270000046 | ORDINARY | 01/02/2019 09:02:48
PROJ4527 |  | LINK INTERNET OUTLET BTN | CONNECTIVITY | BANK TABUNGAN NEGARA (PERSERO) | BMS-1 |  |  | HARI MULYA | DWI ARYANTO SULISTYO |  | 15-OCT-18 | 15-OCT-19 |  | 0 |  | LEAD |  | 39330000 | REGULAR | 05/03/2019 15:23:47
PROJ27 |  | PROJECT CEMINDO TOWER | SMART BUILDING | CEMINDO TOWER | PCS |  |  | NAZIRWAN, ST. M.KOM | MUHAMMAD SIDIK | PT Telkom Akses | 01-SEP-14 | 31-DEC-17 | 100 | 100 | 0 | DELAY | 4.Keterlambatan BAST (customer) | 13900000000 | ORDINARY | 11/03/2019 10:40:24
PROJ36 |  | PROJECT SMART BUILDING HOTEL KEMPINSKI | SMART BUILDING | GRAHA ALAM LESTARI | PCS |  | null | AD STEFEN RATU EDA | GERRY ROY MANAEK SIAHAAN | PT PINS Indonesia, PT PINS Indonesia | 11-FEB-16 | 30-APR-19 | 98.309 | 84.46 | -13.849 | LAG | 11.Komitmen mitra(termasuk deal harga)(mitra) | 23000000000 | BIG | 06/03/2019 11:25:55
PROJ442 |  | PROJECT PROPRIETARY LOYALTY PROGRAM PT PERTAMINA PERSERO | APPLICATION | PERTAMINA PT | ERS |  | null | HERU IRMAN |  | PT Finnet Indonesia | 11-JUL-17 | 11-JUL-22 | 63.28 | 62 | -1.28 | LAG | 8.CR (perubahan yang belum terkendali) & amandemen (customer) | 61862540000 | MEGA | 12/03/2019 15:04:20
PROJ743 |  | PENGADAAN SEWA EDC PERUNTUKAN BANSOS BANK BTN | CPE DEVICES | BANK TABUNGAN NEGARA (PERSERO) | BMS-1 |  | null | MUTTAQIN NASUTION | DISKAERI | PT Sigma Cipta Caraka, PT Sigma Cipta Caraka | 22-SEP-17 | 31-DEC-18 | 100 | 70 | -30 | DELAY | 2.Kesiapan lokasi ( customer) | 7265454545 | ORDINARY | 13/03/2019 11:20:24
PROJ753 |  | PEKERJAAN INFRASTRUKTUR GPON GALAXY MALL 3 SURABAYA | SMART BUILDING | SINAR GALAXI | TDS |  |  | ATAM RUSTAM | SUCI ERNANINGTYAS | PT PINS Indonesia, PT PINS Indonesia | 17-NOV-17 | 30-NOV-18 | 100 | 89.55 | -10.45 | DELAY | 1.Delivery barang/jasa (mitra) | 2300000000 | ORDINARY | 12/03/2019 00:14:08
PROJ771 |  | PROJECT E-DAPEM TASPEN | APPLICATION | TASPEN PT | HWS |  | null | ZAKY AHMAD | ELMAN HASIHOLAN SIANTURI, IR.MT. | PT Sigma Cipta Caraka | 17-OCT-17 | 11-FEB-19 | 98.29 | 99 | 0.71 | DELAY | 3.Perubahan desain/spek pelanggan (customer) | 585728682000 | MEGA | 27/02/2019 11:30:16
PROJ790 |  | PEKERJAAN SEWA OUTSOURCING 300 EDC DAN PERANGKAT PENDUKUNG OPERASIONAL BANK SUMSEL BABEL (BATCH 1) | CPE DEVICES | BPD SUMATERA SELATAN (BANK SUMSEL) | BMS-2 |  | null | HASBUR GHALI | EVI NOVIARNI | PT PINS Indonesia | 30-OCT-17 | 30-OCT-20 | 100 | 97.5 | -2.5 | LAG | 8.CR (perubahan yang belum terkendali) & amandemen (customer) | 3518405000 | ORDINARY | 12/03/2019 14:31:06
PROJ824 |  | PROJECT PEKERJAAN JASA IMPLEMENTASI ENTERPRISE RESOURCE PLANNING (ERP) DI PERUM PERURI | APPLICATION | PERURI PERUM | FMS |  | null | IRWANDI | WIJAYANTO | PT Sigma Metrasys Solution | 04-JAN-18 | 28-FEB-19 | 97.25 | 95.8 | -1.45 | DELAY | 1.Delivery barang/jasa (mitra) | 54329137800 | MEGA | 12/03/2019 15:42:37
PROJ829 |  | PROJECT APARTEMEN GRAND JATI JUNCTION MEDAN | SMART BUILDING | PEMBANGUNAN PERUMAHAN PT | PCS |  | null | NAZIRWAN, ST. M.KOM | RADIAN SIGIT DWIANANTO | PT Graha Sarana Duta | 01-SEP-17 | 31-DEC-18 | 100 | 67.715 | -32.285 | DELAY | 8.CR (perubahan yang belum terkendali) & amandemen (customer) | 51400000000 | MEGA | 13/03/2019 12:11:53
PROJ928 | LOP25066 | PENGADAAN SEWA 12.000 UNIT EDC BNI UNTUK PT. BRINGIN GIGANTARA | CPE DEVICES | BANK RAKYAT INDONESIA (PERSERO) | BMS-1 |  |  | RUDIONO | RUDY WIBOWO | PT Sigma Cipta Caraka | 15-JAN-18 | 31-DEC-19 | 100 | 34.13 | -65.87 | LAG | 2.Kesiapan lokasi ( customer) | 57000000000 | MEGA | 09/01/2019 16:12:01
PROJ1043 | LOP31751 | PREMISES AND SISTEM TELEMARKETING PT BNI LIFE INSURANCE | CPE DEVICES | BNI LIFE | HWS |  | null | HERU IRMAN | MOH. ZAINUL ARIFIN | PT Infomedia Nusantara | 01-MAR-18 | 28-FEB-19 | 100 | 99.73 | -0.27 | DELAY | 3.Perubahan desain/spek pelanggan (customer) | 9389952000 | ORDINARY | 12/03/2019 14:55:29
PROJ1285 | LOP25267 | PEKERJAAN ELEKTRONIK DAN ELEKTRIKAL DI APARTEMEN ZAMZAM TOWER DEPOK | SMART BUILDING | WIJAYA KARYA | PCS |  |  | TEDDY AWALUDIN | NOVI ANDRIYANI | PT Infrastruktur Telekomunikasi Indonesia (TELKOMINFRA) | 01-JAN-18 | 30-NOV-18 | 100 | 96.57 | -3.43 | DELAY | 1.Delivery barang/jasa (mitra) | 10200000000 | ORDINARY | 30/01/2019 11:21:53
PROJ3384 | LOP109217 | HOTEL NEXA MAKASSAR - PENYEDIAAN LAYANAN INFRASTRUKTUR DAN ICT SOLUSION (PERJANJIAN PERPANJANGAN) | SMART BUILDING | HOTEL NEXA MAKASSAR | THS |  | null | ADITYA | ANDI ABDUL WARIS | PT PINS Indonesia | 24-OCT-18 | 24-MAR-19 | 84.09 | 87.88 | 3.79 | LAG |  | 1650183093 | ORDINARY | 08/03/2019 21:00:25
PROJ3724 | LOP109438 | PENGADAAN JASA KONSULTAN PEMBUATAN SISTEM BACKEND E-TICKETING TRANSJAKARTA | APPLICATION | PT. TRANSPORTASI JAKARTA | TMS | K.TEL.01-0463/HK.850/DES-MLS/2019 | null | DODI IRAWAN | ERSYHAD PRABAWA ADIGUNA | PT NUTECH INTEGRASI | 17-DEC-18 | 01-APR-19 | 0 | 0 | 0 | LAG |  | 2647082111 | ORDINARY | 13/03/2019 14:27:08
PROJ3831 | LOP108872 | PENYEDIAAN IMPLEMENTASI IT DRC (IT DISASTER RECOVERY CENTER) PT KRAKATAU STEEL (PERSERO) TBK | CPE DEVICES | KRAKATAU STEEL | TDS |  |  | HADI TRIYONO | MHM. THOHIRUN | PT Sigma Cipta Caraka | 31-OCT-18 | 28-FEB-19 | 100 | 0 | -100 | DELAY | 2.Kesiapan lokasi ( customer) | 11100000000 | ORDINARY | 08/01/2019 15:06:10
PROJ4197 |  | WIFI.ID DAN CONNECTIVITY J.CO | CONNECTIVITY | JOHNY ANDREAN GROUP | THS |  |  | SRI NURFALAH | EVY YULIA RAMADHAN |  | 01-JAN-19 | 31-DEC-19 | 38.5 | 55 | 16.5 | LEAD |  | 2527200000 | ORDINARY | 12/03/2019 10:03:20
PROJ30 |  | PROJECT PEKERJAAN SALURAN PENANGGAL BAWAH TANAH DI PROYEK BOULEVARD BUSINESS CENTER | SMART BUILDING | ADHI KARYA PT | PCS |  | null | IRWANDI | MUHAMMAD SIDIK | PT Telkom Akses | 19-NOV-14 | 31-JUL-17 | 100 | 62.59 | -37.41 | DELAY | 2.Kesiapan lokasi ( customer) | 472727273 | REGULAR | 12/03/2019 15:53:11
PROJ35 |  | PROJECT PAKET PEKERJAAN ELEKTRONIK UNTUK TUNJUNGAN PLAZA 6 | SMART BUILDING | PAKUWON JATI | PCS |  | null | AD STEFEN RATU EDA | YAFRINO, ST, M.M | PT PINS Indonesia, PT PINS Indonesia | 12-JAN-16 | 31-MAR-19 | 100 | 55.155 | -44.845 | LAG | 1.Delivery barang/jasa (mitra) | 16640000000 | ORDINARY | 29/01/2019 15:46:30
PROJ89 |  | ICT FTTH GPON ANANDAMAYA RESIDENCE | SMART BUILDING | ADHI KARYA PT | PCS |  | null | ATAM RUSTAM | SHERA MAYANGSARI SUWITO | PT PINS Indonesia, PT PINS Indonesia | 28-JUL-16 | 17-NOV-18 | 100 | 94.15 | -5.85 | DELAY | 1.Delivery barang/jasa (mitra) | 2285000000 | ORDINARY | 12/03/2019 00:26:35
PROJ204 |  | PROJECT RESUNAMI GRAND SENTRALAND KARAWANG | SMART BUILDING | PEMBANGUNAN PERUMAHAN PT | PCS |  |  | TEUKU HAMIZUL | RADIAN SIGIT DWIANANTO | PT Infomedia Nusantara, PT Infomedia Nusantara, PT Infomedia Nusantara | 31-OCT-16 | 30-JUN-18 | 99.997 | 82.009 | -17.988 | DELAY | 3.Perubahan desain/spek pelanggan (customer) | 23500000000 | BIG | 11/03/2019 20:27:31
PROJ779 |  | PROJECT CORE INSURANCE SYSTEM ASKRINDO | APPLICATION | ASURANSI KREDIT INDONESIA | HWS |  | null | ZAKY AHMAD | JOKO PADANG RAHINO | PT Sigma Cipta Caraka, PT Sigma Cipta Caraka | 14-NOV-17 | 20-DEC-19 | 98.51 | 61.6 | -36.91 | LAG | 8.CR (perubahan yang belum terkendali) & amandemen (customer) | 10792188000 | ORDINARY | 12/03/2019 17:06:03
PROJ2398 |  | PEKERJAAN ELEKTRONIK PROJEK TRANS PARK BEKASI | SMART BUILDING | ADHI KARYA PT | PCS |  | null | IMAM ZAHIR | DWI PUDJI IRAWATI | PT PINS Indonesia | 23-AUG-18 | 31-DEC-19 |  | 0 |  | LEAD |  | 20300000156 | BIG | 29/01/2019 11:34:20
PROJ2572 | LOP106605 | PEMBANGUNAN INFRASTRUKTUR FIBER OPTIK TAHAP 2 - SINERGI OPTIMA NALADHIPA | SMART BUILDING | SINERGI OPTIMA NALADHIPA | THS |  |  | TEUKU HAMIZUL | R. WIDHA ANDI PARMOKO | PT Patra Telekomunikasi Indonesia | 02-AUG-18 | 02-JUN-19 | 32.866 | 17.81 | -15.056 | LAG |  | 32654000000 | BIG | 11/03/2019 20:09:42
PROJ2585 | LOP106715 | JASA MIGRASI PORT DARI LAYANAN VSAT KE MPLS DI 99 REMOTE EX PROVIDER CSM | CONNECTIVITY | BANK RAKYAT INDONESIA (PERSERO) | BMS-1 | K.TEL.04-0090/HK.850/DES-BMS1/2018 | null | NUR WIJAYANTO | RUDY SETYO NUGROHO | PT Multimedia Nusantara | 31-AUG-18 | 31-DEC-18 |  | 0 |  | DELAY |  | 62260000 | REGULAR | 13/03/2019 14:20:49
PROJ2643 | LOP106895 | CONTACT CENTER PT. ANUGERAH PHARMINDO LESTARI | CPE DEVICES | ANUGERAH PHARMINDO LESTARI | HWS |  | null | MUTTAQIN NASUTION | QUVIN NOLA PRIHANDANI | PT Infomedia Nusantara | 27-AUG-18 | 07-JAN-19 | 100 | 91.5 | -8.5 | DELAY | 3.Perubahan desain/spek pelanggan (customer) | 2609196400 | ORDINARY | 01/02/2019 15:28:57
PROJ2695 |  | PENGADAAN PEREMAJAAN PERANGKAT VIDEO CONFERENCE PT PEGADAIAN (PERSERO) TAHUN 2018 | CPE DEVICES | PEGADAIAN PT | FMS | K.TEL.08-0614/HK.810/DES-00/2018 | null | FAHMI RAHMANTHAHA NURDINSYAH | ANDIKA PRATAMA PUTRA | PT Sigma Metrasys Solution | 21-AUG-18 | 27-NOV-18 | 100 | 99.07 | -0.93 | DELAY | 1.Delivery barang/jasa (mitra) | 5363636364 | ORDINARY | 11/03/2019 16:21:44
PROJ3062 | LOP108175 | PENGADAAN UPGRADE 230 SERVER DI DC GTI DAN TABANAN UNTUK PT. BANK RAKYAT INDONESIA (PERSERO), TBK | CPE DEVICES | BANK RAKYAT INDONESIA (PERSERO) | BMS-1 |  | null | RUDIONO | RUDY SETYO NUGROHO | PT Signet Pratama | 12-OCT-18 | 30-APR-19 |  | 97.35 |  | LEAD | 3.Perubahan desain/spek pelanggan (customer) | 69027000000 | MEGA | 28/02/2019 13:34:40
PROJ3107 | LOP108271 | PEKERJAAN SISTEM ELEKTRONIK PROYEK SEDAYU CITY APARTEMEN @ KELAPA GADING APARTEMENT JAKARTA | SMART BUILDING | AGUNG SEDAYU PROPERTINDO | IBS |  | null | HADI TRIYONO | FAHMI MUHAMMAD HUSIN | PT PINS Indonesia | 01-OCT-18 | 25-DEC-19 | 37.4 | 6.751 | -30.649 | LAG | 2.Kesiapan lokasi ( customer) | 18984900000 | ORDINARY | 06/03/2019 16:48:12
PROJ3619 | LOP109961 | SEWA STORAGE DC & DRC BPJS KETENAGAKERJAAN | CPE DEVICES | BPJS KETENAGAKERJAAN | HWS | K.TEL.12-0121/HK.850/DES-HWS/2018 | null | MUTTAQIN NASUTION | SUSILO IRAWAN | PT Sigma Cipta Caraka | 03-DEC-18 | 01-JAN-19 | 100 | 85 | -15 | DELAY | 5.Keterlambatan SPK ke mitra (di awal) (Telkom) | 2195000004 | ORDINARY | 12/03/2019 16:44:55
PROJ4020 | LOP143678 | PENYEMPURNAAN GEDUNG AOCC | CPE DEVICES | ANGKASA PURA II (PERSERO) - BUISH | TMS | - | null | RISTYAWAN FAUZI MUBAROK | HIDAYAT KURNIAWAN | PT PINS Indonesia | 17-DEC-18 | 16-JUN-19 | 36.92 | 33.195 | -3.725 | LAG |  | 24093860273 | BIG | 05/03/2019 13:40:10
PROJ4301 | LOP144617 | PENGADAAN KOMPUTER DAN LAPTOP UTBK SBMPTN UNIVERSITAS DIPONEGORO 2019 | CPE & OTHERS | UNIVERSITAS DIPONEGORO SEMARANG | EMS |  | null | HADI TRIYONO | INDAH ARFIYATI KURNIA | PT PINS Indonesia | 27-DEC-18 | 30-APR-19 |  | 0 |  | LEAD |  | 9418572727 | ORDINARY | 06/03/2019 15:43:46
PROJ4374 | LOP144731 | PENYEDIAAN LAYANAN TELKOMSOLUTION DI LINGKUNGAN TIARA MARGA TRAKINDO GROUP | CPE & OTHERS | TIARA MARGA TRAKINDO | DTS |  | null | NAZIRWAN, ST. M.KOM | MAMAN ROCHAMAN | PT Teltranet Aplikasi Solusi (Telkom Telstra) | 01-FEB-19 | 31-JAN-24 |  | 0 |  | LEAD |  | 75824743560 | MEGA | 06/03/2019 11:22:58
PROJ4470 | LOP150395 | PENGADAAN MESIN EDC - 10.600 UNIT (MENGACU PADA SPK PFA/3.2/013) | CPE & OTHERS | BANK NEGARA INDONESIA 46TBK(BNI 46) | BMS-1 | K.TEL.01-0277/HK.850/ DES-00/2019 | null | HASBUR GHALI | BAKTI MUDIAZKO | SWADHARMA SARANA INFORMATIKA | 10-JAN-19 | 19-APR-19 | 84.94 | 0 | -84.94 | LAG | 5.Keterlambatan SPK ke mitra (di awal) (Telkom) | 19184940000 | ORDINARY | 12/03/2019 11:24:20
PROJ385 |  | PROJECT WIFI.ID STARBUCK | CONNECTIVITY | MAP FOOD & BEVERAGE | THS |  |  | SRI NURFALAH | EVY YULIA RAMADHAN |  | 01-JAN-17 | 31-DEC-18 | 100 | 95 | -5 | DELAY |  | 480000000 | REGULAR | 05/03/2019 08:49:03
PROJ375 |  | PROJECT WIFI.ID BANK RAKYAT INDONESIA | CONNECTIVITY | BANK RAKYAT INDONESIA (PERSERO) | BMS-1 |  |  | SRI NURFALAH | RUDY SETYO NUGROHO |  | 01-JAN-17 | 31-DEC-18 | 100 | 88 | -12 | DELAY |  | 138772727 | REGULAR | 12/03/2019 10:16:23
PROJ141 |  | PROJECT SEAT MANAGEMENT PT. PELABUHAN INDONESIA (PELINDO) III | CPE DEVICES | PELINDO III | MLS |  |  | TEDDY AWALUDIN | RIFANDA PUTRI INDRESWARI | PT PINS Indonesia | 01-JAN-17 | 31-DEC-19 | 82.25 | 74.37 | -7.88 | LAG | 3.Perubahan desain/spek pelanggan (customer) | 13868640000 | ORDINARY | 30/01/2019 11:51:38
PROJ367 |  | LAYANAN INFOKOM MODERENISASI JARINGAN GRAND INDONESIA | SMART BUILDING | GRAND INDONESIA | PCS |  |  | TEDDY AWALUDIN | NOVI ANDRIYANI | PT Bangtelindo | 01-DEC-16 | 31-DEC-18 | 100 | 100 | 0 | DELAY | 1.Delivery barang/jasa (mitra) | 6685966305 | ORDINARY | 30/01/2019 11:46:02
PROJ457 |  | PROJECT GPON ICT DI CIPUTRA INTERNASIONAL | SMART BUILDING | CIPUTRA WORLD JAKARTA | PCS |  |  | IRWANDI | GERRY ROY MANAEK SIAHAAN | PT PINS Indonesia | 02-NOV-16 | 31-DEC-17 | 69.82 | 89.42 | 19.6 | DELAY | 2.Kesiapan lokasi ( customer) | 5336000000 | ORDINARY | 07/12/2018 09:48:09
PROJ745 |  | ROLL OUT 2 PTPN 1 ACEH | APPLICATION | PERKEBUNAN NUSANTARA I PT | MAS |  | null | NURUL HIDAYATI | AGUS FRIADI | PT Sigma Metrasys Solution | 01-OCT-17 | 30-JUN-19 | 80.4 | 92 | 11.6 | LAG | 8.CR (perubahan yang belum terkendali) & amandemen (customer) | 12793140000 | ORDINARY | 27/02/2019 17:27:30
PROJ1275 | LOP102281 | PAKET SISTEM ELEKTRONIK APARTEMENT TOWER 1, HOTEL DAN MALL,PROYEK GREEN SEDAYU TAMAN PALEM JAKARTA | SMART BUILDING | AGUNG SEDAYU PROPERTINDO | IBS |  | null | HARI MULYA | FAHMI MUHAMMAD HUSIN | PT PINS Indonesia, PT PINS Indonesia | 26-MAR-18 | 26-MAR-19 | 92.28 | 20.594 | -71.686 | LAG | 1.Delivery barang/jasa (mitra) | 26124999999 | BIG | 28/01/2019 21:58:47
PROJ1680 |  | ICT LIVING WORLD PEKANBARU (PT TIGA DUA DELAPAN - CC KAWAN LAMA GROUP) | SMART BUILDING | KAWAN LAMA SEJAHTERA | TDS |  | null | ATAM RUSTAM | YULISTIKA RAHAYU | PT Telkom Akses, PT Telkom Akses | 23-MAR-18 | 30-NOV-18 | 100 | 100 | 0 | DELAY |  | 1110000000 | ORDINARY | 12/03/2019 00:05:08
PROJ2669 | LOP107004 | PENGADAAN KONEKSI DIGITAL UNTUK PASSENGER EXIT SURVEY - BPS | APPLICATION | PENGELOLA STATISTIK DISTRIBUSI DAN JASA | THS |  | null | IMAM ZAHIR | R. WIDHA ANDI PARMOKO | PT Metra Digital Media | 27-AUG-18 | 31-MAR-19 |  | 100 |  | LEAD | 10.Keterbatasan kapabilitas mitra (mitra) | 5681850000 | ORDINARY | 12/03/2019 15:32:32
PROJ2748 | LOP107405 | PENGADAAN IMPLEMENTASI DIGITALISASI KFTD (PLATFORM E-DISTRIBUTION) UNTUK PT KIMIA FARMA | APPLICATION | KIMIA FARMA PT | HWS |  | null | ZAKY AHMAD | MELANY ULFA | PT Sigma Cipta Caraka | 18-DEC-18 | 20-SEP-19 |  | 6 |  | LEAD | 6.Masalah Administrasi & pembayaran mitra (Telkom) | 10476226900 | ORDINARY | 03/03/2019 16:34:36
PROJ2802 | LOP107558 | PERMINTAAN EDC TAMBAHAN UNTUK LELANG PENGADAAN SEWA OUTSOURCING EDC DAN PERANGKAT PENDUKUNGNYA PT. BPD SUMATERA SELATAN DAN BANGKA BELITUNG | CPE DEVICES | BANK SUMSEL BABEL | BMS-2 | K.TEL.11-0948/HK.810/DES-BMS2/2017 | null | HASBUR GHALI |  | PT PINS Indonesia | 30-MAY-18 | 30-OCT-20 | 0 | 0 | 0 | LAG | 3.Perubahan desain/spek pelanggan (customer) | 4168260000 | ORDINARY | 13/03/2019 15:36:10
PROJ3620 | LOPUP361 | PENGEMBANGAN DASHBOAD MIS | APPLICATION | PT SARANA MULTI INFRASTRUKTUR (PERSERO) | FMS | K.TEL.11-0775/HK.810/DES-FMS/2018 | null | RIKA AMALIA SASANTY | DJOKO SUHARTONO | PT Sigma Cipta Caraka | 13-DEC-18 | 13-SEP-19 | 30.7 | 17 | -13.7 | LAG | 1.Delivery barang/jasa (mitra) | 750000000 | REGULAR | 13/03/2019 15:50:35
PROJ3710 | LOP110338 | INSTALASI DAN SEWA PERANGKAT DATA CENTER DI PT PERTAMINA EP ASSET 1 JAMBI | CPE DEVICES | PERTAMINA PT | ERS |  |  | ADRID | REIKA ERMANSA | PT Sigma Cipta Caraka | 07-DEC-18 | 07-MAR-19 | 27.06 | 19.73 | -7.33 | DELAY | 11.Komitmen mitra(termasuk deal harga)(mitra) | 6250000000 | ORDINARY | 12/03/2019 21:11:44
PROJ3908 | LOP109840 | PROJECT UPGRADE HARDWARE DATA CENTER PUPUK DI DC SENTUL | CPE & OTHERS | PUPUK INDONESIA HOLDING COMPANY | MAS |  | null | FAHMI RAHMANTHAHA NURDINSYAH | OCTORYZA PUTRA | PT Sigma Cipta Caraka | 17-DEC-18 | 24-FEB-19 |  | 0 |  | DELAY |  | 11360000000 | ORDINARY | 11/03/2019 16:05:10
PROJ3912 | LOP107362 | WASKITA - ERP SAP PAKET LISENSI | CPE DEVICES | WASKITA KARYA | PCS | K.TEL.12-0523/HK.810/ DES-00/2018 | null | RIKA AMALIA SASANTY | FIKA FARIYANDI | PT Sigma Metrasys Solution | 17-DEC-18 | 18-DEC-19 | 89.27 | 88 | -1.27 | LAG | 1.Delivery barang/jasa (mitra) | 22000000000 | BIG | 13/03/2019 15:45:59
PROJ4000 | LOP143616 | EKSTERNAL DEDICATED HOSTING SERVICE PERTAMINA HULU MAHAKAM | CPE DEVICES | PERTAMINA PT | ERS |  | null | IKA SADERA M | REIKA ERMANSA | PT Sigma Cipta Caraka | 01-JAN-19 | 31-MAR-19 | 0 | 0 | 0 | LAG |  | 2142498000 | ORDINARY | 13/03/2019 07:40:04
PROJ4006 | LOP143645 | JASA KONSULTAN APLIKASI TALENT MANAGEMENT SYSTEM | APPLICATION | TAMBANG BATU BARA BUKIT ASAM PT | ERS |  | null | ARIA OCTA | MUHAMMAD HANIS | PT Sigma Cipta Caraka | 02-JAN-19 | 01-JUL-19 |  | 0 |  | LEAD |  | 2454545495 | ORDINARY | 11/03/2019 14:55:40
PROJ4058 | LOP143858 | PENYEDIAAN JARINGAN KOMUNIKASI DAN MANAGED SERVICE SDWAN |  | FEDERAL INTERNATIONAL FINANCE (FIF) | FMS |  | null | KRSHNA SULANJANA | CINDY ARINI | PT Teltranet Aplikasi Solusi (Telkom Telstra) | 09-JAN-19 | 09-JAN-20 |  | 0 |  | LEAD |  | 113284000000 | MEGA | 12/03/2019 16:02:12
PROJ4590 | LOP110476 | PEKERJAAN TICKETING SYSTEM ENVIRONMENT PT ASDP INDONESIA FERRY (PERSERO) | CPE & OTHERS | ANGKUTAN SUNGAI DANAU DAN PENYEBERANGAN PT (ASDP) | MLS |  | null | ARIA OKTA CAHYADI | IDHAM | PT NUTECH INTEGRASI | 12-MAR-19 | 13-MAR-19 |  | 0 |  | DELAY |  | 165447509220 | MEGA | 13/03/2019 10:51:51
PROJ3528 |  | DELIVERY LAYANAN DATIN FIBER OPTIC UNTUK PT INDOMARCO PRISMATAMA (INDOMARET GROUP) | CONNECTIVITY | INDOMARCO PRISMATAMA 2 | TDS |  |  | AGUS SOLEH | SYAFRIANDI |  | 21-NOV-18 | 31-DEC-18 |  | 0 |  | DELAY |  | 0 | REGULAR | 27/11/2018 20:08:41
PROJ207 |  | WIFI.ID ANGKASA PURA I (NGURAH RAI) TAHAP 2 | CONNECTIVITY | ANGKASAPURA I | TMS |  |  | SRI NURFALAH | ONHI YULIARTI SEMARA |  | 01-JAN-17 | 31-DEC-18 | 100 | 88 | -12 | DELAY |  | 2394000000 | ORDINARY | 12/03/2019 10:21:19
PROJ2179 |  | LAYANAN MIGRASI VSAT KE VPN IP PT. PEGADAIAN | CONNECTIVITY | PEGADAIAN PT | FMS |  |  | FACHRI | ANDIKA PRATAMA PUTRA |  | 01-JUL-18 | 31-DEC-18 |  | 0 |  | DELAY |  | 248640300000 | MEGA | 06/11/2018 14:12:10
PROJ7 |  | PROJECT FTTH DUKUH GOLF KEMAYORAN BOUGENVILLE | SMART BUILDING | AGUNG SEDAYU PROPERTINDO | IBS |  | null | PRAKOSA TRIWIBOWO | FAHMI MUHAMMAD HUSIN | PT PINS Indonesia, PT PINS Indonesia | 18-SEP-14 | 30-SEP-16 | 99.986 | 100 | 0.014 | DELAY | 4.Keterlambatan BAST (customer) | 19043050000 | ORDINARY | 13/03/2019 14:49:52
PROJ26 |  | PROJECT SMART BUILDING SENTRALAND SEMARANG | SMART BUILDING | PERUMNAS PERUM | PCS |  |  | HADI TRIYONO | RADIAN SIGIT DWIANANTO | PT PINS Indonesia, PT PINS Indonesia | 16-JAN-15 | 31-MAR-18 | 100 | 87.182 | -12.818 | DELAY | 1.Delivery barang/jasa (mitra) | 4129738470 | ORDINARY | 04/01/2019 16:51:51
PROJ137 |  | PROJECT JASA KONSULTASI PENDAMPINGAN ICT PT. PAL INDONESIA (PERSERO) | APPLICATION | PAL | IBS |  | null | NURUL HIDAYATI | I GUSTI BAGUS YOGISWARA GHEARTHA | PT Sigma Cipta Caraka | 01-DEC-16 | 31-DEC-18 | 100 | 67 | -33 | DELAY | 8.CR (perubahan yang belum terkendali) & amandemen (customer) | 1350000000 | ORDINARY | 27/02/2019 20:42:53
PROJ405 |  | PROJECT PENGADAAN DAN PEMASANGAN GATE BARRIER SELURUH GERBANG CLUSTER PROYEK ORCHARD PARK BATAM | SMART BUILDING | PODOMORO GROUP | PCS |  | null | IRWANDI | NOVI ANDRIYANI | PT PINS Indonesia, PT PINS Indonesia | 01-APR-17 | 01-APR-18 | 100 | 88.58 | -11.42 | DELAY | 2.Kesiapan lokasi ( customer) | 1000000000 | ORDINARY | 12/03/2019 15:48:46
PROJ429 |  | PEKERJAAN ELEKTRONIKA DAN GPON PROYEK GALLERIA VIVO MALL SENTUL | SMART BUILDING | ADHIBALADIKA AGUNG | PCS |  | null | AD STEFEN RATU EDA | HELVIANA | PT PINS Indonesia, PT PINS Indonesia | 24-MAY-17 | 31-AUG-18 | 93.2 | 81.823 | -11.377 | DELAY | 1.Delivery barang/jasa (mitra) | 12500000000 | ORDINARY | 06/03/2019 11:20:50
PROJ449 |  | PURI MANSION APARTMENT | SMART BUILDING | AGUNG SEDAYU PROPERTINDO | IBS |  | null | HERU IRMAN | FAHMI MUHAMMAD HUSIN | PT PINS Indonesia | 10-JUL-17 | 07-OCT-17 | 100 | 84 | -16 | DELAY | 3.Perubahan desain/spek pelanggan (customer) | 8301000000 | ORDINARY | 12/03/2019 14:59:03
PROJ744 |  | ROLL OUT 2 PTPN 6 JAMBI | APPLICATION | PERKEBUNAN NUSANTARA VI PT | MAS |  | null | NURUL HIDAYATI | ANWAR | PT Sigma Metrasys Solution | 01-OCT-17 | 30-JUN-19 | 100 | 97 | -3 | LAG | 8.CR (perubahan yang belum terkendali) & amandemen (customer) | 30896640000 | BIG | 27/02/2019 18:47:56
PROJ747 |  | ROLL OUT 2 PTPN 7 LAMPUNG | APPLICATION | PERKEBUNAN NUSANTARA VII PT | MAS |  | null | NURUL HIDAYATI | ADE NIRWANI | PT Sigma Metrasys Solution | 01-OCT-17 | 30-JUN-19 | 100 | 93 | -7 | LAG | 8.CR (perubahan yang belum terkendali) & amandemen (customer) | 33189750000 | BIG | 27/02/2019 18:59:31
PROJ749 |  | ROLL OUT 3 PTPN 13 PONTIANAK | APPLICATION | PERKEBUNAN NUSANTARA XIII | MAS |  | null | NURUL HIDAYATI | HAMIDONG | PT Sigma Metrasys Solution | 01-OCT-17 | 30-JUN-19 |  | 55 |  | LEAD | 2.Kesiapan lokasi ( customer) | 18103500000 | ORDINARY | 27/02/2019 19:44:36
PROJ843 |  | NAC SOLUTION EDC DIAL UP BANK MANDIRI | CPE DEVICES | BANK MANDIRI | BMS-1 |  | null | MUHAMMAD MASYHUDI | FERY KURNIAWAN | PT Sigma Cipta Caraka | 21-SEP-17 | 31-OCT-18 | 98.85 | 89.21 | -9.64 | DELAY | 8.CR (perubahan yang belum terkendali) & amandemen (customer) | 39960000000 | BIG | 12/03/2019 16:40:14
PROJ1517 | LOP102419 | PENGADAAN ENHANCEMENT PORTAL BTN PROPERTI PHASE 2 | CPE DEVICES | BANK TABUNGAN NEGARA (PERSERO) | BMS-1 | K.TEL.03-0827/HK.810/DES-BMS1/2018 | null | MUTTAQIN NASUTION | DISKAERI | PT Sigma Cipta Caraka | 28-MAR-18 | 23-JAN-19 | 95 | 87.6 | -7.4 | DELAY | 1.Delivery barang/jasa (mitra) | 4086363636 | ORDINARY | 12/03/2019 16:53:33
PROJ1545 |  | UPGRADE DAN PSB VPN IP DAN 2 BACKHAUL, PSB ASTINET LITE DAN 2 BACKHAUL, DAN MANAGED AP BANK BTPN | CONNECTIVITY | BANK BTPN | BMS-2 |  |  | M ISNAINI SAPUTRO | BERTHA DESVIANI PURBA | PT Teltranet Aplikasi Solusi (Telkom Telstra) | 07-MAY-18 | 07-DEC-18 | 100 | 83.3 | -16.7 | DELAY | 1.Delivery barang/jasa (mitra) | 103745000000 | MEGA | 18/02/2019 15:28:37
PROJ2486 | LOP106379 | PEKERJAAN INSTALASI ELEKTRIKAL PADA PROYEK PEMBANGUNAN GEDUNG HK OFFICE | SMART BUILDING | HUTAMA KARYA PT | PCS | K.TEL.08-0922/HK.810/DES-00/2018 | null | AD STEFEN RATU EDA | GATHUT SUKANDARTO | PT PINS Indonesia | 13-AUG-18 | 15-DEC-18 | 99.999 | 30.999 | -69 | DELAY | 2.Kesiapan lokasi ( customer) | 7425000000 | ORDINARY | 11/03/2019 13:56:23
PROJ2596 | LOP106759 | JASA MIGRASI PORT DARI LAYANAN VSAT KE MPLS DI 20 REMOTE EX PROVIDER TENGARA | CONNECTIVITY | BANK RAKYAT INDONESIA (PERSERO) | BMS-1 | K.TEL.03-1101/HK.850/DES-BMS1/2018 | null | NUR WIJAYANTO | RUDY SETYO NUGROHO | PT Multimedia Nusantara, PT Multimedia Nusantara | 03-SEP-18 | 31-DEC-18 |  | 0 |  | DELAY |  | 12210000 | REGULAR | 13/03/2019 14:11:57
PROJ2706 |  | INSTALASI INFRASTRUKTUR JARINGAN DATA REDUNDANT FASILITAS DATA CENTER DAN DISASTER RECOVERY CENTER PT BIO FARMA | CPE DEVICES | BIO FARMA PERSERO | HWS |  | ["K.TEL.3952\/HK.810\/DR3-10000000\/2018"] | SOPIYAN SOPIYANA | EKO ARDIANSYAH PUTRA | PT PINS Indonesia | 15-AUG-18 | 15-FEB-19 | 100 | 85.611 | -14.389 | DELAY | 3.Perubahan desain/spek pelanggan (customer) | 3609451200 | ORDINARY | 11/02/2019 15:36:31
PROJ3160 | LOP108197 | PENGADAAN PENGEMBANGAN SISTEM APLIKASI OFFICE AUTOMATION JAMKRINDO | APPLICATION | GD. JAMKRINDO | FMS | K.TEL.10-0228/HK.810/DES-FMS/2018 | null | MUTTAQIN NASUTION | MULYADI, ST | PT Sigma Cipta Caraka | 08-OCT-18 | 28-DEC-18 | 100 | 97.5 | -2.5 | DELAY | 8.CR (perubahan yang belum terkendali) & amandemen (customer) | 953447000 | REGULAR | 12/03/2019 16:49:31
PROJ3703 | LOP110303 | PENGADAAN PENGEMBANGAN APLIKASI PENGADAAN BARANG DAN JASA JASA RAHARJA | APPLICATION | ASURANSI JASA RAHARJA PT | HWS |  | null | ARIA OCTA | QUVIN NOLA PRIHANDANI | PT Mitra Mandiri Informatika | 21-DEC-18 | 28-FEB-19 | 42 | 77 | 35 | DELAY | 3.Perubahan desain/spek pelanggan (customer) | 1360000000 | ORDINARY | 11/03/2019 15:02:13
PROJ3992 | LOP143633 | PENGADAAN PERALATAN ELEKTRONIK PENDUKUNG KEGIATAN UTBK UNIVERSITAS BRAWIJAYA TAHUN 2019 |  | UNIVERSITAS BRAWIJAYA | EMS |  |  | HADI TRIYONO | RIZAL AGUSTA | PT PINS Indonesia | 28-JUN-18 | 30-APR-19 |  | 0 |  | LEAD |  | 5889454545 | ORDINARY | 04/03/2019 14:19:42
PROJ4011 | LOP143690 | PENGADAAN UPGRADE 12 UNIT SERVER EKSISTING UNTUK BIG DATA PT. BANK RAKYAT INDONESIA (PERSERO) TBK | CPE DEVICES | BANK RAKYAT INDONESIA (PERSERO) | BMS-1 |  | null | RUDIONO | RUDY SETYO NUGROHO | PT Signet Pratama, PT Signet Pratama | 14-DEC-18 | 31-MAR-19 | 89.29 | 0 | -89.29 | LAG | 5.Keterlambatan SPK ke mitra (di awal) (Telkom) | 2555870000 | ORDINARY | 06/03/2019 16:48:07