## Worksheet
ID PROJECT | ID LOP | CATEGORY | NAME | TYPE | START DATE | END DATE | CUSTOMER | SEGMEN | PARTNER | STATUS | PLAN (This Week) | ACHIEVEMENT | DEVIASI | VALUE | POTENTIAL SCALING THIS WEEK | POTENTIAL SCALING | PM NAME | AM NAME | NOMOR KB | NOMOR KL | REASON OF DELAY | LAST UPDATE
PROJ31 |  | ORDINARY | PROJECT INTERNATIONAL FINANCIAL CENTER 2 | SMART BUILDING | 18-AUG-15 | 30-SEP-17 | INTERNATIONAL FINANCIAL CENTER | PCS | PT PINS Indonesia | DELAY | 100 | 95.67 | -4.33 | 2484600427 | 107583198.4891 | 107583198.4891 | HERI IKHWAN DIANA | DWI PUDJI IRAWATI |  |  | 5.Keterlambatan SPK ke mitra (di awal) (Telkom) | 19/10/2018 16:18:35
PROJ89 |  | ORDINARY | ICT FTTH GPON ANANDAMAYA RESIDENCE | SMART BUILDING | 28-JUL-16 | 17-NOV-18 | ADHI KARYA PT | PCS | PT PINS Indonesia, PT PINS Indonesia | DELAY | 100 |  |  | 2285000000 |  |  | ATAM RUSTAM | SHERA MAYANGSARI SUWITO |  |  | 1.Delivery barang/jasa (mitra) | 01/04/2019 06:23:55
PROJ234 |  | MEGA | ROLL OUT I ERP PTPN III (MEDAN) | APPLICATION | 01-MAR-17 | 30-JUN-19 | PERKEBUNAN NUSANTARA III PT | MAS | PT Sigma Metrasys Solution | LAG |  |  |  | 65172600000 |  |  | NURUL HIDAYATI | SIMON |  |  | 8.CR (perubahan yang belum terkendali) & amandemen (customer) | 01/04/2019 12:36:54
PROJ364 |  | ORDINARY | IMPLEMENTASI ORACLE PRIMAVERA DI PT PAL INDONESIA | APPLICATION | 28-FEB-17 | 31-DEC-18 | PAL | IBS | SIGMA SOLUSI INTEGRASI | DELAY | 100 | 88.1 | -11.896 | 3044996000 | 362354524 | 362354524 | NURUL HIDAYATI | I GUSTI BAGUS YOGISWARA GHEARTHA |  |  | 8.CR (perubahan yang belum terkendali) & amandemen (customer) | 27/02/2019 20:29:44
PROJ745 |  | ORDINARY | ROLL OUT 2 PTPN 1 ACEH | APPLICATION | 01-OCT-17 | 30-JUN-19 | PERKEBUNAN NUSANTARA I PT | MAS | PT Sigma Metrasys Solution | LAG |  |  |  | 12793140000 |  |  | NURUL HIDAYATI | AGUS FRIADI |  |  | 8.CR (perubahan yang belum terkendali) & amandemen (customer) | 01/04/2019 12:39:32
PROJ977 |  | MEGA | PEKERJAAN MEKANIKAL, ELEKTRIKAL & PLUMBING PROYEK TEKNOPLEX LIVING APARTMENT | SMART BUILDING | 31-OCT-17 | 31-MAY-19 | PT.MULTI KARYA UTAMA ABADI -BANDUNG TECHNOPLEX LIVING | PCS | PT Infrastruktur Telekomunikasi Indonesia (TELKOMINFRA) | LAG | 95.91 | 32.308 | -63.602 | 55000000000 | 34981100000 | 37230600000 | TEUKU HAMIZUL | RADIAN SIGIT DWIANANTO |  |  | 2.Kesiapan lokasi ( customer) | 31/03/2019 20:21:34
PROJ1043 | LOP31751 | ORDINARY | PREMISES AND SISTEM TELEMARKETING PT BNI LIFE INSURANCE | CPE DEVICES | 01-MAR-18 | 28-FEB-19 | BNI LIFE | HWS | PT Infomedia Nusantara | DELAY | 100 | 99.73 | -0.27 | 9389952000 | 25352870.4 | 25352870.4 | HERU IRMAN | MOH. ZAINUL ARIFIN |  | null | 3.Perubahan desain/spek pelanggan (customer) | 28/03/2019 15:04:12
PROJ1517 | LOP102419 | ORDINARY | PENGADAAN ENHANCEMENT PORTAL BTN PROPERTI PHASE 2 | CPE DEVICES | 28-MAR-18 | 23-JAN-19 | BANK TABUNGAN NEGARA (PERSERO) | BMS-1 | PT Sigma Cipta Caraka | DELAY | 100 | 87.6 | -7.4 | 4086363636 | 506709090.864 | 506709090.864 | MUTTAQIN NASUTION | DISKAERI | K.TEL.03-0827/HK.810/DES-BMS1/2018 |  | 10.Keterbatasan kapabilitas mitra (mitra) | 18/03/2019 14:13:12
PROJ1877 | LOP104326 | MEGA | PROJECT PEKERJAAN DIGITAL CORE PLATFORM DI PERUM PERURI | CPE DEVICES | 05-JUL-18 | 30-JAN-19 | PERURI PERUM | FMS | PT Sigma Metrasys Solution | DELAY | 100 | 100 | 0 | 89318181818 | 0 | 0 | IRWANDI | WIJAYANTO | K.TEL.06-0826/HK.850/DES-A00000000/2018 |  | 1.Delivery barang/jasa (mitra) | 12/03/2019 15:38:02
PROJ2237 | LOP105044 | ORDINARY | PEKERJAAN PEMBANGUNAN SMART BUILDING PADA KANTOR BARU DI BELAWAN PT. PELABUHAN INDONESIA I (PERSERO) | SMART BUILDING | 26-JUL-18 | 31-AUG-19 | PELINDO 1 | MLS | PT PINS Indonesia, PT PINS Indonesia, PT PINS Indonesia | LAG | 55.16 | 62.19 | 7.03 | 10288470610 | 3890070737.641 | 3890070737.641 | NAZIRWAN, ST. M.KOM | YETTI ASRI, SE |  | null | 2.Kesiapan lokasi ( customer) | 29/03/2019 15:25:11
PROJ2443 | LOP106326 | ORDINARY | SEWA LAYANAN LAN EXTENSION ASSET 5 | CPE DEVICES | 26-OCT-18 | 31-JAN-19 | PERTAMINA PT | ERS | PT Nusantara Compnet Integrator, PT Wave Communication Indonesia | DELAY | 100 | 90 | 34 | 5992332000 | 599233200 | 599233200 | IKA SADERA M | REIKA ERMANSA | K.TEL.08-0209/HK.850/ DES-00/2018 |  |  | 20/03/2019 14:50:45
PROJ2748 | LOP107405 | ORDINARY | PENGADAAN IMPLEMENTASI DIGITALISASI KFTD (PLATFORM E-DISTRIBUTION) UNTUK PT KIMIA FARMA | APPLICATION | 18-DEC-18 | 15-AUG-19 | KIMIA FARMA PT | HWS | PT Sigma Cipta Caraka | LEAD | 0 | 10.1 | 10.1 | 10476226900 | 9418127983.1 | 9418127983.1 | ZAKY AHMAD | MELANY ULFA |  |  |  | 22/03/2019 19:44:47
PROJ2940 | LOP108000 | ORDINARY | ASTINET LITE BACKUP TELKOMSEL FLASH 12 GB DAN 32 GM (CARD ONLY) - PT HERO SUPERMARKET, TBK | CONNECTIVITY | 05-OCT-18 | 06-NOV-18 | HERO SUPERMARKET | TDS | PT Telekomunikasi Selular, PT Telekomunikasi Selular, PT Telekomunikasi Selular | DELAY | 100 | 55 | -45 | 3057600000 | 1375920000 | 1375920000 | YUSUF SARTONO | POERBO SOESENO |  |  | 2.Kesiapan lokasi ( customer) | 18/03/2019 13:53:07
PROJ3284 | LOP108944 | ORDINARY | PENGEMBANGAN DATA CENTER DAN DRC (KAPASITAS SERVER) UNTUK SERVER APLIKASI KERETA API INDONESIA | APPLICATION | 06-NOV-18 | 03-FEB-19 | KERETA API INDONESIA | TMS | PT Sigma Cipta Caraka | DELAY | 100 | 100 | 0 | 9846000000 | 0 | 0 | ARIEF SUSILO WIBOWO | NURI FAJARIYANAH | K.TEL.11-0151/HK.810/DES-00/2018 | null | 1.Delivery barang/jasa (mitra) | 29/03/2019 15:06:56
PROJ3348 | LOP21683 | REGULAR | JASA SYSTEM MANAGEMENT MONITORING PRODUCTION PERUM PERURI | APPLICATION | 12-NOV-18 | 31-MAR-19 | PERURI PERUM | FMS | PT PINS Indonesia, PT PINS Indonesia | DELAY | 100 | 91.55 | -8.45 | 680454545 | 57498409.0525 | 57498409.0525 | DODI IRAWAN | MULYADI, ST | K.TEL.11-0905/HK.810/DES-FMS/2018 |  | 1.Delivery barang/jasa (mitra) | 26/03/2019 22:45:02
PROJ3992 | LOP143633 | ORDINARY | PENGADAAN PERALATAN ELEKTRONIK PENDUKUNG KEGIATAN UTBK UNIVERSITAS BRAWIJAYA TAHUN 2019 |  | 28-JUN-18 | 30-APR-19 | UNIVERSITAS BRAWIJAYA | EMS | PT PINS Indonesia | LAG | 100 | 100 | 0 | 5889454545 | 0 | 0 | HADI TRIYONO | RIZAL AGUSTA |  |  |  | 17/03/2019 08:17:46
PROJ4177 | LOP144368 | ORDINARY | SUPPLY AND INSTALLATION OF CCTV, PERSONAL COMPUTER, NOTEBOOK, AND LICENSE FOR PT NEW PRIOK CONTAINER TERMINAL ONE | CPE DEVICES | 16-JAN-19 | 15-MAY-19 | PT NEW PRIOK CONTAINER TERMINAL ONE | MLS | PT Sigma Cipta Caraka, PT Wave Communication Indonesia | LAG | 84.89 | 49.04 | -35.85 | 1875294586 | 672293109.081 | 955650121.0256 | DODI IRAWAN | M. TEEZAR DWIPUTRA R | K.TEL.01-0463/HK.850/DES-MLS/2019 |  | 10.Keterbatasan kapabilitas mitra (mitra) | 26/03/2019 22:35:28
PROJ42 |  | REGULAR | PROJECT WIFI.ID GARUDA INDONESIA | CONNECTIVITY | 01-JAN-16 | 31-DEC-18 | GARUDA INDONESIA PT | TMS |  | DELAY | 100 | 100 | 5 | 162000000 | 0 | 0 | SRI NURFALAH | NOSKI PANDAPOTAN SAMOSIR |  |  |  | 31/12/2018 13:58:20
PROJ7 |  | ORDINARY | PROJECT FTTH DUKUH GOLF KEMAYORAN BOUGENVILLE | SMART BUILDING | 18-SEP-14 | 30-SEP-16 | AGUNG SEDAYU PROPERTINDO | IBS | PT PINS Indonesia, PT PINS Indonesia | DELAY | 100 |  |  | 19043050000 |  |  | PRAKOSA TRIWIBOWO | FAHMI MUHAMMAD HUSIN |  |  | 4.Keterlambatan BAST (customer) | 01/04/2019 12:36:11
PROJ18 |  | ORDINARY | PROJECT VIMALA HILLS (PANIC BUTTON) | SMART BUILDING | 10-MAR-14 | 31-MAY-18 | PODOMORO GROUP | PCS | PT PINS Indonesia | DELAY | 100 | 90.95 | -9.05 | 2100000000 | 190050000 | 190050000 | HERI IKHWAN DIANA | GERRY ROY MANAEK SIAHAAN |  |  | 8.CR (perubahan yang belum terkendali) & amandemen (customer) | 19/10/2018 16:06:43
PROJ367 |  | ORDINARY | LAYANAN INFOKOM MODERENISASI JARINGAN GRAND INDONESIA | SMART BUILDING | 01-DEC-16 | 31-DEC-18 | GRAND INDONESIA | PCS | PT Bangtelindo | DELAY | 100 | 100 | 0 | 6685966305 | 0 | 0 | TEDDY AWALUDIN | NOVI ANDRIYANI |  |  | 1.Delivery barang/jasa (mitra) | 30/01/2019 11:46:02
PROJ449 |  | ORDINARY | PURI MANSION APARTMENT | SMART BUILDING | 10-JUL-17 | 07-OCT-17 | AGUNG SEDAYU PROPERTINDO | IBS | PT PINS Indonesia | DELAY | 100 | 84 | -16 | 8301000000 | 1328160000 | 1328160000 | HERU IRMAN | FAHMI MUHAMMAD HUSIN |  |  | 3.Perubahan desain/spek pelanggan (customer) | 12/03/2019 14:59:03
PROJ743 |  | ORDINARY | PENGADAAN SEWA EDC PERUNTUKAN BANSOS BANK BTN | CPE DEVICES | 22-SEP-17 | 31-DEC-18 | BANK TABUNGAN NEGARA (PERSERO) | BMS-1 | PT Sigma Cipta Caraka, PT Sigma Cipta Caraka | DELAY | 100 | 70 | -30 | 7265454545 | 2179636363.5 | 2179636363.5 | MUTTAQIN NASUTION | DISKAERI |  |  | 4.Keterlambatan BAST (customer) | 13/03/2019 11:20:24
PROJ843 |  | BIG | NAC SOLUTION EDC DIAL UP BANK MANDIRI | CPE DEVICES | 21-SEP-17 | 31-OCT-18 | BANK MANDIRI | BMS-1 | PT Sigma Cipta Caraka | DELAY | 100 | 89.21 | -9.64 | 39960000000 | 4311684000 | 4311684000 | MUHAMMAD MASYHUDI | FERY KURNIAWAN |  |  | 8.CR (perubahan yang belum terkendali) & amandemen (customer) | 12/03/2019 16:40:14
PROJ1169 | LOP101909 | REGULAR | PENGADAAN JASA PENGEMBANG APLIKASI E-PAS & INFRASTRUKTUR PENDUKUNGNYA PT PUPUK SRIWIDJAJA PALEMBANG | APPLICATION | 23-MAR-18 | 19-MAY-19 | PUPUK SRIWIJAYA | MAS | PT Infomedia Nusantara | LAG | 60 | 81.5 | 21.5 | 523800000 | 96903000 | 96903000 | RIKA AMALIA SASANTY | MUHAMMAD HANIS | K.TEL.04-0031/HK.810/DR1-11120000/2018 |  | 3.Perubahan desain/spek pelanggan (customer) | 27/03/2019 18:07:55
PROJ1545 |  | MEGA | UPGRADE DAN PSB VPN IP DAN 2 BACKHAUL, PSB ASTINET LITE DAN 2 BACKHAUL, DAN MANAGED AP BANK BTPN | CONNECTIVITY | 07-MAY-18 | 07-DEC-18 | BANK BTPN | BMS-2 | PT Teltranet Aplikasi Solusi (Telkom Telstra) | DELAY | 100 | 83.3 | -16.7 | 103745000000 | 17325415000 | 17325415000 | M ISNAINI SAPUTRO | BERTHA DESVIANI PURBA |  |  | 1.Delivery barang/jasa (mitra) | 18/02/2019 15:28:37
PROJ2392 | LOP104964 | ORDINARY | PENGADAAN PEMBANGUNAN DATA CENTER KERETA COMMUTER INDONESIA | APPLICATION | 13-AUG-18 | 31-OCT-18 | KERETA COMMUTER INDONESIA | TMS | PT Sigma Cipta Caraka | DELAY | 100 | 100 | 0 | 1749000000 | 0 | 0 | ARIEF SUSILO WIBOWO | VINO HARSADITYA SAPUTRA | K.TEL.07-1015/HK.810/DES-TMS/2018 |  | 1.Delivery barang/jasa (mitra) | 27/03/2019 10:46:15
PROJ2572 | LOP106605 | BIG | PEMBANGUNAN INFRASTRUKTUR FIBER OPTIK TAHAP 2 - SINERGI OPTIMA NALADHIPA | SMART BUILDING | 02-AUG-18 | 02-JUN-19 | SINERGI OPTIMA NALADHIPA | THS | PT Patra Telekomunikasi Indonesia | LAG | 47.354 | 27.73 | -19.624 | 32654000000 | 6408020960 | 23599045800 | TEUKU HAMIZUL | R. WIDHA ANDI PARMOKO |  |  |  | 31/03/2019 20:10:49
PROJ3507 | LOP109718 | ORDINARY | REVISI MITRA PENGADAAN JASA LAIN DISASTER RECOVERY CENTER (DRC) SAP S/4 HANA JASA MARGA (PERSERO) | APPLICATION | 06-NOV-18 | 03-FEB-19 | JASA MARGA (PERSERO) | TMS | PT Sigma Cipta Caraka, PT Sigma Metrasys Solution | DELAY | 100 | 100 | 0 | 8024730000 | 0 | 0 | ARIEF SUSILO WIBOWO | ERSYHAD PRABAWA ADIGUNA | K.TEL.11-0878/HK.810/DES-00/2018 | null | 2.Kesiapan lokasi ( customer) | 29/03/2019 15:05:04
PROJ3671 | LOP109230 | REGULAR | PEMENUHAN PENYEDIAAN MANAGE SERVICE UNTUK ASTINET DI PT GUYOVITAL | CONNECTIVITY | 07-DEC-18 | 31-MAR-19 | NEOVIA GROUP | IBS | PT PINS Indonesia | DELAY | 100 | 100 | 0 | 15000000 | 0 | 0 | HARI MULYA | SOENARKO |  |  |  | 30/03/2019 08:09:50
PROJ4006 | LOP143645 | ORDINARY | JASA KONSULTAN APLIKASI TALENT MANAGEMENT SYSTEM | APPLICATION | 02-JAN-19 | 01-JUL-19 | TAMBANG BATU BARA BUKIT ASAM PT | ERS | PT Sigma Cipta Caraka | LEAD | 0 | 0 | 0 | 2454545495 | 0 | 2454545495 | ARIA OCTA | MUHAMMAD HANIS | K.TEL.01-0032/HK.850/DES-ERS/2019 |  |  | 15/03/2019 11:40:16
PROJ4020 | LOP143678 | BIG | PENYEMPURNAAN GEDUNG AOCC | SMART BUILDING | 17-DEC-18 | 16-JUN-19 | ANGKASA PURA II (PERSERO) - BUISH | TMS | PT PINS Indonesia | LAG | 57.49 | 71.241 | 13.751 | 24093860273 | 6929153275.9121 | 6929153275.9121 | RISTYAWAN FAUZI MUBAROK | FERRYMANSYAH, ST | K.TEL.12-0758/HK.810/DES-TMS/2018 | null |  | 29/03/2019 15:02:58
PROJ4785 |  | REGULAR | WIFI-ID UNIVERSITAS NEGERI PADANG SEWA LAYANAN WIFI ID SSO 600 AP | CONNECTIVITY | 01-FEB-19 | 31-DEC-19 | UNIVERSITAS NEGERI PADANG | EMS |  | LEAD | 0 | 0 | 0 | 0 | 0 | 0 | SRI NURFALAH | ARFAN SUATAN |  |  |  | 29/03/2019 10:17:09
PROJ3617 | LOP108934 | ORDINARY | MERCURY PROJECT LAFARGE HOLCIM INDONESIA. | CONNECTIVITY | 05-DEC-18 | 31-MAR-19 | HOLCIM INDONESIA | MAS |  | DELAY | 100 | 87.5 | 87.5 | 19256400000 | 2407050000 | 2407050000 | HARI MULYA | OCTORYZA PUTRA | K.TEL.11-0250/HK.810/DES-00/2018 |  |  | 01/04/2019 09:48:33
PROJ2179 |  | MEGA | LAYANAN MIGRASI VSAT KE VPN IP PT. PEGADAIAN | CONNECTIVITY | 01-JUL-18 | 31-DEC-18 | PEGADAIAN PT | FMS |  | DELAY | 100 | 0 | 0 | 248640300000 | 248640300000 | 248640300000 | FACHRI | ANDIKA PRATAMA PUTRA |  |  |  | 06/11/2018 14:12:10
PROJ903 |  | ORDINARY | PROJECT 5000 AKSES POINT WIFI PEGADAIAN | CONNECTIVITY | 22-FEB-18 | 31-DEC-19 | PEGADAIAN PT | FMS |  | LAG | 100 | 25 | -75 | 18000000000 | 13500000000 | 13500000000 | DWI WIDYA SAKTI | ANDIKA PRATAMA PUTRA |  |  |  | 02/01/2019 11:34:47
PROJ35 |  | ORDINARY | PROJECT PAKET PEKERJAAN ELEKTRONIK UNTUK TUNJUNGAN PLAZA 6 | SMART BUILDING | 12-JAN-16 | 31-MAR-19 | PAKUWON JATI | PCS | PT PINS Indonesia, PT PINS Indonesia | DELAY | 100 | 71.794 | -28.206 | 16640000000 | 4693478400 | 4693478400 | AD STEFEN RATU EDA | YAFRINO, ST, M.M |  |  | 1.Delivery barang/jasa (mitra) | 20/03/2019 10:45:11
PROJ204 |  | BIG | PROJECT RESUNAMI GRAND SENTRALAND KARAWANG | SMART BUILDING | 31-OCT-16 | 30-JUN-18 | PEMBANGUNAN PERUMAHAN PT | PCS | PT Infomedia Nusantara, PT Infomedia Nusantara, PT Infomedia Nusantara | DELAY | 100 | 82.009 | -17.988 | 23500000000 | 4227885000 | 4227885000 | TEUKU HAMIZUL | RADIAN SIGIT DWIANANTO |  |  | 3.Perubahan desain/spek pelanggan (customer) | 31/03/2019 20:32:05
PROJ237 |  | ORDINARY | ROLL OUT I ERP PTPN XII (SURABAYA) | APPLICATION | 01-MAR-17 | 30-JUN-19 | PERKEBUNAN NUSANTARA XII PT | MAS | PT Sigma Metrasys Solution | LAG |  |  |  | 19793160000 |  |  | NURUL HIDAYATI | I GUSTI BAGUS YOGISWARA GHEARTHA |  |  | 8.CR (perubahan yang belum terkendali) & amandemen (customer) | 01/04/2019 12:39:22
PROJ456 |  | ORDINARY | ICT DAN ELECTRONIC INSTALLATION DI THE WILADATIKA RESIDENCE | SMART BUILDING | 01-DEC-15 | 28-FEB-19 | ARTHA TELEKOMINDO | PCS | PT PINS Indonesia | DELAY | 100 | 94.71 | -5.29 | 5100000000 | 269790000 | 269790000 | TEDDY AWALUDIN | GOGATAMA DESENWA PRAYOGA |  |  | 5.Keterlambatan SPK ke mitra (di awal) (Telkom) | 30/01/2019 11:39:27
PROJ750 |  | ORDINARY | ROLL OUT 3 PTPN XIV MAKASAR | APPLICATION | 01-OCT-17 | 30-JUN-19 | PERKEBUNAN NUSANTARA INDONESIA XIV, PT | MAS | PT Sigma Metrasys Solution | LAG |  |  |  | 9172440000 |  |  | NURUL HIDAYATI | NADIAH LIESTYASARI |  |  | 8.CR (perubahan yang belum terkendali) & amandemen (customer) | 01/04/2019 12:39:08
PROJ751 |  | REGULAR | ROLL OUT 3 KPBN JAKARTA | APPLICATION | 01-OCT-17 | 30-JUN-19 | PERKEBUNAN NUSANTARA VII PT | MAS | PT Sigma Metrasys Solution | LAG |  |  |  | 844830000 |  |  | NURUL HIDAYATI | ANWAR |  |  | 8.CR (perubahan yang belum terkendali) & amandemen (customer) | 01/04/2019 12:40:36
PROJ801 | LOP101832 | MEGA | PROJECT DIGITALISASI KIMIA FARMA | CPE DEVICES | 27-DEC-17 | 31-DEC-18 | KIMIA FARMA PT | HWS | PT Sigma Cipta Caraka | DELAY | 100 | 98 | -2 | 787000000000 | 15740000000 | 15740000000 | ADRID | MELANY ULFA | K.TEL.156/HK.810/COP-G0000000/2017 | null | 10.Keterbatasan kapabilitas mitra (mitra) | 28/03/2019 15:02:36
PROJ1285 | LOP25267 | ORDINARY | PEKERJAAN ELEKTRONIK DAN ELEKTRIKAL DI APARTEMEN ZAMZAM TOWER DEPOK | SMART BUILDING | 01-JAN-18 | 30-NOV-18 | WIJAYA KARYA | PCS | PT Infrastruktur Telekomunikasi Indonesia (TELKOMINFRA) | DELAY | 100 | 82 | -18 | 10200000000 | 1836000000 | 1836000000 | TEDDY AWALUDIN | NOVI ANDRIYANI | K.TEL.02-0358/HK.810/DES-A00000000/2018 |  | 1.Delivery barang/jasa (mitra) | 15/03/2019 16:01:12
PROJ1492 | LOP24865 | ORDINARY | ORACLE ENTERPRISE BUSINESS SUITE (EBS) SUPPLY CHAIN MANAGEMENT`MODULE PT. PELNI (PERSERO) | APPLICATION | 06-MAR-18 | 08-MAR-19 | PELAYARAN NASIONAL INDONESIA (PELNI) PT | MLS | SIGMA SOLUSI INTEGRASI | DELAY | 100 | 88.4 | -11.6 | 8935000000 | 1036460000 | 1036460000 | ADRID | NAWIN |  | null | 8.CR (perubahan yang belum terkendali) & amandemen (customer) | 28/03/2019 16:19:48
PROJ2155 | LOP105438 | REGULAR | PENGADAAN ADMINISTRATIVE SERVICE ONLY PT. JALIN PEMBAYARAN NUSANTARA | CPE DEVICES | 09-AUG-18 | 08-JUL-21 | PT JALIN PEMBAYARAN NUSANTARA | BMS-1 | PT Administrasi Medika | LAG | 82.82 | 45.68 | -37.14 | 120000000 | 44568000 | 65184000 | DODI IRAWAN | SUPADMI | K.TEL.07-0086/HK.810/DES-BMS1/2018 |  | 1.Delivery barang/jasa (mitra) | 21/03/2019 14:49:50
PROJ2487 | LOP106420 | ORDINARY | PAKET PEMBANGUNAN DATA CENTER PT. INKA (PERSERO) | CPE DEVICES | 16-AUG-18 | 31-MAR-19 | INKA | IBS | PT Sigma Cipta Caraka | DELAY | 100 | 91.65 | -2.98 | 3624500000 | 302645750 | 302645750 | RUDIONO | FURI DIAH AYU HAPSARI | K.TEL.09-0124/HK.850/DES-IBS/2018 |  | 3.Perubahan desain/spek pelanggan (customer) | 25/03/2019 17:33:20
PROJ2583 | LOP106720 | REGULAR | JASA MIGRASI PORT DARI LAYANAN VSAT KE MPLS DI 244 REMOTE | CONNECTIVITY | 31-AUG-18 | 31-DEC-18 | BANK RAKYAT INDONESIA (PERSERO) | BMS-1 | PT Multimedia Nusantara | DELAY | 100 | 0 | 0 | 142450000 | 142450000 | 142450000 | NUR WIJAYANTO | RUDY SETYO NUGROHO |  |  |  | 13/03/2019 14:25:25
PROJ2695 |  | ORDINARY | PENGADAAN PEREMAJAAN PERANGKAT VIDEO CONFERENCE PT PEGADAIAN (PERSERO) TAHUN 2018 | CPE DEVICES | 21-AUG-18 | 27-NOV-18 | PEGADAIAN PT | FMS | PT Sigma Metrasys Solution | DELAY | 100 |  |  | 5363636364 |  |  | FAHMI RAHMANTHAHA NURDINSYAH | ANDIKA PRATAMA PUTRA | K.TEL.08-0614/HK.810/DES-00/2018 |  | 1.Delivery barang/jasa (mitra) | 01/04/2019 12:36:29
PROJ2802 | LOP107558 | ORDINARY | PERMINTAAN EDC TAMBAHAN UNTUK LELANG PENGADAAN SEWA OUTSOURCING EDC DAN PERANGKAT PENDUKUNGNYA PT. BPD SUMATERA SELATAN DAN BANGKA BELITUNG | CPE DEVICES | 30-MAY-18 | 30-OCT-20 | BANK SUMSEL BABEL | BMS-2 | PT PINS Indonesia | LAG | 99.91 | 40.64 | -59.27 | 4168260000 | 2470527702 | 2474279136 | HASBUR GHALI |  | K.TEL.11-0948/HK.810/DES-BMS2/2017 |  | 3.Perubahan desain/spek pelanggan (customer) | 27/03/2019 14:27:31
PROJ3146 | LOP108542 | ORDINARY | LAN & IPPBX FIELD SUBANG COLL PERTAMINA EP ASSET 3 SUBANG FIELD | SMART BUILDING | 22-OCT-18 | 21-DEC-18 | PERTAMINA PT | ERS | PT Nusantara Compnet Integrator | DELAY | 100 | 45 | -34.64 | 7735000000 | 4254250000 | 4254250000 | HADI TRIYONO | REIKA ERMANSA |  |  | 2.Kesiapan lokasi ( customer) | 18/03/2019 00:31:21
PROJ3500 | LOP108850 | REGULAR | PEMENUHAN PENYEDIAAN INFRASTRUKTUR JARINGAN WAN DAN MANAGE SERVICE PT WIRIFA SAKTI | CONNECTIVITY | 26-NOV-18 | 31-MAR-19 | NEOVIA GROUP | IBS | PT PINS Indonesia | DELAY | 100 | 100 | 0 | 376769982 | 0 | 0 | HARI MULYA | SOENARKO |  |  |  | 30/03/2019 08:19:18
PROJ3670 | LOP109210 | REGULAR | PEMENUHAN PENYEDIAAN INFRASTRUKTUR JARINGAN WAN DAN MANAGE SERVICE PT. WELGRO FEEDMILL | CONNECTIVITY | 07-DEC-18 | 31-MAR-19 | PT WIRIFA SAKTI (NEOVIA GROUP) | IBS | PT PINS Indonesia, PT PINS Indonesia, PT PINS Indonesia | DELAY | 100 | 100 | 2 | 358378352 | 0 | 0 | HARI MULYA | SOENARKO |  |  |  | 30/03/2019 08:20:26
PROJ3831 | LOP108872 | ORDINARY | PENYEDIAAN IMPLEMENTASI IT DRC (IT DISASTER RECOVERY CENTER) PT KRAKATAU STEEL (PERSERO) TBK | CPE DEVICES | 31-OCT-18 | 28-FEB-19 | KRAKATAU STEEL | TDS | PT Sigma Cipta Caraka | DELAY | 100 | 0 | -100 | 11100000000 | 11100000000 | 11100000000 | HADI TRIYONO | MHM. THOHIRUN |  |  | 2.Kesiapan lokasi ( customer) | 19/03/2019 15:01:13
PROJ4000 | LOP143616 | ORDINARY | EKSTERNAL DEDICATED HOSTING SERVICE PERTAMINA HULU MAHAKAM | CPE DEVICES | 01-JAN-19 | 21-MAR-19 | PERTAMINA PT | ERS | PT Sigma Cipta Caraka | DELAY | 100 | 12 | -80.28 | 2142498000 | 1885398240 | 1885398240 | IKA SADERA M | REIKA ERMANSA |  |  |  | 29/03/2019 09:07:29
PROJ4291 | LOP144688 | BIG | PENGADAAN MANAGED SERVICE VSAT REMOTE TERMINAL UNTUK INTEGRASI FASE 2B (ZONA 1) (MENGACU PADA SPK B80.P-PBJ/PIT/01/2019) | CONNECTIVITY | 18-JAN-19 | 03-APR-19 | BANK RAKYAT INDONESIA (PERSERO) | BMS-1 | PT Multimedia Nusantara | LEAD | 0 | 0 | 0 | 47456010000 | 0 | 47456010000 | WIM MUDJIONO | RUDY SETYO NUGROHO |  |  |  | 25/03/2019 12:12:12
PROJ4301 | LOP144617 | ORDINARY | PENGADAAN KOMPUTER DAN LAPTOP UTBK SBMPTN UNIVERSITAS DIPONEGORO 2019 | CPE DEVICES | 27-DEC-18 | 30-APR-19 | UNIVERSITAS DIPONEGORO SEMARANG | EMS | PT PINS Indonesia | LAG | 99.99 | 100 | 0.01 | 9418572727 | 0 | 0 | HADI TRIYONO | INDAH ARFIYATI KURNIA | K.TEL.01-0844/HK.810/DR4-1000000/2019 |  | 1.Delivery barang/jasa (mitra) | 29/03/2019 08:58:46
PROJ4510 | LOP150629 | REGULAR | PENGADAAN ENHANCEMENT EDC ACQUIRE INTROPS, MINI ATM DAN E- WALLET PROGRAM BANTUAN SOSIAL (SISI APLIKASI EDC) | CPE DEVICES | 13-FEB-19 | 13-JUN-19 | BANK TABUNGAN NEGARA (PERSERO) | BMS-1 | PT Sigma Cipta Caraka | LEAD | 63.75 | 64.5 | 0.75 | 500000000 | 177500000 | 177500000 | MUTTAQIN NASUTION | DISKAERI |  |  |  | 01/04/2019 19:42:10
PROJ4464 |  | REGULAR | PENYEDIAAN LAYANAN INTERNET WIFI ID DAN USEE TV CHANNELS | CONNECTIVITY | 12-NOV-18 | 12-APR-19 | ASTON HOTEL BALI | THS |  | LEAD | 0 | 0 | 0 | 12000000 | 0 | 12000000 | SRI NURFALAH | I MADE BUDIANA, SE, MM |  |  |  | 25/02/2019 10:53:34
PROJ379 |  | REGULAR | PROJECT WIFI.ID KFC | CONNECTIVITY | 01-JAN-17 | 31-DEC-18 | FASTFOOD INDONESIA | THS |  | DELAY | 100 | 80 | -20 | 237000000 | 47400000 | 47400000 | SRI NURFALAH | ANAK AGUNG ARDHA CHANDRA DEWI |  |  |  | 19/03/2019 10:49:42
PROJ30 |  | REGULAR | PROJECT PEKERJAAN SALURAN PENANGGAL BAWAH TANAH DI PROYEK BOULEVARD BUSINESS CENTER | SMART BUILDING | 19-NOV-14 | 31-JUL-17 | ADHI KARYA PT | PCS | PT Telkom Akses | DELAY | 100 | 62.59 | -37.41 | 472727273 | 176847272.8293 | 176847272.8293 | IRWANDI | MUHAMMAD SIDIK |  |  | 2.Kesiapan lokasi ( customer) | 12/03/2019 15:53:11
PROJ32 |  | ORDINARY | PROJECT PANIC BUTTON ORCHARD PARK BATAM | SMART BUILDING | 30-AUG-15 | 30-APR-18 | PODOMORO GROUP | PCS | PT PINS Indonesia, PT PINS Indonesia | DELAY | 100 | 90.84 | -9.16 | 2109703600 | 193248849.76 | 193248849.76 | IRWANDI | NOVI ANDRIYANI |  |  | 2.Kesiapan lokasi ( customer) | 15/03/2019 15:35:30
PROJ59 |  | ORDINARY | PROJECT ICT FTTH GPON (VERTIKAL DAN HORIZONTAL) DI APARTMENT BINTARO ICON | SMART BUILDING | 01-MAY-16 | 30-NOV-18 | ADITYA TOA DEV / MENARA THAMRIN | PCS | PT PINS Indonesia | DELAY | 100 |  |  | 5744549322 |  |  | ATAM RUSTAM | NADIAH LIESTYASARI |  |  | 1.Delivery barang/jasa (mitra) | 01/04/2019 12:34:27
PROJ95 |  | BIG | PROJECT ERP N-HOLDING LOKASI : PTPN V (PEKANBARU) | APPLICATION | 17-AUG-16 | 30-JUN-19 | PERKEBUNAN NUSANTARA V PT | MAS | PT Sigma Metrasys Solution | LAG | 100 | 100 | 0 | 35603550000 | 0 | 0 | NURUL HIDAYATI | SITI WIMA ADITYA MAHADINI |  |  | 8.CR (perubahan yang belum terkendali) & amandemen (customer) | 21/03/2019 19:02:07
PROJ182 |  | ORDINARY | PROJECT IN BUILDING SOLUTION (IBS) KEMPINSKI HOTEL BALI | SMART BUILDING | 16-DEC-16 | 30-APR-19 | GRAHA ALAM LESTARI | PCS | PT Dayamitra Telekomunikasi, PT Dayamitra Telekomunikasi | LAG | 100 | 95.36 | -4.64 | 7100000000 | 329440000 | 329440000 | AD STEFEN RATU EDA | GERRY ROY MANAEK SIAHAAN |  |  | 2.Kesiapan lokasi ( customer) | 18/03/2019 11:37:00
PROJ236 |  | BIG | ROLL OUT I ERP PTPN IX (SEMARANG) | APPLICATION | 01-MAR-17 | 30-JUN-19 | PERKEBUNAN NUSANTARA IX | MAS | PT Sigma Metrasys Solution | LAG |  |  |  | 31017330000 |  |  | NURUL HIDAYATI | NANANG RUSTANDI |  |  | 8.CR (perubahan yang belum terkendali) & amandemen (customer) | 01/04/2019 12:38:43
PROJ457 |  | ORDINARY | PROJECT GPON ICT DI CIPUTRA INTERNASIONAL | SMART BUILDING | 02-NOV-16 | 31-DEC-17 | CIPUTRA WORLD JAKARTA | PCS | PT PINS Indonesia | DELAY | 100 | 89.42 | 19.6 | 5336000000 | 564548800 | 564548800 | IRWANDI | GERRY ROY MANAEK SIAHAAN |  |  | 2.Kesiapan lokasi ( customer) | 07/12/2018 09:48:09
PROJ643 |  | ORDINARY | PEKERJAAN PROYEK RUSUNAMI JAKABARING TOWER 3 | SMART BUILDING | 02-OCT-17 | 28-MAR-18 | PEMBANGUNAN PERUMAHAN PT | PCS | PT Graha Sarana Duta, PT Graha Sarana Duta | DELAY | 100 | 99.26 | -0.57 | 8900000000 | 65860000 | 65860000 | NAZIRWAN, ST. M.KOM | RADIAN SIGIT DWIANANTO |  |  | 13.Kendala Finansial ( Customer ) | 14/03/2019 16:15:19
PROJ656 |  | ORDINARY | PROJECT CCTV ORCHARD PARK BATAM | SMART BUILDING | 13-OCT-17 | 30-MAR-18 | PENGUSAHAAN DAERAH INDUSTRI PULAU BATAM PT | PCS | PT PINS Indonesia, PT PINS Indonesia | DELAY | 100 | 89.5 | -10.5 | 1468000000 | 154140000 | 154140000 | IRWANDI | AGUS WIDIANTARA |  |  |  | 12/03/2019 15:45:20
PROJ753 |  | ORDINARY | PEKERJAAN INFRASTRUKTUR GPON GALAXY MALL 3 SURABAYA | SMART BUILDING | 17-NOV-17 | 30-NOV-18 | SINAR GALAXI | TDS | PT PINS Indonesia, PT PINS Indonesia | DELAY | 100 | 89.55 | -10.45 | 2300000000 | 240350000 | 240350000 | ATAM RUSTAM | SUCI ERNANINGTYAS |  |  | 1.Delivery barang/jasa (mitra) | 15/03/2019 14:32:30
PROJ790 |  | ORDINARY | PEKERJAAN SEWA OUTSOURCING 300 EDC DAN PERANGKAT PENDUKUNG OPERASIONAL BANK SUMSEL BABEL (BATCH 1) | CPE DEVICES | 30-OCT-17 | 30-OCT-20 | BPD SUMATERA SELATAN (BANK SUMSEL) | BMS-2 | PT PINS Indonesia | LAG | 100 | 97.5 | -2.5 | 3518405000 | 87960125 | 87960125 | HASBUR GHALI | EVI NOVIARNI |  |  | 8.CR (perubahan yang belum terkendali) & amandemen (customer) | 27/03/2019 14:32:08
PROJ1117 |  | BIG | PROJECT ELEKTRIKAL DAN ELEKTRONIK GEDUNG BIO FARMA 2 BANDUNG | SMART BUILDING | 26-FEB-18 | 27-MAY-19 | PEMBANGUNAN PERUMAHAN PT | PCS | PT Infrastruktur Telekomunikasi Indonesia (TELKOMINFRA) | LAG | 87.21 | 57.072 | -30.138 | 20800000000 | 6268704000 | 8929024000 | HADI TRIYONO | SHEINI CHRISTY | K.TEL.03-0026/HK.810/DES-A00000000/2018 |  | 1.Delivery barang/jasa (mitra) | 28/03/2019 08:25:05
PROJ1257 | LOP102059 | REGULAR | KFC 31 LOKASI WIFI ID + PROFILING | CONNECTIVITY | 01-JAN-19 | 31-DEC-19 | FASTFOOD INDONESIA | THS | PT Infomedia Nusantara | LAG | 53.2 | 65 | 11.8 | 669600000 | 234360000 | 234360000 | SRI NURFALAH | RINO SUPRIADI PUTRA |  |  |  | 25/03/2019 10:57:42
PROJ2293 |  | BIG | PENGADAAN PENYEDIAAN JASA LAYANAN PAKET E-TICKETING PERUM DAMRI | APPLICATION | 05-JUN-18 | 30-NOV-18 | DAMRI PO | TMS | PT NUTECH INTEGRASI | DELAY | 100 | 100 | 15.44 | 22461600000 | 0 | 0 | ARIEF SUSILO WIBOWO | ERSYHAD PRABAWA ADIGUNA | K.TEL.07-0342/HK.810/ DES-00/2018 | null | 4.Keterlambatan BAST (customer) | 29/03/2019 15:07:41
PROJ2396 |  | ORDINARY | PROJECT EASTERN GREEN BEKASI | SMART BUILDING | 30-NOV-17 | 30-NOV-19 | ADHI KARYA PT | PCS | PT PINS Indonesia | LAG | 100 | 76.5 | -23.5 | 6850000000 | 1609750000 | 1609750000 | PRAKOSA TRIWIBOWO | DWI PUDJI IRAWATI |  |  | 2.Kesiapan lokasi ( customer) | 28/03/2019 15:46:39
PROJ2398 |  | BIG | PEKERJAAN ELEKTRONIK PROJEK TRANS PARK BEKASI | SMART BUILDING | 23-AUG-18 | 31-DEC-19 | ADHI KARYA PT | PCS | PT PINS Indonesia | LAG | 42.57 | 0 | -42.57 | 20300000156 | 8641710066.4092 | 20300000156 | IMAM ZAHIR | DWI PUDJI IRAWATI |  |  |  | 17/03/2019 10:08:01
PROJ2584 | LOP106718 | REGULAR | JASA MIGRASI PORT DARI LAYANAN VSAT KE MPLS UNTUK KEBUTUHAN 215 LOKASI ATM | CONNECTIVITY | 31-AUG-18 | 31-DEC-18 | BANK RAKYAT INDONESIA (PERSERO) | BMS-1 | PT Multimedia Nusantara | DELAY | 100 | 0 | 0 | 128260000 | 128260000 | 128260000 | NUR WIJAYANTO | RUDY SETYO NUGROHO | K.TEL.03-0840/HK.850/DES-BMS1/2018 |  |  | 13/03/2019 14:23:56
PROJ2596 | LOP106759 | REGULAR | JASA MIGRASI PORT DARI LAYANAN VSAT KE MPLS DI 20 REMOTE EX PROVIDER TENGARA | CONNECTIVITY | 03-SEP-18 | 31-DEC-18 | BANK RAKYAT INDONESIA (PERSERO) | BMS-1 | PT Multimedia Nusantara, PT Multimedia Nusantara | DELAY | 100 | 0 | 0 | 12210000 | 12210000 | 12210000 | NUR WIJAYANTO | RUDY SETYO NUGROHO | K.TEL.03-1101/HK.850/DES-BMS1/2018 |  |  | 13/03/2019 14:11:57
PROJ2643 | LOP106895 | ORDINARY | CONTACT CENTER PT. ANUGERAH PHARMINDO LESTARI | CPE DEVICES | 27-AUG-18 | 07-JAN-19 | ANUGERAH PHARMINDO LESTARI | HWS | PT Infomedia Nusantara | DELAY | 100 |  |  | 2609196400 |  |  | MUTTAQIN NASUTION | QUVIN NOLA PRIHANDANI |  | null | 4.Keterlambatan BAST (customer) | 01/04/2019 12:38:05
PROJ4063 | LOP142853 | ORDINARY | PAKET PENGADAAN JASA IMPLEMENTASI ERP SAP S/4 HANA | CPE DEVICES | 01-JAN-19 | 01-JUL-19 | WASKITA KARYA | PCS | PT Sigma Metrasys Solution | LAG | 46.48 | 34 | -12.48 | 16300000000 | 2034240000 | 10758000000 | RIKA AMALIA SASANTY | FIKA FARIYANDI |  |  | 3.Perubahan desain/spek pelanggan (customer) | 27/03/2019 18:55:27
PROJ3212 |  | ORDINARY | LAYANAN REFRESHMENT INFRASTRUKTUR LAN PT PUPUK ISKANDAR MUDA (PIM) | CPE DEVICES | 13-OCT-18 | 10-FEB-19 | PUPUK ISKANDAR MUDA | MAS |  | DELAY | 100 | 0 | 0 | 4791949310 | 4791949310 | 4791949310 | RANDY NOARY | MULKI ZUCHRI |  |  |  | 01/11/2018 13:56:56
PROJ207 |  | ORDINARY | WIFI.ID ANGKASA PURA I (NGURAH RAI) TAHAP 2 | CONNECTIVITY | 01-JAN-17 | 31-DEC-18 | ANGKASAPURA I | TMS |  | DELAY | 100 | 88 | -12 | 2394000000 | 287280000 | 287280000 | SRI NURFALAH | ONHI YULIARTI SEMARA |  | null |  | 29/03/2019 15:10:54
PROJ375 |  | REGULAR | PROJECT WIFI.ID BANK RAKYAT INDONESIA | CONNECTIVITY | 01-JAN-17 | 31-DEC-18 | BANK RAKYAT INDONESIA (PERSERO) | BMS-1 |  | DELAY | 100 | 97 | -3 | 138772727 | 4163181.81 | 4163181.81 | SRI NURFALAH | RUDY SETYO NUGROHO |  |  |  | 25/03/2019 11:18:01
PROJ11 |  | ORDINARY | PROJECT PARK LAND AVENUE | SMART BUILDING | 01-NOV-15 | 30-DEC-18 | SUMMARECON AGUNG TBK | IBS | PT PINS Indonesia | DELAY | 100 | 72.028 | -27.042 | 3550000000 | 993006000 | 993006000 | PRAKOSA TRIWIBOWO | ACHMAD SUTARJONO |  |  | 11.Komitmen mitra(termasuk deal harga)(mitra) | 28/03/2019 15:50:58
PROJ137 |  | ORDINARY | PROJECT JASA KONSULTASI PENDAMPINGAN ICT PT. PAL INDONESIA (PERSERO) | APPLICATION | 01-DEC-16 | 31-DEC-18 | PAL | IBS | PT Sigma Cipta Caraka | DELAY | 100 | 67 | -33 | 1350000000 | 445500000 | 445500000 | NURUL HIDAYATI | I GUSTI BAGUS YOGISWARA GHEARTHA |  |  | 8.CR (perubahan yang belum terkendali) & amandemen (customer) | 27/02/2019 20:42:53
PROJ642 |  | ORDINARY | PEKERJAAN PROYEK RUSUNAMI JAKABARING TOWER 1 DAN 2 | SMART BUILDING | 02-OCT-17 | 28-MAR-18 | PEMBANGUNAN PERUMAHAN PT | PCS | PT Graha Sarana Duta | DELAY | 100 |  |  | 6000000000 |  |  | NAZIRWAN, ST. M.KOM | RADIAN SIGIT DWIANANTO |  |  | 13.Kendala Finansial ( Customer ) | 01/04/2019 12:35:43
PROJ824 |  | MEGA | PROJECT PEKERJAAN JASA IMPLEMENTASI ENTERPRISE RESOURCE PLANNING (ERP) DI PERUM PERURI | APPLICATION | 04-JAN-18 | 28-FEB-19 | PERURI PERUM | FMS | PT Sigma Metrasys Solution | DELAY | 100 |  |  | 54329137800 |  |  | IRWANDI | WIJAYANTO |  |  | 1.Delivery barang/jasa (mitra) | 01/04/2019 12:36:43
PROJ1275 | LOP102281 | BIG | PAKET SISTEM ELEKTRONIK APARTEMENT TOWER 1, HOTEL DAN MALL,PROYEK GREEN SEDAYU TAMAN PALEM JAKARTA | SMART BUILDING | 26-MAR-18 | 26-MAR-19 | AGUNG SEDAYU PROPERTINDO | IBS | PT PINS Indonesia, PT PINS Indonesia | DELAY | 100 | 20.594 | -76.376 | 26124999999 | 20744817499.206 | 20744817499.206 | HARI MULYA | FAHMI MUHAMMAD HUSIN |  |  | 1.Delivery barang/jasa (mitra) | 19/03/2019 15:54:02
PROJ1646 | LOP103401 | ORDINARY | PROYEK PEMBANGUNAN B RESIDENCE, SERPONG - TANGERANG PEKERJAAN ELEKTRONIK | SMART BUILDING | 15-JAN-18 | 15-SEP-19 | PT. MAJU GEMILANG SERPONG | PCS | PT PINS Indonesia, PT PINS Indonesia | LAG | 71.741 | 35.118 | -36.623 | 17985000000 | 6586646550 | 11669027700 | NAZIRWAN, ST. M.KOM | SUNARTO AMSALOM SAIRO |  |  | 2.Kesiapan lokasi ( customer) | 15/03/2019 16:06:47
PROJ1680 |  | ORDINARY | ICT LIVING WORLD PEKANBARU (PT TIGA DUA DELAPAN - CC KAWAN LAMA GROUP) | SMART BUILDING | 23-MAR-18 | 30-NOV-18 | KAWAN LAMA SEJAHTERA | TDS | PT Telkom Akses, PT Telkom Akses | DELAY | 100 |  |  | 1110000000 |  |  | ATAM RUSTAM | YULISTIKA RAHAYU | K.TEL.03-0585/HK.810/DES-TDS/2018 |  |  | 01/04/2019 12:34:04
PROJ1944 | LOP104864 | ORDINARY | PENGADAAN JARINGAN DATA GRAHA INKA | CPE DEVICES | 03-JUL-18 | 31-MAR-19 | INKA | IBS | PT PINS Indonesia | DELAY | 100 | 94.34 | -5.66 | 2585000000 | 146311000 | 146311000 | RUDIONO | FURI DIAH AYU HAPSARI | K.TEL.07-0073/HK.850/DES-IBS/2018 |  | 6.Masalah Administrasi & pembayaran mitra (Telkom) | 25/03/2019 17:45:28
PROJ2161 | LOP105406 | BIG | PROYEK PENGADAAN MATERIAL MEKANIKAL, ELEKTRIKAL, ELEKTRONIK PROYEK PADINA APARTEMENT | SMART BUILDING | 23-JUL-18 | 31-DEC-18 | PT PATRA BANGUN PROPERTI | PCS | PT Sandhy PutraMakmur | DELAY | 100 | 70.46 | -22.246 | 34875496682 | 10302221719.863 | 10302221719.863 | HERU IRMAN |  | K.TEL.07-0292/HK.810/DES-00/2018 |  | 1.Delivery barang/jasa (mitra) | 12/03/2019 14:45:38
PROJ2669 | LOP107004 | ORDINARY | PENGADAAN KONEKSI DIGITAL UNTUK PASSENGER EXIT SURVEY - BPS | APPLICATION | 27-AUG-18 | 31-MAR-19 | PENGELOLA STATISTIK DISTRIBUSI DAN JASA | THS | PT Metra Digital Media | DELAY | 100 | 100 | 0 | 5681850000 | 0 | 0 | IMAM ZAHIR | R. WIDHA ANDI PARMOKO |  |  | 10.Keterbatasan kapabilitas mitra (mitra) | 12/03/2019 15:32:32
PROJ3282 | LOP21842 | MEGA | PAKET JASA IMPLEMENTASI SISTEM ENTERPRISE RESOURCE PLANNING (ERP) PT. PEGADAIAN | APPLICATION | 23-OCT-18 | 19-FEB-19 | PEGADAIAN PT | FMS | PT Sigma Metrasys Solution | DELAY | 100 | 97.5 | -2.5 | 177272727273 | 4431818181.825 | 4431818181.825 | FAHMI RAHMANTHAHA NURDINSYAH | ANDIKA PRATAMA PUTRA | K.TEL.10-0683/HK.810/DES-00/2018 |  |  | 15/03/2019 15:22:46
PROJ3594 | LOP109872 | ORDINARY | PENGADAAN PENINGKATAN BUSINESS INTELEGENCE DI ATAS PLATFORM CLOUDERA (ATSCALE) | CPE DEVICES | 27-NOV-18 | 27-MAY-19 | BANK RAKYAT INDONESIA (PERSERO) | BMS-1 | PT Metra-Net | LAG | 92.31 | 94.43 | 2.12 | 13600000000 | 757520000 | 757520000 | ARIA OCTA | RUDY WIBOWO | K.TEL.09-0745/HK.810/DES-BMS1/2018 |  | 2.Kesiapan lokasi ( customer) | 15/03/2019 13:45:29
PROJ3724 | LOP109438 | ORDINARY | PENGADAAN JASA KONSULTAN PEMBUATAN SISTEM BACKEND E-TICKETING TRANSJAKARTA | APPLICATION | 17-DEC-18 | 16-APR-19 | PT. TRANSPORTASI JAKARTA | TMS | PT NUTECH INTEGRASI | LAG | 99.8 | 91.4 | -8.4 | 2647082111 | 222354897.324 | 227649061.546 | DODI IRAWAN | ERSYHAD PRABAWA ADIGUNA | K.TEL.01-0463/HK.850/DES-MLS/2019 | null |  | 29/03/2019 15:04:04
PROJ4011 | LOP143690 | ORDINARY | PENGADAAN UPGRADE 12 UNIT SERVER EKSISTING UNTUK BIG DATA PT. BANK RAKYAT INDONESIA (PERSERO) TBK | CPE DEVICES | 14-DEC-18 | 31-MAR-19 | BANK RAKYAT INDONESIA (PERSERO) | BMS-1 | PT Signet Pratama, PT Signet Pratama | DELAY | 100 | 0 | -100 | 2555870000 | 2555870000 | 2555870000 | RUDIONO | RUDY SETYO NUGROHO | K.TEL.12-0620/HK.850/DES-BMS1/2018 |  | 6.Masalah Administrasi & pembayaran mitra (Telkom) | 16/03/2019 16:27:26
PROJ4018 | LOP143683 | ORDINARY | PATRAJASA CIREBON - SMART TV DAN SHOWCASE MINI BARU | CPE DEVICES | 28-DEC-18 | 28-MAR-19 | HOTEL PATRAJASA | THS | PT PINS Indonesia | DELAY | 100 | 99 | -1 | 1404922018 | 14049220.18 | 14049220.18 | TEUKU HAMIZUL | FEBRINA HANIFAH |  |  |  | 31/03/2019 19:47:36
PROJ4058 | LOP143858 | MEGA | PENYEDIAAN JARINGAN KOMUNIKASI DAN MANAGED SERVICE SDWAN | CONNECTIVITY | 09-JAN-19 | 09-JAN-20 | FEDERAL INTERNATIONAL FINANCE (FIF) | FMS | PT Teltranet Aplikasi Solusi (Telkom Telstra) | LEAD | 0 | 0 | 0 | 113284000000 | 0 | 113284000000 | KRSHNA SULANJANA | CINDY ARINI |  |  |  | 18/03/2019 17:19:18
PROJ4668 | LOP107213 | MEGA | PENGADAAN MANAGED SERVICES PARTNER BRI BOX ZONA 4 (JAWA, NON DKI & NON JATIM) (MENGACU PADA SPK B. 117.P-PBJ/PIT/01/2019) | CPE DEVICES | 31-JAN-19 | 30-SEP-19 | BANK RAKYAT INDONESIA (PERSERO) | BMS-1 |  | LEAD | 0 | 0 | 0 | 295390026593 | 0 | 295390026593 | IMAM ZAHIR | RUDY SETYO NUGROHO |  |  |  | 22/03/2019 11:27:25
PROJ4197 |  | ORDINARY | WIFI.ID DAN CONNECTIVITY J.CO | CONNECTIVITY | 01-JAN-19 | 31-DEC-19 | JOHNY ANDREAN GROUP | THS |  | LAG | 49 | 75 | 26 | 2527200000 | 631800000 | 631800000 | SRI NURFALAH | EVY YULIA RAMADHAN |  |  |  | 25/03/2019 10:54:05
PROJ4198 |  | REGULAR | WIFI.ID UNIVERSITAS NEGERI PADANG | CONNECTIVITY | 01-JAN-19 | 31-DEC-19 | UNIVERSITAS NEGERI PADANG | EMS |  | LAG | 100 | 95 | -5 | 119350000 | 5967500 | 5967500 | SRI NURFALAH | ARFAN SUATAN |  |  |  | 19/03/2019 10:17:32
PROJ4527 |  | REGULAR | LINK INTERNET OUTLET BTN | CONNECTIVITY | 15-OCT-18 | 15-OCT-19 | BANK TABUNGAN NEGARA (PERSERO) | BMS-1 |  | LAG | 97 | 90.82 | -6.18 | 39330000 | 2430594 | 3610494 | HARI MULYA | DWI ARYANTO SULISTYO |  |  |  | 30/03/2019 08:40:54
PROJ1240 |  | ORDINARY | PERUBAHAN LAYANAN DAN PENAMBAHAN LOKASI MANAGE SERVICE ASTINET LITE 212 LOKASI PT. CHAROEN POKPHAND | CONNECTIVITY | 27-MAR-18 | 26-MAR-19 | CHAROEN POKPHAND INDONESIA PT | MAS |  | DELAY | 100 | 77 | -23 | 5003200000 | 1150736000 | 1150736000 | YUSUF SARTONO | ANISAH SOFWATI |  |  | 2.Kesiapan lokasi ( customer) | 18/03/2019 13:51:01
PROJ386 |  | REGULAR | PROJECT WIFI.ID PIZZA HUT | CONNECTIVITY | 01-JAN-17 | 31-DEC-19 | MAP FOOD & BEVERAGE | THS |  | LAG | 99.18 | 87 | -12.18 | 186000000 | 22654800 | 24180000 | SRI NURFALAH | EVY YULIA RAMADHAN |  |  |  | 25/03/2019 11:00:14
PROJ26 |  | ORDINARY | PROJECT SMART BUILDING SENTRALAND SEMARANG | SMART BUILDING | 16-JAN-15 | 31-MAR-18 | PERUMNAS PERUM | PCS | PT PINS Indonesia, PT PINS Indonesia | DELAY | 100 | 87.182 | -12.818 | 4129738470 | 529349877.0846 | 529349877.0846 | HADI TRIYONO | RADIAN SIGIT DWIANANTO |  |  | 1.Delivery barang/jasa (mitra) | 15/03/2019 15:29:07
PROJ27 |  | ORDINARY | PROJECT CEMINDO TOWER | SMART BUILDING | 01-SEP-14 | 31-DEC-17 | CEMINDO TOWER | PCS | PT Telkom Akses | DELAY | 100 |  |  | 13900000000 |  |  | NAZIRWAN, ST. M.KOM | MUHAMMAD SIDIK |  |  | 4.Keterlambatan BAST (customer) | 01/04/2019 12:35:16
PROJ36 |  | BIG | PROJECT SMART BUILDING HOTEL KEMPINSKI | SMART BUILDING | 11-FEB-16 | 30-APR-19 | GRAHA ALAM LESTARI | PCS | PT PINS Indonesia, PT PINS Indonesia | LAG | 98.309 | 84.46 | -13.849 | 23000000000 | 3185270000 | 3574200000 | AD STEFEN RATU EDA | GERRY ROY MANAEK SIAHAAN |  |  | 11.Komitmen mitra(termasuk deal harga)(mitra) | 18/03/2019 12:01:48
PROJ217 |  | ORDINARY | PROJECT MEKANIKAL & ELEKTRIKAL PEKERJAAN CINERE TERRACE SUITES - APARTMENT & CITYWALK | SMART BUILDING | 17-FEB-17 | 31-AUG-18 | METROPOLITAN TOWER | PCS | PT PINS Indonesia, PT PINS Indonesia | DELAY | 100 | 95.61 | -4.39 | 18568190000 | 815143541 | 815143541 | TEDDY AWALUDIN | SUNARTO AMSALOM SAIRO |  |  | 8.CR (perubahan yang belum terkendali) & amandemen (customer) | 13/03/2019 16:44:45
PROJ235 |  | MEGA | ROLL OUT I ERP PTPN IV (MEDAN) | APPLICATION | 01-MAR-17 | 30-JUN-19 | PERKEBUNAN NUSANTARA IV PT | MAS | PT Sigma Metrasys Solution | LAG |  |  |  | 55638090000 |  |  | NURUL HIDAYATI | SIMON |  |  | 8.CR (perubahan yang belum terkendali) & amandemen (customer) | 01/04/2019 12:39:57
PROJ405 |  | ORDINARY | PROJECT PENGADAAN DAN PEMASANGAN GATE BARRIER SELURUH GERBANG CLUSTER PROYEK ORCHARD PARK BATAM | SMART BUILDING | 01-APR-17 | 01-APR-18 | PODOMORO GROUP | PCS | PT PINS Indonesia, PT PINS Indonesia | DELAY | 100 | 88.58 | -11.42 | 1000000000 | 114200000 | 114200000 | IRWANDI | NOVI ANDRIYANI |  |  | 2.Kesiapan lokasi ( customer) | 12/03/2019 15:48:46
PROJ442 |  | MEGA | PROJECT PROPRIETARY LOYALTY PROGRAM PT PERTAMINA PERSERO | APPLICATION | 11-JUL-17 | 11-JUL-22 | PERTAMINA PT | ERS | PT Finnet Indonesia | LAG | 64.6 | 62 | -2.6 | 61862540000 | 1608426040 | 23507765200 | HERU IRMAN |  |  |  | 8.CR (perubahan yang belum terkendali) & amandemen (customer) | 12/03/2019 15:04:20
PROJ744 |  | BIG | ROLL OUT 2 PTPN 6 JAMBI | APPLICATION | 01-OCT-17 | 30-JUN-19 | PERKEBUNAN NUSANTARA VI PT | MAS | PT Sigma Metrasys Solution | LAG | 100 | 100 | 0 | 30896640000 | 0 | 0 | NURUL HIDAYATI | ANWAR |  |  | 8.CR (perubahan yang belum terkendali) & amandemen (customer) | 21/03/2019 18:38:35
PROJ746 |  | BIG | ROLL OUT 2 PTPN 2 MEDAN | APPLICATION | 01-OCT-17 | 30-JUN-19 | PERKEBUNAN NUSANTARA II PT | MAS | PT Sigma Metrasys Solution | LAG |  |  |  | 31982850000 |  |  | NURUL HIDAYATI | SIMON |  |  | 8.CR (perubahan yang belum terkendali) & amandemen (customer) | 01/04/2019 12:40:09
PROJ748 |  | MEGA | ROLL OUT 3 PTPN 8 BANDUNG | APPLICATION | 01-OCT-17 | 30-JUN-19 | PERKEBUNAN NUSANTARA VIII PT | MAS | PT Sigma Metrasys Solution | LAG |  |  |  | 65776050000 |  |  | NURUL HIDAYATI | EKO ARDIANSYAH PUTRA |  |  | 8.CR (perubahan yang belum terkendali) & amandemen (customer) | 01/04/2019 12:38:55
PROJ829 |  | MEGA | PROJECT APARTEMEN GRAND JATI JUNCTION MEDAN | SMART BUILDING | 01-SEP-17 | 31-DEC-18 | PEMBANGUNAN PERUMAHAN PT | PCS | PT Graha Sarana Duta | DELAY | 100 | 67.715 | -32.285 | 51400000000 | 16594490000 | 16594490000 | NAZIRWAN, ST. M.KOM | RADIAN SIGIT DWIANANTO |  |  | 8.CR (perubahan yang belum terkendali) & amandemen (customer) | 13/03/2019 12:11:53
PROJ2585 | LOP106715 | REGULAR | JASA MIGRASI PORT DARI LAYANAN VSAT KE MPLS DI 99 REMOTE EX PROVIDER CSM | CONNECTIVITY | 31-AUG-18 | 31-DEC-18 | BANK RAKYAT INDONESIA (PERSERO) | BMS-1 | PT Multimedia Nusantara | DELAY | 100 | 0 | 0 | 62260000 | 62260000 | 62260000 | NUR WIJAYANTO | RUDY SETYO NUGROHO | K.TEL.04-0090/HK.850/DES-BMS1/2018 |  |  | 13/03/2019 14:20:49
PROJ2706 |  | ORDINARY | INSTALASI INFRASTRUKTUR JARINGAN DATA REDUNDANT FASILITAS DATA CENTER DAN DISASTER RECOVERY CENTER PT BIO FARMA | CPE DEVICES | 15-AUG-18 | 15-FEB-19 | BIO FARMA PERSERO | HWS | PT PINS Indonesia | DELAY | 100 | 85.611 | -14.389 | 3609451200 | 519363933.168 | 519363933.168 | SOPIYAN SOPIYANA | EKO ARDIANSYAH PUTRA |  | ["K.TEL.3952\/HK.810\/DR3-10000000\/2018"] | 3.Perubahan desain/spek pelanggan (customer) | 13/03/2019 16:36:43
PROJ3041 | LOP108246 | ORDINARY | PEMBANGUNAN DATA CENTER PT PERTAMINA EP ASSET 5 | CPE DEVICES | 20-SEP-18 | 18-JAN-19 | PERTAMINA PT | ERS | PT Sigma Cipta Caraka | DELAY | 100 | 0 | 0 | 1497000000 | 1497000000 | 1497000000 | IKA SADERA M | REIKA ERMANSA | K.TEL.09-0739/HK.850/DES-ERS/2018 |  |  | 12/03/2019 15:13:12
PROJ3296 | LOP108701 | ORDINARY | PERANGKAT CCTV AREA HCC & JETTY RU II DUMAI | SMART BUILDING | 12-OCT-18 | 31-MAR-19 | PERTAMINA PT | ERS | PT PINS Indonesia | DELAY | 100 | 70 | -30 | 7516950000 | 2255085000 | 2255085000 | HARI MULYA | REIKA ERMANSA | K.TEL.11-0361/HK.850/DES-ERS/2018 |  | 1.Delivery barang/jasa (mitra) | 19/03/2019 17:39:58
PROJ3384 | LOP109217 | ORDINARY | HOTEL NEXA MAKASSAR - PENYEDIAAN LAYANAN INFRASTRUKTUR DAN ICT SOLUSION (PERJANJIAN PERPANJANGAN) | SMART BUILDING | 24-OCT-18 | 24-MAR-19 | HOTEL NEXA MAKASSAR | THS | PT PINS Indonesia | DELAY | 100 | 94.76 | -5.24 | 1650183093 | 86469594.0732 | 86469594.0732 | ADITYA | ANDI ABDUL WARIS |  |  | 2.Kesiapan lokasi ( customer) | 27/03/2019 13:31:06
PROJ3595 | LOP108938 | ORDINARY | PEKERJAAN PENGADAAN INFRASTRUKTUR IN-BUILDING COVERAGE (IBC) SYSTEM DI SEQUIS TOWER | SMART BUILDING | 05-NOV-18 | 05-APR-19 | PT PROSPERO REALTY | PCS | PT Dayamitra Telekomunikasi, PT Dayamitra Telekomunikasi | LAG | 100 | 89.3 | -10.7 | 5890000000 | 630230000 | 630230000 | IMAM ZAHIR | AGUS HARYO WINARDI | K.Tel.11-0128/HK.810/DES-00/2018 |  |  | 22/03/2019 10:01:13
PROJ3598 | LOP109855 | MEGA | PENGADAAN PROYEK RELOKASI & PENINGKATAN KAPASITAS DATA CENTER (COLOCATION) BANK BUKOPIN | APPLICATION | 30-NOV-18 | 31-MAR-19 | BANK BUKOPIN | BMS-2 | PT Sigma Cipta Caraka | DELAY | 100 | 0 | 0 | 94812000000 | 94812000000 | 94812000000 | FAHMI RAHMANTHAHA NURDINSYAH | GALIH ABDUL RAUF | K.TEL.11-0802/HK.810/DES-00/20188 |  |  | 15/03/2019 15:18:45
PROJ3620 | LOPUP361 | REGULAR | PENGEMBANGAN DASHBOAD MIS | APPLICATION | 13-DEC-18 | 13-SEP-19 | PT SARANA MULTI INFRASTRUKTUR (PERSERO) | FMS | PT Sigma Cipta Caraka | LAG | 36.66 | 23.25 | -13.41 | 750000000 | 100575000 | 575625000 | RIKA AMALIA SASANTY | DITHA NATASIA | K.TEL.11-0775/HK.810/DES-FMS/2018 |  | 10.Keterbatasan kapabilitas mitra (mitra) | 27/03/2019 18:09:05
PROJ3703 | LOP110303 | ORDINARY | PENGADAAN PENGEMBANGAN APLIKASI PENGADAAN BARANG DAN JASA JASA RAHARJA | APPLICATION | 21-DEC-18 | 28-FEB-19 | ASURANSI JASA RAHARJA PT | HWS | PT Mitra Mandiri Informatika | DELAY | 100 | 97 | 7 | 1360000000 | 40800000 | 40800000 | ARIA OCTA | QUVIN NOLA PRIHANDANI | K.TEL.12-0272/HK.810/DES-HWS/2018 | null | 3.Perubahan desain/spek pelanggan (customer) | 28/03/2019 14:53:33
PROJ3912 | LOP107362 | BIG | WASKITA - ERP SAP PAKET LISENSI | CPE DEVICES | 17-DEC-18 | 18-DEC-19 | WASKITA KARYA | PCS | PT Sigma Metrasys Solution | LAG | 90.44 | 88 | -2.44 | 22000000000 | 536800000 | 2640000000 | RIKA AMALIA SASANTY | FIKA FARIYANDI | K.TEL.12-0523/HK.810/ DES-00/2018 |  | 1.Delivery barang/jasa (mitra) | 27/03/2019 18:04:56
PROJ4152 | LOP144253 | ORDINARY | SEWA AKSES CONTROL SYSTEM DI PT PERTAMINA (PERSERO) RU IV CILACAP | SMART BUILDING | 21-JAN-19 | 22-JAN-19 | PERTAMINA PT | ERS | PT PINS Indonesia | DELAY | 100 | 1 | -17.14 | 13270000046 | 13137300045.54 | 13137300045.54 | HARI MULYA | REIKA ERMANSA |  |  |  | 30/03/2019 08:30:20
PROJ4579 | LOP150782 | ORDINARY | PEKERJAAN PEMBANGUNAN APLIKASI INTEGRATED TALENT MANAGEMENT SYSTEM (ITMS) PT PELABUHAN INDONESIA I (PERSERO) | APPLICATION | 11-MAR-19 | 19-AUG-19 | PELINDO 1 | MLS | PT Sigma Cipta Caraka | LAG | 14.5 | 17.5 | 3 | 3119910200 | 2573925915 | 2573925915 | MUTTAQIN NASUTION | YETTI ASRI, SE |  |  |  | 01/04/2019 17:54:46
PROJ3522 |  | ORDINARY | ASTINET LITE 93 LOKASI UNTUK PT. INDOMOBIL FINANCE INDONESIA | CONNECTIVITY | 04-OCT-18 | 31-DEC-18 | INDOMOBIL GROUP | IBS |  | DELAY | 100 | 0 | 0 | 2136901944 | 2136901944 | 2136901944 | ARI WIDIYANTO | ANDI SYAHRUDDIN |  |  |  | 27/11/2018 18:30:39
PROJ29 |  | ORDINARY | PROJECT GRAND TARUMA KARAWANG | SMART BUILDING | 09-MAY-14 | 31-DEC-18 | ADHI KARYA PT | PCS | PT PINS Indonesia | DELAY | 100 | 99.7 | -0.3 | 2888000000 | 8664000 | 8664000 | TEDDY AWALUDIN | NOVI ANDRIYANI |  |  | 8.CR (perubahan yang belum terkendali) & amandemen (customer) | 30/01/2019 12:17:32
PROJ429 |  | ORDINARY | PEKERJAAN ELEKTRONIKA DAN GPON PROYEK GALLERIA VIVO MALL SENTUL | SMART BUILDING | 24-MAY-17 | 31-AUG-18 | ADHIBALADIKA AGUNG | PCS | PT PINS Indonesia, PT PINS Indonesia | DELAY | 100 | 81.823 | -11.377 | 12500000000 | 2272125000 | 2272125000 | AD STEFEN RATU EDA | HELVIANA |  |  | 1.Delivery barang/jasa (mitra) | 18/03/2019 11:21:38
PROJ659 |  | ORDINARY | IMPLEMENTASI SISTEM ERP PT. HUTAMA KARYA (PERSERO) | APPLICATION | 25-OCT-17 | 25-MAY-19 | HUTAMA KARYA PT | PCS | PT Sigma Metrasys Solution | LAG | 91.67 | 100 | 8.33 | 14120376710 | 0 | 0 | RIKA AMALIA SASANTY | NURUL RIZKI UTAMI |  |  | 4.Keterlambatan BAST (customer) | 20/03/2019 08:45:06
PROJ747 |  | BIG | ROLL OUT 2 PTPN 7 LAMPUNG | APPLICATION | 01-OCT-17 | 30-JUN-19 | PERKEBUNAN NUSANTARA VII PT | MAS | PT Sigma Metrasys Solution | LAG |  |  |  | 33189750000 |  |  | NURUL HIDAYATI | ADE NIRWANI |  |  | 8.CR (perubahan yang belum terkendali) & amandemen (customer) | 01/04/2019 12:40:26
PROJ749 |  | ORDINARY | ROLL OUT 3 PTPN 13 PONTIANAK | APPLICATION | 01-OCT-17 | 30-JUN-19 | PERKEBUNAN NUSANTARA XIII | MAS | PT Sigma Metrasys Solution | LAG | 97 | 100 | 3 | 18103500000 | 0 | 0 | NURUL HIDAYATI | HAMIDONG |  |  | 8.CR (perubahan yang belum terkendali) & amandemen (customer) | 01/04/2019 12:39:47
PROJ2141 | LOP105334 | ORDINARY | PENYEDIAAN ICT, PABX, DATA, CCTV, SOUND SYSTEM, FIRE ALARM & IPTV PROYEK RSKIA KOTA BANDUNG | SMART BUILDING | 04-JUN-18 | 28-DEC-18 | ADHI KARYA PT | PCS | PT PINS Indonesia | DELAY | 100 | 90.01 | 33.79 | 7650000000 | 764235000 | 764235000 | PRAKOSA TRIWIBOWO | DWI PUDJI IRAWATI | K.TEL.06-0868/HK.810/DES-00/2018 |  | 1.Delivery barang/jasa (mitra) | 15/03/2019 15:38:31
PROJ2542 | LOP106618 | BIG | PENGADAAN APLIKASI PENDUKUNG PROGRAM PROMO BERKAH ENERGI PERTAMINA | APPLICATION | 30-AUG-18 | 08-AUG-19 | PERTAMINA PT | ERS | PT Finnet Indonesia, PT Sigma Metrasys Solution | LAG | 50 | 50 | 0 | 22570000000 | 0 | 11285000000 | HERU IRMAN |  | K.TEL.08-0615/HK.810/DES-00/2018 |  | 2.Kesiapan lokasi ( customer) | 12/03/2019 14:36:40
PROJ2582 | LOP106719 | REGULAR | JASA MIGRASI PORT DARI LAYANAN VSAT KE MPLS UNTUK 134 LOKASI | CONNECTIVITY | 31-AUG-18 | 31-DEC-18 | BANK RAKYAT INDONESIA (PERSERO) | BMS-1 | PT Multimedia Nusantara | DELAY | 100 | 0 | 0 | 81620000 | 81620000 | 81620000 | NUR WIJAYANTO | RUDY SETYO NUGROHO |  |  |  | 13/03/2019 14:26:34
PROJ3107 | LOP108271 | ORDINARY | PEKERJAAN SISTEM ELEKTRONIK PROYEK SEDAYU CITY APARTEMEN @ KELAPA GADING APARTEMENT JAKARTA | SMART BUILDING | 01-OCT-18 | 25-DEC-19 | AGUNG SEDAYU PROPERTINDO | IBS | PT PINS Indonesia | LAG | 43.01 | 10.818 | -32.192 | 18984900000 | 6111619008 | 16931113518 | HADI TRIYONO | FAHMI MUHAMMAD HUSIN | K.TEL.10-0030/HK.810/DES-IBS/2018 |  | 2.Kesiapan lokasi ( customer) | 19/03/2019 15:24:07
PROJ3710 | LOP110338 | ORDINARY | INSTALASI DAN SEWA PERANGKAT DATA CENTER DI PT PERTAMINA EP ASSET 1 JAMBI | APPLICATION | 07-DEC-18 | 11-MAR-19 | PERTAMINA PT | ERS | PT Sigma Cipta Caraka | DELAY | 100 | 26.12 | -9.04 | 6250000000 | 4617500000 | 4617500000 | ADRID | REIKA ERMANSA | K.TEL.12-0481/HK.810/ DES-00/2018 |  | 11.Komitmen mitra(termasuk deal harga)(mitra) | 23/03/2019 10:38:00
PROJ3908 | LOP109840 | ORDINARY | PROJECT UPGRADE HARDWARE DATA CENTER PUPUK DI DC SENTUL | APPLICATION | 17-DEC-18 | 24-FEB-19 | PUPUK INDONESIA HOLDING COMPANY | MAS | PT Sigma Cipta Caraka | DELAY | 100 | 0 | 0 | 11360000000 | 11360000000 | 11360000000 | FAHMI RAHMANTHAHA NURDINSYAH | OCTORYZA PUTRA | K.TEL.12-0504/HK.810/ DES-00/2018 |  |  | 15/03/2019 15:16:02
PROJ4140 | LOP144181 | ORDINARY | PENGADAAN LICENSE CLOUDERA UNTUK KEBUTUHAN ENTERPRISE DATA WAREHOUSE (EDW) | CPE DEVICES | 31-DEC-18 | 31-JAN-19 | BANK RAKYAT INDONESIA (PERSERO) | BMS-1 | PT Metra-Net | DELAY | 100 | 0 | 0 | 2763636364 | 2763636364 | 2763636364 | ARIA OCTA | RUDY SETYO NUGROHO | K.TEL.12-0922/HK.850/DES-BMS1/2018 |  | 5.Keterlambatan SPK ke mitra (di awal) (Telkom) | 15/03/2019 13:51:59
PROJ4374 | LOP144731 | MEGA | PENYEDIAAN LAYANAN TELKOMSOLUTION DI LINGKUNGAN TIARA MARGA TRAKINDO GROUP | CPE DEVICES | 01-FEB-19 | 31-JAN-24 | TIARA MARGA TRAKINDO | DTS | PT Teltranet Aplikasi Solusi (Telkom Telstra) | LAG | 24.2 | 23.58 | -0.62 | 75824743560 | 470113410.072 | 57945269028.552 | NAZIRWAN, ST. M.KOM | MAMAN ROCHAMAN |  |  |  | 28/03/2019 14:48:12
PROJ4470 | LOP150395 | ORDINARY | PENGADAAN MESIN EDC - 10.600 UNIT (MENGACU PADA SPK PFA/3.2/013) | CPE DEVICES | 10-JAN-19 | 19-APR-19 | BANK NEGARA INDONESIA 46TBK(BNI 46) | BMS-1 | SWADHARMA SARANA INFORMATIKA | LAG | 92.41 | 70 | -22.41 | 19184940000 | 4299345054 | 5755482000 | HASBUR GHALI | BAKTI MUDIAZKO | K.TEL.01-0277/HK.850/ DES-00/2019 |  | 5.Keterlambatan SPK ke mitra (di awal) (Telkom) | 28/03/2019 10:24:30
PROJ4595 | LOP150651 | BIG | PENGADAAN SOLUSI PSAK 71- FINANCIAL INSTRUMEN IMPLEMENTATION (IFRS 9) | CPE DEVICES | 12-MAR-19 | 13-MAR-19 | BANK MANDIRI | BMS-1 | PT Sigma Cipta Caraka, PT Sigma Cipta Caraka | DELAY | 100 | 0 | 0 | 45598000000 | 45598000000 | 45598000000 | DODI IRAWAN | M. AGUSTINUS SIANTURI | K.TEL.01-0982/HK.810/DES-00/2019 |  | 7.SoW belum sepakat (Telkom) | 16/03/2019 09:23:18
PROJ4201 |  | ORDINARY | WIFI.ID ANGKASA PURA II 2018 - 2019 | CONNECTIVITY | 16-JUL-18 | 17-JUL-19 | ANGKASA PURA II (PERSERO) - BUISH | TMS |  | LAG | 31.48 | 92 | 60.52 | 9798840000 | 783907200 | 783907200 | SRI NURFALAH | FERRYMANSYAH, ST |  |  |  | 19/03/2019 10:14:17
PROJ8 |  | REGULAR | PROJECT WIFI ID SAMSUNG EXPERIENCE STORE 106 LOKASI | CONNECTIVITY | 01-APR-14 | 31-DEC-18 | SAMSUNG ELECTRONIC INDONESIA | IBS |  | DELAY | 100 | 75 | -25 | 111600000 | 27900000 | 27900000 | SRI NURFALAH | ANDI SYAHRUDDIN |  |  |  | 25/03/2019 11:08:08
PROJ385 |  | REGULAR | PROJECT WIFI.ID STARBUCK | CONNECTIVITY | 01-JAN-17 | 31-DEC-18 | MAP FOOD & BEVERAGE | THS |  | DELAY | 100 | 95 | -5 | 480000000 | 24000000 | 24000000 | SRI NURFALAH | EVY YULIA RAMADHAN |  |  |  | 25/03/2019 11:02:13
PROJ21 |  | BIG | PROJECT CWJ 2 PHASE 1 | SMART BUILDING | 26-SEP-14 | 31-DEC-17 | CIPUTRA WORLD JAKARTA | PCS | PT PINS Indonesia | DELAY | 100 |  |  | 23660990600 |  |  | IRWANDI | GERRY ROY MANAEK SIAHAAN |  |  | 2.Kesiapan lokasi ( customer) | 01/04/2019 12:34:50
PROJ37 |  | ORDINARY | PROJECT SMART BUILDING MARIGOLD NAVAPARK - BSD | SMART BUILDING | 05-FEB-16 | 31-DEC-18 | ADHI KARYA PT | PCS | PT PINS Indonesia, PT PINS Indonesia | DELAY | 100 | 56.554 | -43.276 | 16500000000 | 7168590000 | 7168590000 | TEDDY AWALUDIN |  |  |  | 8.CR (perubahan yang belum terkendali) & amandemen (customer) | 15/03/2019 15:57:01
PROJ141 |  | ORDINARY | PROJECT SEAT MANAGEMENT PT. PELABUHAN INDONESIA (PELINDO) III | CPE DEVICES | 01-JAN-17 | 31-DEC-19 | PELINDO III | MLS | PT PINS Indonesia | LAG | 83.486 | 74.37 | -9.116 | 13868640000 | 1264265222.4 | 3554532432 | TEDDY AWALUDIN | RIFANDA PUTRI INDRESWARI |  |  | 3.Perubahan desain/spek pelanggan (customer) | 30/01/2019 11:51:38
PROJ203 |  | ORDINARY | ERP N-HOLDING | APPLICATION | 17-AUG-16 | 30-JUN-19 | PERKEBUNAN NUSANTARA III PT | MAS | PT Sigma Metrasys Solution | LAG | 59.864 | 94.9 | 35.036 | 10888000000 | 555288000 | 555288000 | NURUL HIDAYATI | ADRI SYAFMA PUTRA |  |  | 8.CR (perubahan yang belum terkendali) & amandemen (customer) | 21/03/2019 19:37:15
PROJ458 |  | ORDINARY | PROJECT ELEKTRONIK APARTEMEN DI BORNEO BAY BALIKPAPAN | SMART BUILDING | 01-JUL-17 | 22-OCT-18 | PODOMORO GROUP | PCS | PT PINS Indonesia, PT PINS Indonesia | DELAY | 100 | 82.6 | -16.188 | 14181818000 | 2467636332 | 2467636332 | PRAKOSA TRIWIBOWO | NOVI ANDRIYANI | K.TEL.0617-0606/HK.810/DES-A1000000/2017 |  | 2.Kesiapan lokasi ( customer) | 15/03/2019 15:41:15
PROJ771 |  | MEGA | PROJECT E-DAPEM TASPEN | APPLICATION | 17-OCT-17 | 11-FEB-19 | TASPEN PT | HWS | PT Sigma Cipta Caraka | DELAY | 100 | 99 | 0.71 | 585728682000 | 5857286820 | 5857286820 | ZAKY AHMAD | ROSIDAH |  | ["K.TEL.1017-0094\/HK.810\/DES-A1000000\/2017"] | 4.Keterlambatan BAST (customer) | 27/03/2019 17:09:47
PROJ779 |  | ORDINARY | PROJECT CORE INSURANCE SYSTEM ASKRINDO | APPLICATION | 14-NOV-17 | 20-DEC-19 | ASURANSI KREDIT INDONESIA | HWS | PT Sigma Cipta Caraka, PT Sigma Cipta Caraka | LAG | 75.03 | 62.07 | -12.96 | 10792188000 | 1398667564.8 | 4093476908.4 | ZAKY AHMAD | JOKO PADANG RAHINO |  |  | 8.CR (perubahan yang belum terkendali) & amandemen (customer) | 27/03/2019 15:12:22
PROJ852 |  | ORDINARY | PENYEDIAAN DIGITAL MENU BOARD BURGER KING INDONESIA 159 STORE | CPE DEVICES | 01-FEB-18 | 30-NOV-19 | MAP FOOD & BEVERAGE | THS | PT Teltranet Aplikasi Solusi (Telkom Telstra), PT Teltranet Aplikasi Solusi (Telkom Telstra), PT Teltranet Aplikasi Solusi (Telkom Telstra), PT Teltranet Aplikasi Solusi (Telkom Telstra), PT Teltranet Aplikasi Solusi (Telkom Telstra) | LAG | 83.72 | 89.94 | 6.22 | 3728736000 | 375110841.6 | 375110841.6 | HASBUR GHALI | EVY YULIA RAMADHAN |  |  | 2.Kesiapan lokasi ( customer) | 27/02/2019 11:37:38
PROJ928 | LOP25066 | MEGA | PENGADAAN SEWA 12.000 UNIT EDC BNI UNTUK PT. BRINGIN GIGANTARA | CPE DEVICES | 15-JAN-18 | 31-DEC-19 | BANK RAKYAT INDONESIA (PERSERO) | BMS-1 | PT Sigma Cipta Caraka | LAG | 100 | 34.13 | -65.87 | 57000000000 | 37545900000 | 37545900000 | RUDIONO | RUDY WIBOWO | K.TEL.02-0022/HK.810/DES-A00000000/2018 |  | 2.Kesiapan lokasi ( customer) | 13/03/2019 16:34:12
PROJ2486 | LOP106379 | ORDINARY | PEKERJAAN INSTALASI ELEKTRIKAL PADA PROYEK PEMBANGUNAN GEDUNG HK OFFICE | SMART BUILDING | 13-AUG-18 | 15-DEC-18 | HUTAMA KARYA PT | PCS | PT PINS Indonesia | DELAY | 100 | 60.162 | -39.837 | 7425000000 | 2957971500 | 2957971500 | AD STEFEN RATU EDA | GATHUT SUKANDARTO | K.TEL.08-0922/HK.810/DES-00/2018 |  | 2.Kesiapan lokasi ( customer) | 18/03/2019 11:34:46
PROJ2789 | LOP107494 | ORDINARY | PERPANJANGAN JASA DEDICATED COLOCATION DATA CENTER UNTUK BANK SYARIAH MANDIRI | APPLICATION | 01-FEB-18 | 31-JAN-19 | BANK SYARIAH MANDIRI | BMS-1 | PT Sigma Cipta Caraka | DELAY | 100 | 0 | 0 | 6500000000 | 6500000000 | 6500000000 | FAHMI RAHMANTHAHA NURDINSYAH | FARAINY ADINDA GITAWARDHANI | K.TEL.03-0414/HK.820/DES-00/2018 |  |  | 27/03/2019 15:18:30
PROJ2875 | LOP107762 | ORDINARY | PENGADAAN CASH MANAGEMENT SYSTEM BANK MANTAP (BANK MANDIRI TASPEN POS) | CPE DEVICES | 27-SEP-18 | 16-APR-19 | BANK MANDIRI TASPEN POS (MANTAP) | BMS-1 | PT Sigma Cipta Caraka | LAG | 71 | 67 | -4 | 1245000000 | 49800000 | 410850000 | ZAKY AHMAD | SUPADMI |  |  | 8.CR (perubahan yang belum terkendali) & amandemen (customer) | 27/03/2019 17:06:01
PROJ3062 | LOP108175 | MEGA | PENGADAAN UPGRADE 230 SERVER DI DC GTI DAN TABANAN UNTUK PT. BANK RAKYAT INDONESIA (PERSERO), TBK | APPLICATION | 12-OCT-18 | 30-APR-19 | BANK RAKYAT INDONESIA (PERSERO) | BMS-1 | PT Signet Pratama | LAG | 100 | 97.35 | -2.65 | 69027000000 | 1829215500 | 1829215500 | RUDIONO | RUDY SETYO NUGROHO | K.TEL.09-0837/HK.850/DES-00/2018 |  | 2.Kesiapan lokasi ( customer) | 27/03/2019 15:20:05
PROJ3160 | LOP108197 | REGULAR | PENGADAAN PENGEMBANGAN SISTEM APLIKASI OFFICE AUTOMATION JAMKRINDO | APPLICATION | 08-OCT-18 | 28-DEC-18 | GD. JAMKRINDO | FMS | PT Sigma Cipta Caraka | DELAY | 100 |  |  | 953447000 |  |  | MUTTAQIN NASUTION | MULYADI, ST | K.TEL.10-0228/HK.810/DES-FMS/2018 |  |  | 01/04/2019 12:38:16
PROJ3185 | LOP108406 | MEGA | PENGADAAN MITRA PENGELOLA UNIT LAYANAN BPJS KETENAGAKERJAAN | CPE DEVICES | 12-OCT-18 | 31-JAN-19 | BPJS KETENAGAKERJAAN | HWS | PT Infomedia Nusantara | DELAY | 100 | 84.3 | -15.7 | 50000000000 | 7850000000 | 7850000000 | ADRID | SUSILO IRAWAN | K.TEL.10-0349/HK.850/DES-HWS/2018 |  | 1.Delivery barang/jasa (mitra) | 25/03/2019 09:52:25
PROJ3385 | LOP109311 | ORDINARY | PENGADAAN PENINGKATAN KAPASITAS CLUSTER CLOUDERA BIG DATA | APPLICATION | 30-OCT-18 | 30-APR-19 | BANK RAKYAT INDONESIA (PERSERO) | BMS-1 | PT Metra-Net | LAG | 99.51 | 0 | -99.51 | 11220000000 | 11165022000 | 11220000000 | ARIA OCTA | RUDY SETYO NUGROHO | K.TEL.11-0393/HK.850/DES-00/2018 |  | 2.Kesiapan lokasi ( customer) | 27/03/2019 15:03:46
PROJ3530 | LOP109710 | BIG | IMPLEMENTASI BIG DATA KIMIA FARMA | CPE DEVICES | 22-NOV-18 | 22-NOV-19 | KIMIA FARMA PT | HWS | PT Metra-Net | LAG | 69.62 | 48.5 | -21.12 | 21720155875 | 4587296920.8 | 11185880275.625 | ZAKY AHMAD | MELANY ULFA | K.TEL.11-0645/HK.850/DES-00/2018 | null | 10.Keterbatasan kapabilitas mitra (mitra) | 28/03/2019 14:57:18
PROJ3533 | LOP109736 | ORDINARY | PEKERJAAN INSTALASI PUBLIC ADDRESSOR DAN INFRASTRUKTUR PENDUKUNG OPERASIONAL DI FIELD JATIBARANG DAN TAMBUN PT PERTAMINA EP ASSET 3 | SMART BUILDING | 23-NOV-18 | 31-MAR-19 | PERTAMINA PT | ERS | PT PINS Indonesia | DELAY | 100 | 100 | 100 | 1484746749 | 0 | 0 | TEUKU HAMIZUL | REIKA ERMANSA | K.TEL.12-0062/HK.810/DES-ERS/2018 | null |  | 31/03/2019 19:45:44
PROJ4258 | LOP144611 | MEGA | PENGADAAN MANAGED SERVICE OFFSITE DATA CENTER (ODC), DATA CENTER (DC) GTI RAGUNAN DAN TABANAN TAHAP 1(MENGACU PADA SPK B.79.P-PBJ/PIT/01/2019) | APPLICATION | 23-JAN-19 | 30-MAY-19 | BANK RAKYAT INDONESIA (PERSERO) | BMS-1 | PT Sigma Cipta Caraka | LAG | 97.78 | 71.99 | -25.79 | 149500000000 | 38556050000 | 41874950000 | RUDIONO | RUDY SETYO NUGROHO | K.TEL.01-0675/HK.850/DES-00/2019 |  | 1.Delivery barang/jasa (mitra) | 27/03/2019 15:21:59
PROJ4590 | LOP110476 | MEGA | PEKERJAAN TICKETING SYSTEM ENVIRONMENT PT ASDP INDONESIA FERRY (PERSERO) | CPE DEVICES | 12-MAR-19 | 13-MAR-19 | ANGKUTAN SUNGAI DANAU DAN PENYEBERANGAN PT (ASDP) | MLS | PT NUTECH INTEGRASI | DELAY | 100 | 0 | 0 | 165447509220 | 165447509220 | 165447509220 | ARIEF SUSILO WIBOWO | IDHAM | K.TEL.03-0013/HK.850/DES-00/2019 | null | 3.Perubahan desain/spek pelanggan (customer) | 01/04/2019 10:36:17